## All Districts
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## Central
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## KC
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## NE
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## NW
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## SE
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## SW
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## SL
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA) | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## Bridges (hidden)
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## P&M (hidden)
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## PD Team (hidden)
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## Direct Recipient (hidden)
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | PODI (If yes check box) | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | CD0007 CD0108 | 0633118 0633119 | Rte. 63 Corridor Upgrade | Scoping for corridor improvements and environmental study from Rte. 50 to Rolla. Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Osage |  | Corridor improvements | Pursley, Charles (FHWA);#37;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 |  |  | Core Team Member;#EA/EIS Core Team | [7 empty] | 2022-09-27 09:57 | Scheulen, Ashley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Design Build Procurement;#AJR Approval;#Interstate Designation Request |  | AJR (if required), Interstate De-designation, NEPA EA review/approval, Design-Build procurement |  |  |  | FY 21 and 22: FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. MoDOT and the MPO have differing positions on what option should be selected as the preferred alternative and this has created significant delays in the completion of NEPA. FHWA continues to be engaged with MoDOT on the progress of the ongoing EA through project update meetings with MoDOT and their consultant. This project will be retained as a FY23 PoDI. |  | 2022-09-21 16:50 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-10-10 | Pavement and Bridge | Irving, Kevin (FHWA);#29;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. |  |  | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting | Construction Inspections;#Work Zone/TMP;#Erosion Control;#Pavement/Materials Review |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. PY22 activity: Provided guidance and feedback on a rough draft of the BUILD Grant agreement in October 2021 and submitted revised version to Alison Rogers and revised accordingly and resubmitted for further review. Coordinated and participated in multiple meetings with MoDOT to establish a plan forward to advertising the project once the ROD is signed for the main reservoir project and OST agrees to the grant agreement. Provided guidance to MoDOT staff and have answered many questions on the BUILD process during many meetings. Participated and provided feedback at 6 core team meetings in October, November, January, March, April, and May. Briefly reviewed the 90% plans package and provided feedback at a core team meeting. Coordinated in November with HQ on approach to resolve issue with delay of main reservoir project including drafting a position memo from the Division Office. Facilitated the completion of the grant agreement that is awaiting signature by FHWA after the PS&E is approved. Conducted in depth coordination with FMIS, Design, and environment to advance the project to Final PS&E. Construction authorization is in FMIS awaiting approval. Project is scheduled for an October, 2022 letting. Compile and submit bi-weekly reports on time for HQ to remain informed. Provided updates to Division Office staff and management on project updates and issues at the September, November, January, March, and May All Employee meetings as well as routine discussion and coordination with team leader to keep her apprised of the project status and issues. This project will be retained as a FY 23 PoDI for construction involvement. |  | 2022-09-27 10:12 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | 0703295 | J2I3274 I70 RR Overpass at High Hill | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | Montgomery |  | Reconstruction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member |  |  | Work Zone/TMP |  |  |  |  | 2022-09-20 14:44 | Miller, John P (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 IS70 Stracks Church Interchange | Scoping for interchange improvements at Stracks Church County Road near Wright City. | Warren |  | Interchange | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval |  | attended project meeting 4/21/22 | [5 empty] | 2022-09-14 11:43 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 I70/Mo 19 Roundabouts | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | Montgomery | 2022-06-17 | Interchange | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Title VI;#Construction Inspections |  |  | JS sent email to Lauren and Taylor 6/15/22 informing project has been let and moving to construction |  | 2022-09-26 17:45 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson | 2023-07-31 | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval;#Core Team Member;#Design Build Procurement |  | The previously approved AJR will be reevaluated and updated. Title VI review. |  |  |  | PY22: Participated in and provided guidance and expectations at a meeting with MoDOT and consultant on 12/2/21 of what is to be included in the updated AJR that will be developed for the corridor. Will implement new AJR policy requiring only the two Traffic Safety and Operational analysis points. The rest of the points are to be addressed in the NEPA document. As of 8/15/22 FHWA participated in 4 project update meetings in early 2022 where the MoDOT consultant provided an update on the EIS reevaluation. |  | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | not assigned | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification will require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#AJR Approval;#Design Exception Approval;#Core Team Member |  | Core team member. AJR is required and design exception approval. |  |  |  | PY22: Participated in and provided project guidance at both the October 20 and November 18th, 2021 core team meetings including AJR requirements and expectations and project specific considerations for safety. I also met in a separate meeting with MoDOT on November 16th to provide details and expectations on the AJR and our new policy approach. Participated in core team meetings in January, February, April, May, and July 2022. The project draft AJR was submitted to FHWA in July, 2022. FHWA provided review comments in August and September, 2022. This project will be retained as an FY23 PoDI. |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3087 | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22;#FY23 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | FMIS Authorization;#Core Team Member;#PEL |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added; Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted.MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. PY22 value added: Provided guidance to MoDOT on requirements for developing the consultant solicitation document. Reviewed the consultant solicitation document to assure that it was consistent with the BUILD grant agreement. Executed the BUILD grant agreement on 2/17/22. Since August 15, 2022 a total of 26 bi-weekly reports have been submitted to HQ. The FMIS agreement was signed in March, 2022. Submitted 5 monthly BUILD reports thru July, 2022. Assisted MoDOT with getting two new staff members access to UPACS/ORC so that they can submit quarterly reports. Coordinated a response to additional funding needs sent by HQ for possible additional BUILD 20 funds—MoDOT replied that they would not request additional funds. An addendum may be needed to add additional scope to the consultant agreement to conduct additional public meetings. FHWA MO is coordinating with HQ to determine if an addendum is needed to include this additional scope even though the additional work will be 100% state funded. |  | 2022-09-19 18:30 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY20;#PY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  |  |  | Construction Inspections;#Bridge Inspection |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21-Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21.Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. PY22-Reviewed and provided comments to revised project AJR and issued approval in August 2021. Submitted all required monthly project reports through April 15, 2022 (9 monthly reports submitted in PY22 through April 15th). Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan (QOP) in coordination with the Division Office Pavement and Materials Engineer. Approval provided for the QOP. Conducted 5 construction inspections including 2 Work Zone Traffic Control reviews, 1 Buy America, 1 Certified Payroll review, and an erosion control checklist review. Findings were communicated to MoDOT via inspection report for response. Participated in the initial Executive Partnering meeting in the fall of 2021 and a quarterly partnering meeting in early 2022. Reviewed and approved 10 change orders through 8/15/22. Provided comments including requesting an independent cost estimate to support the price for the Case Wall change order. Coordinated a project tour for the Missouri Division Office staff that was done on September 16, 2022. This project will be retained as a FY23 PoDI project for construction inspections. |  | 2022-09-27 10:50 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Scheulen, Ashley (FHWA);#22;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. FY 2022 - I participated in design team meetings and plan reviews. as well as construction status meetings. I reviewed and concurred in the Rte. BB interchange plans and insured conformatce with interstate access requirements. Approved the I-70 emergency access elimination request. A work zone review was conducted and suggested improvements were provided. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397 J5I3572 | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. | Construction Inspections;#Work Zone/TMP;#Bridge Inspection;#Pavement/Materials Review |  |  | Project was marked for PS&E review for FY 2021. However the PS&E was completed and advertised before FY2021. Bids were received that were too high so the project was re-let in spring of 2022. FY - 2023 |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3414 | not assigned | I-44 Flood Resiliency Improvements | Scoping for flood improvements at the Gasconade River. Potential Design-Build. | Laclede |  | Reconstruction | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3411 J5I3107 | 0633113 0703261 | I-70 Improvements DB project in Columbia | Modify interchange configuration at I-70, I-70 Ramps, I-70 Added lanes. Potential Design-Build project in Columbia | Boone |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Other |  | Core Team Member;#Design Exception Approval |  | TS&O Approval was granted on 06-21-2022. Attended several Core Team Member Meetings. |  |  |  | OINCC was granted on 11-29-2021. TS&O: Suggest adding a Tables in the Intermediate Build section including results from all three future scenarios. | VE Study scheduled / OINCC submittal / Major Project | 2022-09-26 18:03 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Local Considerations |  | Core Team Member |  |  | Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  | no construction activities have been performed this FY22 |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY20;#PY19;#FY22;#FY23 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Pavement/Materials Review |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2022-09-27 10:15 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22;#FY23 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections;#VECP Approval |  |  | FY 2022-suggest improving pedestrian accomodatioins along the project. Suggest improvements in the plans adding better diagrams and safety features. FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination.FY 2022 |  | 2022-09-26 17:47 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments;#Conceptual Report Review | [6 empty] | Part of I-270 North Major project / EA reval | 2022-08-23 13:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Environmental and Stakeholders;#Local Considerations;#National/Regional Significance;#Complexity;#Other |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#Title VI;#VECP Approval;#Design Build NTP |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed.FY 2022 |  | 2022-09-26 17:59 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 J6I3500 | 2553052 255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review |  |  | Construction Inspections |  | no construction activities have been performed this FY22 |  | VE Study | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B - SL0020 | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  |  | Title VI |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 SL0057 | Interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification |  | Review Alternative Screening & Traffic Forecast |  |  |  |  | System to System Interchange / EIS reval | 2022-09-26 16:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3660 | not assigned | J6I3660 - SL0058 - SL0086 | Roadway improvements from the Missouri River to east of North Hanley Road. Project involves various bridges. Potential Design Build. Including Lambert Airport I-70 Improvements | St. Louis |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Cost;#Project Administration |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Title VI |  |  |  |  | 2022-09-26 17:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 JP3496B | S502067 S502089 | J6P3496 & J6P3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Cost;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  | Core Team Member | [7 empty] | 2022-09-26 17:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I0797C | 0712062 | I-49 Jasper Co. | Re. I-49/ Rte. 171 Interchange in Carthage | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 17:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3010 SU0146 | not assigned | I-44 Webster and Greene Co. | Pavement resurfacing, realign curve 3.5 miles east of Rte. 125 and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. Rebuild pavement on the westbound lanes. | Webster |  | Reconstruction | Pursley, Charles (FHWA);#37;#McGee, Mike (FHWA);#31 | No | TRUE | FY23 | Complexity;#Schedule |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review |  |  |  |  | 2022-09-27 10:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations |  |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | FY 2022 - Participated in DB procurement process and approved all DB document including the RFP. Participated in desing meetinga s well as construction progress meetings. The initial construction inspection was made on 7/6/2022. The buletin board locatoin requirements were clarified and multiple boards will be required. The requirements for the complete wage rates clarified and corrected. FY2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0797M | 0711074 | Rte. I-49/I-44 Interchange, Jasper Co. | Scoping for roadway improvements at the I-49 and Rte. 59 interchange in Fidelity | Jasper |  | Interchange | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 |  |  | Core Team Member | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P3485 | 0492434 | I-49 and other various bridges rebuild DB | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build | Bates |  | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#FMIS Authorization | [7 empty] | 2022-09-26 16:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Project Administration;#Local Considerations | Bridge replacement using ATC |  |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  | Construction delayed until FY2023. FY 2023 - |  | 2022-09-27 10:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I3044C SU0076 | 0442337 | I-44 Added lanes in Springfield | Add lanes and replace bridges from Rte. 13 to Rte. 65 in Springfield. Interchange improvements at I-44 and Rte. 13. | Greene |  | Widen and Resurface | Pursley, Charles (FHWA);#37 | No | TRUE | FY23 | Complexity;#Corporate Actions |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2022-09-26 16:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 | 0615042 | J9P3122 I55/US 1 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY22;#FY23 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [5 empty] | attended core team meeting 6/8/22, discussed top 3 configurations and safety and traffic model results |  | 2022-09-27 10:51 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 Chester Bridge | Chester Bridge | Perry | 2022-09-02 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#Conditional Clearance | [5 empty] | 7/20/22 - observed SOQ review and group discussion. 7/21/22 - attended and observed team interviews. Reviewing Book 1 and 2 and providing comments to team. 8/1/22 - attended and observed short list evaluation meeting with MoDOT exec team. |  | 2022-09-27 10:48 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 | 0191016 | J9P3305 Mo19 | Scoping for bridge improvements over Current River and Round Spring. | Shannon |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74;#Peters, Taylor (FHWA);#43 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations | 404 permitting, NEPA Commitments | Core Team Member;#Scoping;#Environmental Commitments |  | Attended progress meeting 4/26/22, borings have started and working on environmental document, plan for April 23 report. Attended EA Progress meeting 8/30/22. Geotech report has been resubmitted, report on Cultural Resources with Osage, survey will be completed within next couple months. Will advance EA as far as can without the cultural in order to move as quickly as can. Will be addressing FHWA comments and reviewing with MoDOT. |  |  |  | 3/18/2022 reviewed proposal for additional boring for bridge due to inconclusiveness of previous geotech work. Did site visit on May 19 and 20 with environmental to talk through project impacts, etc. Asked to include in discussion on purpose and need report why not considering other side of current river bridge location and to consider pedestrain accessbility since currently have provided a pedestrian bridge and what will be required if relocate ped bridge. |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 Phase 3 Future I57 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | Butler |  | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review | [5 empty] | Attended VE Presentation on 2/22/22 |  | 2022-09-15 22:20 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 Phase 1 Future I57 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | Butler | 2022-05-20 | Pavement and Bridge | Stotlemeyer, Julie (FHWA);#74;#McGee, Mike (FHWA);#31 | No | TRUE | FY21;#FY22;#FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 |  |  |  | Construction Inspections;#Pavement/Materials Review |  |  | Provided recommendation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2022-09-27 10:17 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 | 0671028 | J9P3751 Phase 2 Future I57 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler | 2023-05-19 | Widen and Resurface | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member;#Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-15 21:46 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 | 0604085 | J9S3381 Black River Bridge | Bridge replacement over Black River. Project involves bridge K0263. | Butler | 2022-02-18 | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY22;#FY23 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections |  |  | Project has been delayed til mid-July due to need agreement and right of access with RR and relocation of mussels. |  | 2022-09-15 21:47 | Stotlemeyer, Julie (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#PY20;#FY20;#FY22;#FY23 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America;#Civil Rights/Cert Payroll |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2022-09-23 10:48 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  |  |  |  | Environmental Commitments;#Construction Inspections;#Work Zone/TMP;#Civil Rights/Cert Payroll |  |  | FY 2021 & 2022 - The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. The grant agreement was executed on 8/31/2021. Inital construction inspection made on 7/5/2022. Work zone items and wage rates o the bulletin board were corrected. FY 2023 - |  | 2022-09-26 18:00 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  |  |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Civil Rights/Cert Payroll |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted.FY 2022 |  | 2022-09-26 17:46 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22;#FY23 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll |  | Construction inspections with focused review checklists. | PY21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. PY22: Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ and received approval and facilitated the execution of the agreement. Submitted all monthly BUILD reports as required. Assured recipient submits quarterly reports and am coordinating performance reporting with the City. Provided guidance to the City and MoDOT that facilitated the first of BUILD funds to be reimbursed in FMIS. The project is approximately 50% complete. This project will be retained as a FY23 PoDI.. |  | 2022-09-23 10:52 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22;#FY23 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#Design Exception Approval |  |  | Civil Rights/Cert Payroll |  |  |  |  | 2022-09-26 17:54 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9901521 | TAP in St. Elizabeth | TAP ADA improvements in St. Elizabeth. Install pedestrian facilities along Church Street at the Saint Elizabeth School to the Track on Jefferson Street | Miller |  | ADA/Sidewalk | Pursley, Charles (FHWA);#37;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 |  |  | Core Team Member;#Design Preliminary Plans |  |  | Construction Inspections;#ADA;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 590982 | Kansas Expressway Extension Phase 1 | West Republic Street to Plainview Road (Farm Road 182) | Greene |  | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY23 | [5 empty] | Environmental Commitments;#Civil Rights/Cert Payroll |  |  |  |  | 2022-09-23 10:57 | Paulwell, Lauren (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 Brickline Greenway | construct a roughly 1.3 mile greenway segment consisting of separated, multi-use paths alongside major roadways from Fairground Park to Page Boulevard, as one of the first segments of the 20-mile Brickline Greenway. | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Funding;#Project Administration;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE-21 West Florissant Great Street | reconstruct approximately 1.5 miles of West Florissant Avenue, a principal arterial in the Greater St. Louis area, from Stein Road to Ferguson Avenue, through the towns of Dellwood and Ferguson. The project includes a new shared-use path, upgrades to transit stops, new traffic signals, medians, modified property access, new crosswalks, and improved ADA-compliant sidewalks. The project will also relocate bus stops, pedestrian wayfinding, and create new greenspace and landscaping. Pedestrian-scale lighting will also be included | St. Louis City |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Cost;#Schedule;#Environmental and Stakeholders;#Project Administration;#Funding;#Corporate Actions;#Local Considerations;#Other | Direct Recipient Discretionary Grant | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design 90% Review;#Design PSandE Review;#Design PSandE Approval;#Design Exception Approval;#Environmental Commitments;#Special Funding;#End Date;#FMIS Authorization;#Conditional Clearance;#Section 106 Review;#Section 4(f) Review;#Appraisal Process;#Significant Relocations;#Advanced Acquisition;#Other | [7 empty] | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II-Noland Multimodal Corridor | RAISE II project. The project will create an approximate 1.7-mile multimodal corridor along the pre-existing Noland Road. It includes adding dedicated north and south bound bike lanes, replacement of more than three miles of derelict sidewalks to be ADA compliant, push button pedestrian signals, and transit stop improvements. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY22;#FY23 | Discretionary Grant and Financing;#Schedule;#Environmental and Stakeholders;#Local Considerations;#Other | RAISE Discretionary Grant awarded to a direct recipient | Core Team Member;#Special Funding;#FMIS Authorization;#Design PSandE Approval |  | Facilitating the completion of the RAISE Grant Agreement and final PS&E package for advertisement. Reporting on project status to HQ and OST. |  |  |  | FY22:&nbsp; Completed congratulatory call with the City of Independence on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | RAISE II: South Main Corridor Improvement Project Phase II | RAISE II Project. This Capital project for Phase II of the South Main Corridor Improvement Project will build on ongoing work to relieve congestion and safely connect residents in underserved neighborhoods to jobs and services via the South Main Street corridor, a common route to downtown. The Phase II planning project, which will analyze crash data includes reviewing existing traffic conditions, lane configurations, signal spacing and timings, traffic control devices, crash patterns and availability of sidewalks and bike routes along the corridor. | Nodaway |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Project Administration;#Local Considerations | RAISE II discretionary grant. | Core Team Member;#Design PSandE Approval;#FMIS Authorization;#Other |  | RAISE reporting, Facilitating the completion of the RAISE grant agreement and approval of the final PS&E package for advertisement. | Construction Inspections |  | Construction inspection using one or more focused review checklists. | FY22:&nbsp; Conducted congratulatory phone call with Greg McDanel of the City of Maryville on 8/24/22. |  | 2022-09-27 10:56 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Project: US 69 Safe Streets & Sidewalks | The project will rebuild approximately 2 miles of existing streets with curb, gutter, storm drainage, and sidewalks, add approximately 2.3 miles of sidewalk along existing streets, and add approximately 2.5 miles of trail along US-69. The project also includes nine intersections improvements, with signal modifications, round-abouts or pedestrian overpasses. | Clay |  |  | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Cost;#Funding;#Project Administration;#Local Considerations | RAISE II discretionary grant with a direct recipient. | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#Design PSandE Approval;#Special Funding;#FMIS Authorization |  | RAISE project reporting. Facilitating the completion of the RAISE grant agreement and final PS&E package for advertisement. |  |  |  | FY22:&nbsp; Conducted congratulatory phone call with the City of Excelsior Springs on 8/19/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | Direct | RAISE II Study Project: US 71 Reconnecting Neighborhoods | This planning project includes a Planning and Environmental Linkages study, NEPA analysis, and conceptual design for US 71, from 85th Street north to Dr. Martin Luther King Jr. Boulevard in Kansas City. | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29;#Scheulen, Ashley (FHWA);#22;#Peters, Taylor (FHWA);#43 | No | TRUE | FY23 | Discretionary Grant and Financing;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Local Considerations;#Project Administration;#Other | RAISE II Discretionary Grant with a direct recipient. Existing Consent Decree. PEL and NEPA study. | Core Team Member;#Special Funding;#FMIS Authorization;#PEL;#EA/EIS Core Team |  | RAISE II project status reporting, Facilitation of the completion of the RAISE II grant agreement. |  |  |  | FY22: Completed a congratulatory phone call to the City of Kansas City, MO on 8/22/22. |  | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | B023028 | BRO B023 (028) BRO LPA Bridge Clark County |  | Clark |  | Bridge Replacement | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Schedule;#Project Administration;#Corporate Actions;#Local Considerations |  |  |  |  | Construction Inspections |  |  |  |  | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 9900095 | TAP-9900(095) LPA Project St. Francois County | Rte M Sidewalk | St. Francois |  | ADA/Sidewalk | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Project Administration;#Schedule;#Local Considerations |  | Design PSandE Review;#Design Preliminary Plans | [7 empty] | 2022-09-27 10:58 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NE0005 | not assigned | NE0005 US61 Hannibal Expressway | Scoping for Hannibal Expressway (Environmental Study) from Rte. F in Marion County to south of Rte. M in Ralls County | Marion |  | New Construction | Stotlemeyer, Julie (FHWA);#74 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#Corporate Actions |  | Core Team Member;#Scoping;#Conceptual Report Review | [7 empty] | 2022-09-27 10:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NW0026 | Not assigned | Design-Build Bridge replacement project | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. | Mercer | 2024-05-31 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Stotlemeyer, Scott (FHWA);#39 | No | TRUE | FY23 | Complexity;#Cost;#Project Administration;#Schedule | Multiple bridge replacements in various counties delivered by Design-Build contracting method which is first for the district. | FMIS Authorization;#Design Build Certification;#Design Build AAS Concur;#Design Build Procurement;#Core Team Member | [7 empty] | 2022-09-20 18:43 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | SL0021 | not assigned | SL0021 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY23 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Conceptual Report Review;#AJR Approval | [7 empty] | 2022-09-27 10:55 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans