# JOB SPECIAL PROVISIONS TABLE OF CONTENTS (ROADWAY)

# (Job Special Provisions shall prevail over General Special Provisions whenever in conflict therewith.)

A.	General

B.	Project Contact for Contractor/Bidder Questions

- Scope of Work

D.	Job Order Contract

E.	Procedures for Developing a Job Order

F.	Term of Contract

G.	Fixed Unit Price List

- Adjustment Factors

- Bidding the Adjustment Factors

J.	Contract Award

K.	Bonds

- Accelerated Repair

- Notice to Proceed

- Completing the Work

- Final Inspection and Acceptance of the Work

- Liquidated Damages for Failure or Delay in Beginning and/or Completing Work On Time

- Liquidated Damages Specified for Accelerated Repair Response

- Liquidated Damages Specified for Lane Closures

- Liquidated Damages for Winter Months

- Contract Payments

- Work Zone Traffic Management Plan

- Traffic Control Plan Types

- Pavement Marking

- Delay Provisions

- Eliminated Materials

- Sample Job Orders

- Emergency Provisions and Incident Management

- Utilities

- Damage to Existing Pavement

- Full Depth Pavement Repair Requirements

- Mobilization

- Supplemental Revisions

- Concrete Masonry Repair

- Previous Job Order Information

- Safety Plan

- Railroad Requirements

- Safety Requirements

ADDITIONAL INFORMATION

Graphic Representation of Personal Protective Equipment

| “THIS MEDIA SHOULD NOT BE CONSIDERED A CERTIFIED DOCUMENT.” | MISSOURI HIGHWAYS AND TRANSPORTATION COMMISSION 105 W. CAPITOL AVE. JEFFERSON CITY, MO 65102 Phone 1-888-275-6636 |
| --- | --- |
|  | If a seal is present on this sheet, JSP’s have been electronically sealed and dated. |
|  | JOB NUMBER: JXXXXXXX VARIOUS COUNTIES, MO DATE PREPARED: 02/18/2013 |
|  | ADDENDUM DATE: |
| Only the following items of the Job Special Provisions (Roadway) are authenticated by this seal: ALL |

# JOB

# SPECIAL PROVISIONS

A.	GENERAL - FEDERAL JSP-09-02A

1.0  Description.  The Federal Government is participating in the cost of construction of this project.  All applicable Federal laws, and the regulations made pursuant to such laws, shall be observed by the contractor, and the work will be subject to the inspection of the appropriate Federal Agency in the same manner as provided in Sec 105.10 of the Missouri Standard Specifications for Highway Construction with all revisions applicable to this bid and contract.

1.1  This contract requires payment of the prevailing hourly rate of wages for each craft or type of work required to execute the contract as determined by the Missouri Department of Labor and Industrial Relations, and requires adherence to a schedule of minimum wages as determined by the United States Department of Labor.  For work performed anywhere on this project, the contractor and the contractor’s subcontractors shall pay the higher of these two applicable wage rates. State Wage Rates, Information on the Required Federal Aid Provisions, and the current Federal Wage Rates are available on the Missouri Department of Transportation web page at www.modot.org under "Bidding".  Effective Wage Rates will be posted 10 days prior to the applicable bid opening.  These supplemental bidding documents have important legal consequences.  It shall be conclusively presumed that they are in the bidder's possession, and they have been reviewed and used by the bidder in the preparation of any bid submitted on this project.

1.2  The following documents are available on the Missouri Department of Transportation web page at www.modot.org under "Business"; “Standards and Specifications”. The effective version shall be determined by the letting date of the project.

General Provisions & Supplemental Specifications

Supplemental Plans to October 2009 Missouri Std. Plans

For Highway Construction

These supplemental bidding documents contain all current revisions to the bound printed versions and have important legal consequences.  It shall be conclusively presumed that they are in the bidder's possession, and they have been reviewed and used by the bidder in the preparation of any bid submitted on this project.

B.	PROJECT CONTACT FOR CONTRACTOR/BIDDER QUESTIONS

1.0	Any questions relating to the bidding process or concerning the bid document preparation shall be directed to the Central Office Design Division to:

Mr. Jason Vanderfeltz

Bidding and Contract Services Engineer

MoDOT – Central Office

Telephone Number: (573) 526-2923

Email: Jason.Vanderfeltz@modot.mo.gov

# ***INSERT DISTRICT CONTACT INFORMATION HERE***

2.0	Upon award and execution of the contract, the successful bidder/contractor shall forward all questions and coordinate the work with the contract administrator.  The contract will be administered and inspected by the engineer/contract administrator listed below:

***INSERT DISTRICT CONTACT INFORMATION HERE***

C.	SCOPE OF WORK

1.0	The scope of work for this project is to provide concrete pavement repair on an as needed basis in response to sudden occurrences, such as physical damage by the elements, or as a result of wear and tear.  The work will be prescribed through individual Job Orders issued to the contractor by the engineer for each work location.

2.0	A work location for this contract shall be limited to a 2-mile section of roadway.  A 2-mile section shall be defined as 2 miles in one direction on a divided highway or 2 miles in both directions on an undivided highway.

3.0	The project limits for the work will be along the following Interstate Routes and Counties  ***insert list of Counties and Routes***.:

4.0	Job Orders will only be issued for work to be performed from April 1 to November 30, unless otherwise mutually agreed upon between the contractor and the engineer.

5.0	The Commission is not bound to issue a minimum or maximum number of Job Orders during the contract term.  It is the intent, however, to meet the anticipated budget, as noted elsewhere within this proposal.  Award of contract does not guarantee any Job Orders during the duration of the contract.

D.	JOB ORDER CONTRACT

1.0 	A Job Order Contract is an indefinite quantity contract pursuant to which the contractor shall perform the work itemized in a Job Order at individual work locations throughout the project limits.  The contractor shall perform all tasks itemized in the Job Order.

2.0	The engineer will identify the required work at an individual work location in collaboration with the contractor at a Joint Scope Meeting.  The engineer will provide the contractor with a draft Detailed Scope of Work which the contractor shall review.  Once the detailed Scope of Work is agreed upon, the engineer will issue a Job Order to the contractor.  At any given time the contractor may be performing more than one Job Order.

3.0	The contract includes a list of fixed cost pay items with fixed unit prices.  Payment for the work will be determined by multiplying the fixed unit prices by an applicable Adjustment Factor.  The contractor shall bid three separate Adjustment Factors to be applied to the fixed unit prices as applicable for work performed during normal working hours, nighttime hours or weekend hours as defined elsewhere in this contract.  The total cost of an individual Job Order will be determined by multiplying the fixed unit prices of each fixed cost pay item by the appropriate quantity and then multiplying the total cost of all pay items by the appropriate Adjustment Factor.

4.0	Definitions.

4.1	Detailed Scope of Work.  A written document that sets forth the work the contractor is obligated to perform in connection with a particular Job Order.

4.2	Job Order.  A written order from the engineer to the contractor directing the work required at an individual work location in accordance with the Detailed Scope of Work within the Job Order Completion Time.

4.3	Job Order Completion Time.  The time within which the contractor must complete the Detailed Scope of Work for a particular Job Order.

4.4	Fixed Cost Pay Item.  Work for which a description and fixed cost is set forth in the fixed cost pay item list.

4.5	Non-Fixed Cost Pay Item.  Work for which a description and fixed cost is not set forth in the pay item list.  Payment for non-fixed cost pay items will be determined in accordance with Sec 109.4.2, 109.4.3, or 109.4.4.  Non-fixed cost pay items will be paid using an Adjustment Factor of 1.000.

E.	PROCEDURES FOR DEVELOPING A JOB ORDER

1.0	Initiation of a Job Order.  The engineer will notify the contractor of a potential Job Order by issuing a Notice of Joint Scope Meeting.  The notification will be issued by electronic mailing or facsimile machine at the discretion of the engineer to the contractor, unless the engineer approves other arrangements.  The contractor shall confirm receipt of all job orders by the same means as issued.  Notification for accelerated repair work can be initiated by telephone.

1.1	The contractor shall attend the Joint Scope Meeting and be prepared to discuss, at a minimum:

- The general scope of the work;

- Existing conditions, presence of waterways, wetlands, or other natural resources,

- Presence of hazardous materials

- Methods and alternative for accomplishing the work;

- Access to the site;

- Staging area availability/location;

- Requirements for catalog cuts, technical data, samples and shop drawings;

- Requirements for professional services, including sketches, drawings, and specifications;

- Hours of operation;

- Anticipated working days and schedule;

- Liquidated damages;

- Specific quality requirements for equipment and material;

- List of anticipated Subcontractors and Material Suppliers.

1.2	Upon completion of the joint scoping process, the engineer will prepare a draft detailed Scope of Work referencing any sketches, drawings, photographs, and specifications required to document accurately the work to be accomplished.  The contractor shall review the detailed Scope of Work and request any desired changes or modifications thereto.  When an acceptable detailed Scope of Work has been completed, the engineer will issue a Draft Job Order.

1.3	The contractor does not have the right to refuse to perform any Job Order or any work identified in a Job Order.  If the contractor refuses to perform any Job Order or any work identified in a Job Order, the contractor may be considered to be in default in accordance with Sec 108.

2.0	Preparation of the Job Order.  The engineer will prepare a Draft Job Order and submit the order to the contractor for final review.  The contractor and the engineer will jointly review the Draft Job Order and finalize the order.  Establishment of pricing for any non-fixed cost pay items shall be in accordance with Sec 109.4.2 or 109.4.3.  If no agreement to pricing can be made then the work will proceed with payment for non-fixed cost items under Sec 109.4.4.

2.1	When the engineer and contractor have agreed to the scope of work and Fixed Cost and Non-Fixed Cost tasks to be performed, the engineer will finalize the official Job Order and submit a signed Job Order for the contractor to review and sign.  The affixed signatures by the engineer and the contractor shall bind the Job Order.  If the contractor is not clear or in disagreement with the terms of the Job Order he shall NOT sign the Job Order, but shall work with the engineer to clear up any discrepancies in the work to be done.  If the contractor fails to execute the Job Order, the contractor may be considered to be in default in accordance with Sec 108.

3.0	The Commission reserves the right to cancel or reject a Job Order for any reason.  The Commission also reserves the right not to issue a Job Order if that is determined to be in the best interests of the Commission.  The contractor shall not recover costs arising out of or related to the development of the Job Order including but not limited to the costs to attend the Joint Scope Meeting, review the Detailed Scope of Work, subcontractor costs, and the cost to review the Job Order Proposal with the Commission.

4.0	Job Order Issuance.  The Job Order will be signed by the engineer and delivered to the contractor.  The Job Order will reference the Detailed Scope of Work and set forth the amount to be paid and the time to complete the work.

5.0	Notice to Proceed.  Each Job Order will include a notice to proceed, which will stipulate the date the contractor is expected to begin work.  The notice to proceed date will normally be within 14 calendar days after the job order is issued.  For Job Orders that require an accelerated response, contractors shall respond to the work location and begin the accelerated repair work within 5 calendar days of the notice to proceed established in the Job Order.

5.1	The contractor shall provide 48-hour notification prior to start of repair work for accelerated Job Orders and 5-days notification for all other Job Orders.

F.	TERM OF CONTRACT

1.0	The term of this contract shall be for the period commencing ***Insert Date*** and shall end ***Insert Date***.

1.1	Any work already ordered or in progress when the contract term ends shall be completed in accordance with the provisions, price proposals and timelines established in the issued Job Order(s), or liquidated damages will be assessed against the contractor in accordance with the provisions of this contract.

2.0	The contract may be extended under the original terms and contract prices for the period commencing ***Insert Date*** and shall end ***Insert Date*** for a maximum contract term of two (2) years.  If, in the sole discretion of the Commission, the Commission desires to extend the contract, the contractor will be given written notification of the extension no later than December 1 of the current contract year.  The contractor shall provide written notification of acceptance or rejection of the extension of this contract no later than January 1 of the current contract year. If the option for extending the contract is exercised by MoDOT, a time adjustment change order will be issued by the Commission to extend the contract to the new term limits.  The contractor shall increase the performance contract bond to an amount equal to the original contract amount plus the extended contract amount (i.e., double the original bond amount).

G.	FIXED UNIT PRICE LIST

1.0   Description.  A fixed unit price list containing unit prices associated with concrete pavement repair is listed below.  Fixed unit prices are for complete and in-place construction and include all labor, equipment and material required to complete the construction task.  All labor, material, equipment and work required by a specification shall be considered part of the fixed unit price, unless otherwise stated elsewhere in this contract.  Pay limits will be defined in the approved Job Order.

2.0  Fixed Unit Price List for Concrete Pavement Repair Job Orders.

| Item Number | Description | Unit | Fixed Unit Price |
| --- | --- | --- | --- |
| 3039905 | 18 in. Rock Base (Removal, Furnish & Place) | SY | $50.00 |
| 6059903 | Underdrainage – 6 in. Perf Plastic Pipe w/ Geotextile | Lin Ft | $7.25 |
| 6123000A | Truck Or Trailer Mounted Attenuator (TMA) | Each | $750.00 |
| 6131012 | Subgrade Compaction | SY | $5.25 |
| 6131013 | Type 1 or 5 Aggregate | SY | $6.50 |
| 6131014 | Full Depth Saw Cuts | Lin Ft | $7.25 |
| 6131015 | Dowel Bar (Drill, Furn and Install) | Each | $8.00 |
| 6131017 | Dowel Bar (Furn. & Install with Basket) | Each | $7.00 |
| 6131018 | Tie Bar (Drill, Furn and Install) | Each | $7.00 |
| 6132014 | Class A Partial Depth Repair Saw Cuts | Lin Ft | $5.00 |
| 6139905 | Full Depth Repair (10 -100 sy) > 12" | SY | $195.00 |
| 6139905 | Full Depth Repair (10 -100 sy) < 12" | SY | $185.00 |
| 6139905 | Full Depth Repair (100.1 - 500 sy) > 12" | SY | $125.00 |
| 6139905 | Full Depth Repair (100.1 - 500 sy) < 12" | SY | $120.00 |
| 6139905 | Full Depth Repair (> 500 sy) < 12" | SY | $105.00 |
| 6139905 | Removal of Concrete Material for Partial Depth Repair (0-200 sy) | SY | $110.00 |
| 6139905 | Removal of Concrete Material for Partial Depth Repair (> 200 sy) | SY | $90.00 |
| 6139907 | Furnish/Placing Material for Partial Depth Repair (0 – 50 cy) | CY | $525.00 |
| 6139907 | Furnish/Placing Material for Partial Depth Repair (> 50 cy) | CY | $425.00 |
| 6161005 | Construction Signs | SF | $3.00 |
| 6161008 | Advanced Warning Rail System | Each | $45.00 |
| 6161009 | Flag Assembly | Each | $6.00 |
| 6161025 | Channelizer (Trim Line) | Each | $9.00 |
| 6161030 | Type III Moveable Barricade | Each | $75.00 |
| 6161033 | Directional Indicator Barricade | Each | $18.75 |
| 6161040 | Flashing Arrow Panel | Each | $390.00 |
| 6161055 | Sequential Flashing Warning Light | Each | $50.00 |
| 6161098 | CMS, contractor Furnished/Retained | Each | $1,200.00 |
| 6169902 | Single Lane Closure | Each | $3,000.00 |
| 6169902 | Double Lane Closure | Each | $3,900.00 |
| 6169902 | Interior Lane Closure | Each | $3,900.00 |
| 6169902 | Triple Lane Closure | Each | $4,500.00 |
| 6169902 | Ramp Closure | Each | $1,800.00 |
| 6169902 | One-Lane Two-Way Operation with Flagger | Each | $3,000.00 |
| 6189902 | Accelerated Repair | Each | $3,000.00 |
| 6189902 | Mobilization-Full Depth Repair | Each | $4,800.00 |
| 6252003 | Slab Jacking Material High Density Polyurehane | LB | $5.25 |
| 7049904 | Bridge Deck Approach Slab Repair (Full Depth) | SF | $40.00 |
| 7049904 | Bridge Deck Approach Slab Repair (Partial Depth) (Over 200 SF) | SF | $35.00 |
| 7049904 | Bridge Deck Approach Slab Repair (Partial Depth) (0-200 SF) | SF | $70.00 |

H.	ADJUSTMENT FACTORS

1.0	Description.  Adjustment Factors include business and construction related costs as defined in this specification.  It is the responsibility of the contractor to verify the unit prices provided in this contract and to modify their Adjustment Factors accordingly.

1.1	Business Costs.  Business related costs consist of profit, overhead costs, subcontractor profit and overhead, taxes, finance costs, and other costs including but not limited to;

- insurance, bonds and indemnification

- project meetings, training, management and supervision

- project office staff and equipment

- employee or subcontractor wage rates that exceed prevailing wages

- fringe benefits, payroll taxes, worker’s compensation, insurance costs and any other payment mandated by law in connection with labor that exceeds the labor rate allowances.

- Business risks such as the risk of low than expected volumes of work, smaller than anticipated Job Orders, poor subcontractor performance, and inflation or material cost fluctuations.

1.2	Construction Costs.  Construction related costs include but are not limited to;

- personnel safety equipment

- security requirements

- excess material waste

- daily and final clean-up

- costs resulting from inadequate supply of materials, fuel, electricity, or skilled labor

- costs resulting from productivity loss

- working in extreme and adverse weather conditions

- any other discreet items of work required to complete a particular Job Order.

1.3	General Costs.  The above lists are not exhaustive and are intended to provide general examples of cost items to be included in the contractor’s Adjustment Factors as defined in the contract.

2.0	Normal Work Adjustment Factor.  The Adjustment Factor for Normal Working Hours includes work conducted from 6:00 a.m. to 7:30 p.m. Monday through Friday.

2.1  In addition to the time period specified in 2.0, work performed during Normal Working Hours must also be done during daylight hours, unless the contractor provides the necessary lighting equipment.  Daylight hours are defined as ½ hour after sunrise to ½ hour before sunset.  If the contractor chooses to work during Normal Working Hours, but outside of the defined daylight hours, the contractor shall provide lighting equipment at no additional cost to the Commission.

3.0	Nighttime Work Adjustment Factor.  If the engineer determines traffic volumes are such that work cannot be performed during the daytime, Monday through Friday, without significant traffic impacts, the Job Order will specify nighttime repair operations. The Adjustment Factor for Nighttime Work includes any work conducted from 7:30 p.m. to 6:00 a.m. Monday through Thursday.

3.1	Any costs for additional lighting equipment necessary to perform nighttime repair operations is considered included in the Nighttime Work Adjustment Factor.

4.0	Weekend Work Adjustment Factor.  If the engineer determines traffic volumes are such that work cannot be performed Monday through Friday without significant traffic impacts, the Job Order will specify weekend repair operations.  The Adjustment Factor for Weekend Work includes any work conducted from 7:30 p.m. on Friday through 6:00 a.m. on Monday, night or day, or a Holiday.

4.1	All work shall be scheduled to avoid major holidays.  During the term of this contract there are three major holiday periods:  Memorial Day, Independence Day and Labor Day.  All lanes shall be scheduled to be open to traffic during these holiday periods, from 12:00 noon on the last working day preceding the holiday until 9:00 a.m. on the first working day subsequent to the holiday, unless designated as Weekend Work by the engineer.

5.0	The Adjustment Factor for Nighttime Work and Weekend Work will not be applied to adjust the unit bid price(s) unless the contractor is specifically directed to perform Nighttime or Weekend Work by the engineer as part of the Job Order.  If the Job Order does not otherwise restrict nighttime or weekend hours, the contractor may, with the approval of the engineer, perform some or all of the repair operations during nighttime or weekend hours but will paid for the Adjustment Factor specified in the Job Order (i.e. the contractor may be allowed to complete nighttime work on the weekend but will be paid the Nighttime Adjustment Factor).

I.	BIDDING THE ADJUSTMENT FACTORS

1.0	The bidder shall complete the bid form by writing in three Adjustment Factors, one for Normal Working Hours one for Nighttime Work and one for Weekend Work.  The Adjustment Factors shall be specified to three decimal places.  Note that these are contract pay items for contractor payment, not work items.

EXAMPLE:  The Adjustment Factors shall be entered as the following example illustrates.

1 . 1 9 8

OR

0 . 9 8 7

Note:  The Adjustment Factors used are for example purposes only and are not an indication of factors being bid by the contractor.

J.	CONTRACT AWARD

1.0	The Commission will evaluate the bids with the intent of awarding the contract to the lowest responsible bidder.  The anticipated budget for this project is $1,000,000.

2.0	The lowest bid will be determined by multiplying each individual Adjustment Factor by the anticipated budget for each individual adjustment factor.  For purposes of determining award of this contract, the estimated percentage of work performed during Normal Working Hours is 10%, the estimated percentage of Nighttime work is 85%, and the estimated percentage of Weekend work is 5%.  The extended amount for each item will then be totaled, and the total sum will be used for bid comparison purposes.  The initial contract value will be equal to the total sum.  The dollar quantities provided in the bid form are anticipated budgets and are not intended to represent the actual value of work that will be assigned.

EXAMPLE:  The initial contract value is determined by entering the Adjustment Factors as the following example illustrates:

| Item Description | Approximate Quantity | Unit | Unit Price | Bid Amount |
| --- | --- | --- | --- | --- |
|  |  |  | Dollar | Cts | Dollar | Cts |
| 6189916 Normal Work Adjustment Factor | 100,000.00 | DLR | 1.150 | 115,000.00 |
| 6189916 Nighttime Work Adjustment Factor | 850,000.00 | DLR | 1.200 | 1,020,000.00 |
| 6189916 Weekend Work Adjustment Factor | 50,000.00 | DLR | 1.250 | 62,500.00 |
| Bid Total |  |  |  | 1,197,500.00 |

Note:  The Adjustment Factors used are for example purposes only and are not an indication of factors being bid by the contractor.

K.	BONDS

1.0	The amount of the Bid Bond shall be 5% of the anticipated budget for this project.

2.0	The amount of the Performance Bond shall be 100% of the anticipated budget for this project.

L.	ACCELERATED REPAIR

1.0	If the engineer determines the safety of the public is unduly compromised by the damaged facility, the work will be designated as an accelerated repair.  Commission forces or others will initially respond to the location and perform such work as necessary to reduce the immediate danger to the public.

2.0	The contractor will be notified by telephone of the location of the accelerated repair and extent of work needed.  Written confirmation of the required work will be provided by fax, e-mail or personal delivery immediately after notification.  The contractor shall provide a means for the engineer to contact the contractor 24 hours a day for emergencies.   The Job Order will be negotiated and issued by the Commission within 48 hours of notification to the contractor.  It is estimated that accelerated repair could occur up to 5 times during the term of this contract.

3.0	The contractor shall respond to the work location and begin the accelerated repair work within 5 calendar days of the notice to proceed established in the Job Order.  After beginning the accelerated repair work, the contractor shall continuously and diligently pursue the work according to the mutually agreed upon schedule in the Job Order until all of the repairs described in the Job Order are complete, unless otherwise approved by the engineer.

4.0	The contractor will be paid a one-time Accelerated Repair payment for beginning the accelerated repair work within the required 5 calendar days of the Notice to Proceed.  An Adjustment Factor will not be applied to the Accelerated Repair payment.  All other items necessary to complete the repair work will be paid for at the fixed unit price multiplied by the Normal, Nighttime or Weekend Adjustment Factor, as mutually agreed upon in the Job Order.

M.	NOTICE TO PROCEED

Delete Sec 108.2 and substitute the following:

108.2	Notice to Proceed.  For each Job Order, the engineer will include a notice to proceed, which will stipulate the date the contractor is expected to begin work.  The notice to proceed date will normally be 14 calendar days after the job order is issued.

108.2.1	Job orders that require an accelerated response will normally have a notice to proceed of 5 calendar days after the job order is issued.  Response time for accelerated repairs will commence at the time telephone contact is made with the contractor.

N.	COMPLETING THE WORK

1.0	The contractor shall perform any task in the fixed unit price list for the fixed unit price multiplied by the quantity, multiplied by the appropriate Adjustment Factor for tasks performed during Normal Working Hours or for tasks performed during Nighttime or Weekend hours.  The contractor shall perform the Detailed Scope of Work for the Job Order Price as calculated in accordance with the procedure for developing Job Orders set forth herein.

2.0	When installed quantities differ from the estimated quantities in the issued Job Order, the as built quantities in the final Job Order will address the quantity variation(s) for final payment.  When quantities are not specified in the Detailed Scope of Work, the Job Order Price will be deemed to be lump sum for such work.

3.0	The contractor shall employ and supply a sufficient force of workers, materials and equipment and shall progress the work with such diligence so as to ensure completion of the Detailed Scope of Work within the Job Order completion Time or within such extended time for completion as may be granted by the engineer.

4.0	In order to assist in reviewing the Job Order Price Proposal, the contractor shall as part of the Job Order Proposal prepare and submit to the engineer for approval, a progress schedule showing the order in which the contractor proposes to carry on the work, the date of which it will start the major items of work (including but not limited to excavation, drainage, paving, structures, mobilization, soil erosion and sediment control, etc.) and the critical features (including procurement of materials, plant and equipment) and the contemplated dates for completing the same.

O.	FINAL INSPECTION AND ACCEPTANCE OF THE WORK

Delete Secs 105.10.7 through 105.10.7.2 and substitute the following:

105.10.7	Final Inspection.  Upon completion of the required work for each Job Order, the contractor shall notify the engineer by phone, facsimile, or electronic mailing, and the engineer will perform an inspection.  If the engineer determines all work required by the contract has been satisfactorily completed, the engineer will make the acceptance for maintenance and notify the contractor in writing of the date of acceptance for maintenance.

105.10.7.1	Work determined to be unsatisfactory by the engineer and not accepted shall be corrected to acceptable standards at the contractor’s sole cost.  All items that are unsatisfactory shall be corrected within the specified working days for each job order.  If needed for correction of unsatisfactory work, the contractor will be given an extension of contract time in an amount equal to the number of working days remaining in the job order at the time the engineer was notified for inspection.  No contract time extension will be made for notification made prior to completion of the work.  Any time extension given will be considered a noncompensable delay.  Upon completion of the corrections, the contractor shall notify the engineer for a reinspection.

105.10.7.2	Following a Job Order final inspection, the contractor, subcontractors, and suppliers are relieved of any new or additional liability to third parties for personal injury, death, or property damages which may be alleged to result from the performance of the work required by that job order, unless additional work on the right of way is required by the engineer.

105.10.7.3	Nothing in this section shall be deemed to excuse the contractor of liability or responsibility for any personal injury, death, or property damages which may arise from acts or the failure to act prior to the final inspection of the work required by the Job Order.

P.	LIQUIDATED DAMAGES FOR FAILURE OR DELAY IN BEGINNING WORK AND/OR COMPLETING WORK ON TIME

1.0	Description.  If the contractor, or in case of default, the surety fails to begin the work by the notice to proceed date or fails to complete the work within the mutually agreed schedule included in each job order, the Commission, the traveling public, and state and local police and governmental authorities will be damaged in various ways, including but not limited to, increased construction administration cost, potential liability, traffic and traffic flow regulation cost, traffic congestion and motorist delay, with its resulting cost to the traveling public.  These damages are not reasonably capable of being computed or quantified.  Therefore, the contractor will be charged with liquidated damages specified in the amount of $1000.00 per day for each full day that the work is not started and $1000.00 per day for each full day that the work is not completed within the required time periods. It shall be the responsibility of the engineer to determine the quantity of excess time.

2.0	The said liquidated damages specified for beginning work and/or completing work will be assessed in addition to any other applicable liquidated damages specified elsewhere in the contract documents.

Q.  	LIQUIDATED DAMAGES SPECIFIED FOR ACCELERATED REPAIR RESPONSE

1.0	Description.  For work designated as accelerated repair work, if the accelerated repair work is not started within the required 5 calendar days of the Notice to Proceed, the Commission, the traveling public, and state and local police and governmental authorities will be damaged in various ways, including but not limited to, increased construction administration cost, potential liability, traffic and traffic flow regulation cost, traffic congestion and motorist delay, with its resulting cost to the traveling public.  These damages are not reasonably capable of being computed or quantified.  Therefore, the contractor will be charged with liquidated damages specified in the amount of $250.00 per hour for each full hour that the accelerated repair work is not started within the required 5 calendar days of the Notice to Proceed, in excess of the limitation as specified elsewhere in this special provision.  It shall be the responsibility of the engineer to determine the quantity of excess time.

2.0	The contractor will be charged with liquidated damages specified in the amount of $250.00 per hour for each full hour that the accelerated repair work is not completed beyond the mutually agreed upon schedule established in the Job Order, in excess of the limitation as specified elsewhere in this special provision.  It shall be the responsibility of the engineer to determine the quantity of excess time.

3.0	The said liquidated damages specified for accelerated repair response will be assessed in addition to any other applicable liquidated damages specified elsewhere in the contract documents.

R.  	LIQUIDATED DAMAGES SPECIFIED FOR LANE CLOSURES

1.0	Description.  The contractor shall be required to have all lanes open to unrestricted traffic and free of any equipment by the time specified in Job Order for each closure location. Should the contractor fail to have the roadway completely open, and free of any equipment by the time specified in Job Order, the Commission, the traveling public, state and local police and governmental authorities will be damaged in various ways, including but not limited to potential liability, traffic and traffic flow regulation cost, traffic congestion and motorist delay, with its resulting cost to the traveling public.   These damages are not reasonably capable of being computed or quantified.   Therefore, the contractor will be charged with liquidated damages specified in the amount of $1,000 per 15 minutes for each 15-minute increment that the roadway is not open and free of any equipment, in excess of the limitation as specified elsewhere in the special provision.   It will be the responsibility of the engineer to determine the quantity of excess closure time.

1.1	The said liquidated damages specified will be assessed in addition to any other liquidated damages charged under the Missouri Standard Specifications for Highway Construction, as indicated elsewhere in this contract.

1.2	This deduction will continue until such time as the necessary work is completed and traffic is restored.

2.0	A contingency plan mutually agreed upon by the contractor and the engineer shall be established at the joint meeting and documented in each Job Order in the event of a delay of the scheduled traffic opening time due to weather or other unforeseen circumstances.

S.	LIQUIDATED DAMAGES FOR WINTER MONTHS JSP-04-17

1.0	Description.  Revise Sec 108.8.1.2 (a) and (b) and substitute the following for the project:

(a)  Liquidated damages will be assessed from December 15 to March 15

(b)  Liquidated damages will be assessed for Saturdays, Sundays and Holidays.

T.	CONTRACT PAYMENTS

1.0	The engineer will make semi-monthly payment estimates in writing for the Job Orders completed and final inspected during the semi-monthly interval and the value thereof at the price established in the Job Order, including any necessary adjustments.  The semi-monthly estimates will include deductions from the contractor’s invoice for any liquidated damages applicable to any of the Job Orders.

U.	WORK ZONE TRAFFIC MANAGEMENT PLAN

1.0	Description.   The contractor may be responsible for the work zone traffic management as mutually agreed upon by the contractor and engineer for each individual Job Order.  Work zone traffic management shall be in accordance with applicable portions of Division 100 and Division 600 of the Standard Specifications, and specifically as follows.

2.0	Work Zone Scheduling.

2.1	The contractor shall notify the engineer at least 48 hours prior to performing any work at each work site.  The notification shall include all information needed to identify traffic impacts such as work location, anticipated work hours, traffic control plan type, required lane or shoulder closures, anticipated duration of the work, etc.  The contractor shall designate a contact person who is available for the duration of the work to resolve any traffic impact issues resulting from the contractor’s operations.  The engineer will make appropriate notification to the public, MoDOT customer service, and MoDOT work crews of the contractor's operations.  The contractor shall notify the engineer as soon as practical any postponement due to weather, material, or other circumstances and shall notify the engineer when the work has been rescheduled.

2.2	In order to ensure minimal traffic interference, the contractor shall schedule lane closures for the absolute minimum amount of time required to complete the work.  Lanes shall not be closed until material is available for continuous construction and the contractor is prepared to diligently pursue the work until the closed lane is reopened to traffic.

2.3	Traffic shall be maintained through the work zone using the existing pavement.  Provisions shall be made to allow the movement of emergency vehicles through the limits of construction at all times.  During non-working hours the contractor shall have all lanes of traffic open for all routes, ramps, and sideroads.  All channelizers and other traffic control devices shall be removed from the roadway during non-working hours unless otherwise approved by the engineer.

2.4	The contractor shall be responsible for maintaining the existing traffic flow through the job site during construction.  If disruption of the traffic flow occurs and traffic is backed up in queues of 15 minute delays or longer, then the contractor shall review the construction operations which contributed directly to disruption of the traffic flow and make adjustments to the operations to prevent queues from occurring again.

2.5	No direct payment will be made to the contractor to recover the cost of the communication equipment, labor, materials or time required to fulfill the above provisions.

3.0	Work Hour Restrictions.

3.1	During non-working hours the contractor shall have all lanes of traffic open for all routes, ramps, and side roads.  Working hours for weekends and holidays shall be determined by the engineer.

3.2	Due to the wide variance in traffic volumes throughout the contract area, it is not possible to give specific work hours for the term of the contract.  Each Job Order will specify work hours or work hour restrictions based on the repair location, this may include peak hour restrictions.  The following table provides general guidance as to the most restrictive schedule for when work on or adjacent to the roadway may be allowed.

Traffic Control Plan Type	Work Hours (Monday thru Friday)

Single Lane Closure	7:30 p.m. 	to 4:30 a.m.

Double Lane Closure	9:30 p.m. 	to 4:30 a.m.

Triple Lane Closure	10:00 p.m. 	to 4:30 a.m.

Interior Lane Closure	9:30 p.m. 	to 4:30 a.m.

Ramp Closure	Hours and days as approved by the engineer

One Lane Two Way Operation	Hours and days as approved by the engineer

with Flagger

Specific work hours for an individual work location shall be according to the mutually agreed upon schedule in the Job Order.  All work shall be scheduled to avoid major sporting events, conventions, concerts, etc.

4.0	Ramp Closure.  Ramp closures shall be minimized and shall be approved by the engineer a minimum of five days prior to the closure.  Only one ramp closure will be permitted in a particular interchange or complex at one time.  Work on acceleration / deceleration lanes will not require ramp closure unless approved by the engineer.  Detour traffic handling details will be as specified by the engineer.  Major ramp closures may require detour signing with other ramp closures only requiring use of changeable message signs (CMS) for detours.  If the engineer determines detour signing is required, all necessary detour trailblazing placards will be furnished, installed, and covered by others. The contractor shall furnish all CMS required by the engineer.  The contractor shall be responsible for uncovering and covering the trailblazing placards as work progresses.

5.0	Changeable Message Signs.  The contractor shall provide changeable message signs notifying motorists of future traffic disruption and possible traffic slow down one week before traffic is shifted to a detour.  The changeable message sign installation shall be placed at a location as approved or directed by the engineer.

6.0	Basis of Payment.  All items necessary to complete the traffic control will be paid for at the fixed unit price multiplied by the Normal, Nighttime or Weekend Adjustment Factor, as mutually agreed upon in the Job Order.

V.  	TRAFFIC CONTROL PLAN TYPES

1.0	Description.  The following traffic control plan types shall be used for the job orders issued for this contract.

2.0	Plan Types.

2.1	Single Lane Closure.  A single lane closure shall be performed by furnishing, installing, and removing the following set of traffic control devices.

2 each		Road Work Ahead

2 each		Reduced Speed Ahead

2 each		Speed Limit XX MPH

4 each		Work Zone (Plaque)

2 each		Right (Left) Lane Closed Ahead

2 each		Right (Left) Lane Closed

2 each		Speed Limit XX (Normal Speed)

12 each	Flag Assembly

14 each	Directional Indicator Barricade

30 each	Channelizer (Trim Line)

2 each		Flashing Arrow Panel	(One Truck Mount for TMA)

1 each		Truck Mounted Attenuator

1 each		Changeable Message Sign (Contractor Furnished / Retained)

2.2	Double Lane Closure.  The contractor shall obtain approval from the engineer prior to any double lane closure.  A double lane closure shall be performed by furnishing, installing, and removing the following set of traffic control devices.

2 each  	Road Work Ahead

2 each  	Reduced Speed Ahead

4 each 	Speed Limit XX MPH

6 each		Work Zone (Plaque)

2 each 	Right (Left) Lane Closed Ahead

2 each 	Right (Left) Two Lanes Closed Ahead

4 each  	Right (Left) Lane Closed

2 each		Speed Limit XX (Normal Speed)

18 each	Flag Assembly

28 each	Directional Indicator Barricade

100 each	Channelizer (Trim Line)

3 each		Flashing Arrow Panel 	(One Truck Mount for TMA)

1 each		Truck Mounted Attenuator

1 each		Changeable Message Sign (Contractor Furnished / Retained)

2.3	Interior Lane Closure.  The contractor shall obtain approval from the engineer prior to any interior lane closure.  An interior lane closure shall be performed by furnishing, installing, and removing the following set of traffic control devices.

2 each  	Road Work Ahead

2 each  	Reduced Speed Ahead

2 each 	Speed Limit XX MPH

4 each		Work Zone (Plaque)

2 each 	Left (Right) Lane Closed Ahead

2 each  	Left (Right) Lane Closed

2 each		Speed Limit XX (Normal Speed)

12 each	Flag Assembly

14 each	Directional Indicator Barricade

100 each	Channelizer (Trim Line)

3 each		Flashing Arrow Panel 	(One Truck Mount for TMA)

1 each		Truck Mounted Attenuator

1 each		Changeable Message Sign (Contractor Furnished / Retained)

2.4	Triple Lane Closure.  The contractor shall obtain approval from the engineer prior to any triple lane closure.  A triple lane closure shall be performed by furnishing, installing, and removing the following set of traffic control devices.

2 each  	Road Work Ahead

2 each  	Reduced Speed Ahead

6 each 	Speed Limit XX MPH

8 each		Work Zone (Plaque)

4 each 	Right (Left) Lane Closed Ahead

2 each 	Right (Left) 3 Lanes Closed Ahead

6 each  	Right (Left) Lane Closed

2 each		Speed Limit XX (Normal Speed)

24 each	Flag Assembly

42 each	Directional Indicator Barricade

70 each	Channelizer (Trim Line)

4 each		Flashing Arrow Panel 	(One Truck Mount for TMA)

1 each		Truck Mounted Attenuator

1 each		Changeable Message Sign (Contractor Furnished / Retained)

2.5	Ramp Closure.  The contractor shall obtain approval from the engineer a minimum of five days prior to any ramp closure.  A ramp closure shall be performed by furnishing, installing, and removing the following set of traffic control devices.  Uncovering and covering any detour trailblazing placards furnished and installed by others is included in the work.

2 each  	Road Work Ahead

2 each 	Speed Limit XX MPH

4 each		Work Zone (Plaque)

2 each 	Ramp Closed Ahead

2 each 	Detour Ahead

1 each 	Road Closed

2 each		Speed Limit XX (Normal Speed)

10 each	Flag Assembly

14 each	Directional Indicator Barricade

40 each	Channelizer (Trim Line)

2 each		Flashing Arrow Panel 	(One Truck Mount for TMA)

1 each		Truck Mounted Attenuator

2 each		Changeable Message Sign (Contractor Furnished / Retained)

3 each		Type III Movable Barricade

2.6	One-Lane Two-Way Operation with Flaggers.  A minimum of two flaggers will be required to direct traffic.  Additional flaggers may be required when working at intersecting streets or ramps as directed by the engineer.  No direct payment will be made for flaggers.  “One-Lane Two-Way Operation with Flaggers”, shall include furnishing, installing, and removing the following set of traffic control devices as shown on the plans:

2 each		Road Work Ahead

2 each 	One Lane Road Ahead

2 each	 	Be Prepared To Stop

2 each		Flagger (Symbol)

3.0	Additional Traffic Control Devices.  The engineer may determine that signs, channelizers, and Type III Movable Barricades in addition to those devices shown in the plans are necessary to safely accommodate traffic.  These additional devices may be needed for merging ramp traffic, detours, multiple bridges, or other special cases to supplement the specified lane closure devices.  The contract provides a fixed cost for any additional traffic control items.

4.0	Flaggers.  Flaggers may be required when working at intersecting streets or ramps as directed by the engineer.  No direct payment will be made for flaggers.

5.0	Method of Measurement and Basis of Payment.

5.1	Measurement of lane closures will be made per Job Order.   Payment will be made for a maximum of one (1) of each lane closure type at a specific work location, within the maximum 2 mile range, per job order.   Payment will not be made for any lane closure that does not result in productive repair work as determined by the engineer.  Additional lane closures may be installed by the contractor at his expense.  The accepted quantity of each lane closure will be paid for at the fixed unit price for:

Item 616-99.02	Single Lane Closure					Each

Item 616-99.02	Double Lane Closure					Each

Item 616-99.02	Interior Lane Closure					Each

Item 616-99.02	Triple Lane Closure					Each

Item 616-99.02	Ramp Closure						Each

Item 616-99.02	One-Lane Two-Way Operation with Flaggers	Each

multiplied by the Normal, Nighttime or Weekend Adjustment Factor, as mutually agreed upon in the Job Order.

5.2	Measurement of additional traffic control devices will be made per Job Order.  Payment for the devices shall include furnishing, installing, and removing the additional devices at a specific work site.  No payment will be made for additional devices used by the contractor without prior approval of the engineer.  The accepted quantity of additional traffic control devices will be paid for in accordance with the fixed unit price list, multiplied by the Normal, Nighttime or Weekend Adjustment Factor, as mutually agreed upon in the Job Order.

W.	PAVEMENT MARKING

1.0	Description.  The contractor will not be responsible for placing and maintaining pavement marking on pavement undergoing repair operations unless mutually agreed upon in the Job Order.

X.	DELAY PROVISIONS

1.0	If the contractor is delayed in the commencement, prosecution or completion of the work by any act of the Commission, or by any cause beyond the contractor’s control, then the contractor will be entitled to an extension of time.  If the contractor is delayed or prevented from working on a particular date as a result of a delay, error or omission of the Commission, and the contractor incurs unavoidable labor costs as a direct result thereof because the contractor did not have enough time to cancel or divert its labor force, then the contractor will be reimbursed for such costs.  For each worker so paid, the contractor will be reimbursed the amount paid the worker.  Also, the contractor will be reimbursed for construction tasks required as a direct result of such delay, error or omission, such as closing off areas of work.  No other costs shall be paid as a result of a delay or late cancellation.

1.1	If the contractor fails to provide 48-hour notification prior to start of accelerated work or 5-days notification for all other Job Orders this provision will not apply.

Y.	ELIMINATED MATERIALS

1.0	Materials required by the Detailed Scope of Work and not incorporated into the work due to changes caused by field conditions or revisions to the design by the Commission after the material was ordered or purchased will be reimbursed at the material portion of the Pre-priced Task, or if there is no Pre-priced Task, then its material cost minus salvage value, or the material cost plus delivery costs.

Z.	SAMPLE JOB ORDERS

1.0	The following are example Job Orders intended to be illustrations that may be used as a guide for formulating the bid of the Adjustment Factor.  For each example Job Order, the appropriate items that would be used and the quantities are computed based upon the sample work that would be completed in the Job Order.  The contractor shall be reminded these are Job Order samples and the quantity totals in actual Job Orders, if issued, may be more or less than that depicted below or be totally different from the samples illustrated.

1.1	Job Order Sample 1:  Repair Area = 3 - 6’ X 12’, full depth pavement repairs.  Existing pavement thickness is 10” concrete.  All repairs are located within a 1-mile long, 2-lane segment of the interstate with all repairs in the same lane.  Location does not have significant daytime peak hour ADT so off-peak nighttime work is not required to accommodate a daytime lane closure.

| Item Description | Fixed Unit Price | Quantity | Price |
| --- | --- | --- | --- |
| Full Depth Saw Cuts | $7.25 | 108 LF | $783.00 |
| Dowel Bars (Drilling, Furnishing, and Installation) | $8.00 | 60 Each | $480.00 |
| Full Depth Pvmt. Repair (10 – 100 SY) Less than or equal to 12” Thick | $185.00 | 24.0 SY | $4,440.00 |
| Mobilization – Full Depth Pavement Repair | $4,800 | 1 Each | $4,800.00 |
|  |  | Subtotal: | $10,503.00 |
| Normal Work Factor | 1.150 |  |  |
|  |  | TOTAL: | $12,078.45 |

1.2	Job Order Sample 2:  Repair Area = 8 - 9’ X 24’, full depth pavement repairs.  Existing pavement thickness is 14” composite asphalt over concrete (8” concrete + 6” asphalt overlay).  All repairs are located within a 1-mile long, 2-lane segment of the interstate with the repairs across the entire width of the 2-lane segment.  Since the repairs are in both lanes the work will be required over two separate days since the contractor can occupy only one lane of the roadway.  Location is a high ADT location so off-peak nighttime hours are required with reopening to traffic before the next morning rush period.  Location requires quick response due to safety concerns.

| Item Description | Fixed Unit Price | Quantity | Price |
| --- | --- | --- | --- |
| Full Depth Saw Cuts | $7.25 | 768 LF | $5,568.00 |
| Dowel Bars (Drilling, Furnishing, and Installation) | $8.00 | 320 Ea | $2,560.00 |
| Full Depth Pvmt. Repair (100.1 – 500 SY) Greater than 12” Thick | $125.00 | 192.0 SY | $24,000.00 |
| Mobilization – Full Depth Pavement Repair | $4,800.00 | 1 Each | $4,800.00 |
|  |  | Subtotal: | $36,928.00 |
| Nighttime Work Factor | 1.200 |  |  |
|  |  | Subtotal: | $44,313.60 |
| Accelerated Repair | $2,200.00 | 1 Each | $2,200.00 |
|  |  | TOTAL: | $46,513.60 |

1.3	Job Order Sample 3:  Repair Area = 1 - 400’ X 14’, full depth pavement repair.  Existing pavement thickness is 11” composite asphalt over concrete (8” concrete + 3” asphalt overlay).  The entire section is badly deteriorated and has been patched multiple times so the entire outside lane and a portion of the outside shoulder will be removed and reconstructed.  Location is a high ADT location, but due to the length of repair two continuous closure days will be required to complete the work.  To accommodate traffic a weekend closure will be used so the entire 400’ section can be removed and replaced at one time without reopening.  The existing aggregate base and subgrade is in poor/unstable condition.

| Item Description | Fixed Unit Price | Quantity | Price |
| --- | --- | --- | --- |
| Full Depth Saw Cuts | $7.25 | 3,457 LF | $25,063.25 |
| Subgrade Compaction (6 in. Depth) | $5.25 | 622.2 SY | $3,266.55 |
| Type 1 or 5 Aggregate for Base (4 in. Thick) | $6.50 | 622.2 SY | $4,044.30 |
| Dowel Bars (Drilling, Furnishing, and Installation) | $8.00 | 24 Each | $192.00 |
| Dowel Bars (Furnishing and Installing with Baskets) | $7.00 | 300 Each | $2,100.00 |
| Tie Bars (Drilling, Furnishing, and Installation) | $7.00 | 160 Each | $1,120.00 |
| Full Depth Pvmt. Repair (Greater than 500 SY) Less than or equal to 12” Thick | $105.00 | 622.2 SY | $65,331.00 |
| Mobilization – Full Depth Pavement Repair | $4,800.00 | 1 Each | $4,800.00 |
|  |  | Subtotal: | $105,917.10 |
| Weekend Work Factor | 1.200 |  |  |
|  |  | TOTAL: | $127,100.52 |

1.4	Job Order Sample 4:  Repair Area = 3 - 24’ X 14’, 2 - 18’ X 12’, 5 - 12’ X 18’ full depth pavement repairs.  Pavement thickness is 12” composite asphalt over concrete (8” concrete + 4” asphalt overlay).  All repairs are located within a 2-mile, 3-lane segment of the interstate with the repairs scattered across the entire width of the 3-lane segment.  Since the repairs are in all three lanes, the work will be required over two separate days since the contractor must leave at least one lane of the roadway open for traffic.  A double lane closure is allowed during off-peak hours.  Location is a high ADT location so off-peak nighttime hours are required with reopening to traffic before the next morning rush period.

| Item Description |  | Quantity |  |
| --- | --- | --- | --- |
| Full Depth Saw Cuts | $7.25 | 1,356 LF | $9,831.00 |
| Dowel Bars (Drilling, Furnishing, and Installation) | $8.00 | 272 Ea | $2,176.00 |
| Full Depth Pvmt. Repair (100.1 – 500 SY) Less than or equal to 12” Thick | $120.00 | 279.9 SY | $33,588.00 |
| Mobilization – Full Depth Pavement Repair | $4,800.00 | 1 Each | $4,800.00 |
|  |  | Subtotal: | $50,395.00 |
| Nighttime Work Factor | 1.200 |  |  |
|  |  | Subtotal: | $60,474.00 |
| Accelerated Repair | $2,200.00 | 1 Each | $2,200.00 |
|  |  | TOTAL: | $62,674.00 |

AA.	EMERGENCY PROVISIONS AND INCIDENT MANAGEMENT

1.0	The contractor shall have communication equipment on the construction site or immediate access to other communication systems to request assistance from the police or other emergency agencies for incident management.  In case of traffic accidents or the need for police to direct or restore traffic flow through the job site, the contractor shall notify police or other emergency agencies immediately as needed.  The engineer shall also be notified when the contractor requests emergency assistance.

2.0	In addition to the 911 emergency telephone number for ambulance, fire or police services, the following agencies may also be notified for accident or emergency situation within the project limits.

| Missouri Highway Patrol | (314) 340-4000 |
| --- | --- |
| MoDOT District KC Customer Service (24 hr) | (816) 622-6500 |
| MoDOT Incident Response (24 hr) | (816) 241-2223 |
| City of Kansas City Police | (816) 234-5000 |
| City of Kansas City Fire | 816) 513-0911 |
| Clay County Sheriff | (816) 407-3750 |
| Platte County Sheriff | (816) 858-2424 |
| Lafayette County Sheriff | (660) 259-3622 |
| Jackson County Sheriff | (816) 524-4302 |

2.1	This list is not all inclusive.  Notification of the need for wrecker or tow truck services will remain the responsibility of the appropriate police agency.

2.2	The contractor shall notify enforcement and emergency agencies before the start of construction to request their cooperation and to provide coordination of services when emergencies arise during the construction at the project site.  When the contractor completes this notification with enforcement and emergency agencies, a report shall be furnished to the engineer on the status of incident management.

3.0	No direct payment will be made to the contractor to recover the cost of the communication equipment, labor, materials or time required to fulfill the above provisions.

BB.	UTILITIES

1.0	It is the inherent risk of the work under this contract that the contractor may encounter utilities above and/or below the ground or in the vicinity of any given job order which may interfere with their operations.  The contractor expressly acknowledges and assumes this risk even though the nature and extent is unknown to both the contractor and the Commission at the time of bidding and award of the contract.  The effect in cost or time of the presence of utilities above, below or in the vicinity of the contractor’s work under this contract shall not be compensable.

2.0	The contractor will be responsible and is required to call for utility locates prior to performing any excavation work within any project limits for a given job order.  Calling for utility locates will not relieve the contractor of his liability for utility damages caused by excavating operations performed by the contractor and/or any of his subcontractors.  The contractor shall be solely responsible for all costs, fines, and penalties associated with the repair of any damaged utility caused by the actions of the contractor and/or any subcontractor within the given job order limits.

2.1	It shall be noted by the contractor that MoDOT is a member of Missouri One Call (800 Dig Rite). Some work on this project may be in the vicinity of MoDOT utility facilities, which includes but is not limited to traffic signal cables, highway lighting circuits, ITS cables, cathodic protection cables, etc.  Prior to beginning work, the contractor shall request locates from Missouri One Call.  The contractor shall also complete the Notice of Intent to Perform Work form located at the Missouri Department of Transportation website:

http://www.modot.mo.gov/asp/intentToWork.shtml

The contractor shall submit the form over the web (preferred method) or by fax to the numbers on the printed form.  The notice must be submitted a minimum of 2 and a maximum of 10 working days prior to excavation just as Missouri One Call requires.

3.0	Any representation of the presence of utilities on any bidding document provided or job order issued under this contract is disclaimed by the Commission.  The contractor fully understands this disclaimer when determining the basis of their bid for this contract.  The contractor agrees to hold the Commission harmless in the presents or absents of any utility within the limits of any job order resulting from this contract.

CC.	DAMAGE TO EXISTING PAVEMENT

1.0	Description.   This work shall consist of repairing any damage to existing pavement, ramps and/or shoulders caused by contractor operations.  This shall include damage caused either directly or indirectly by contractor operations, including but not be limited to, damage caused by the traffic during contractor operations.

2.0	Construction Requirements.  Any cracking, gouging, or other damage to the existing pavement, ramps and/or shoulders, side roads, or entrances from general construction shall be repaired within twenty four (24) hours of the time of damage at the contractor’s expense.  Repair of the damaged pavement, shoulders, side roads, or entrances shall be as determined by the engineer.

3.0	Method of Measurement.   No measurement of damaged pavement, ramps or shoulder areas as described above shall be made.

4.0	Basis of Payment.   No payment will be made for repairs to existing pavement, ramps and/or shoulders damaged by contractor operations.

DD.	FULL DEPTH PAVEMENT REPAIR REQUIREMENTS

1.0	Description.  This work shall consist of all labor, equipment, and materials necessary to repair existing pavement by performing full depth pavement repairs as specified in the job order or as approved by the engineer.  All work shall be in accordance with Section 613 except as herein modified.

2.0	Construction Requirements.

2.1	At least one lane of traffic shall remain open continuously along the full length of the repair location.  For roadway segments with three or more lanes the engineer may determine that two or more lanes may be closed during the work.  The determination of lane closure configuration and times that lanes may be closed will be determined by the engineer.

2.2	All concrete shall be in accordance with Sec 613.10.2.3.

2.3	All repairs over 15 feet in length shall be straightedged in accordance with Sec 610.

3.0	Material Requirements.

3.1	The contractor shall certify, by letter with the first load of the day, that the material complies with Sec 501.2.1.

3.2	In addition to the requirements of Sec 501.8.11, all batch tickets shall include batch weights, admixture type and admixture quantities.

4.0	Additional or Reduced Work.  If additional repair work is necessary beyond what is specified in the job order or the required repair is not as extensive as originally viewed, the contractor shall contact the engineer for authorization to proceed with the additional or reduced work.  The contractor shall note that with this authorization to proceed with additional or reduced work may change which unit bid item is used to calculate final payment depending on final repair quantities.  Any work performed without authorization of the engineer shall be at the contractor’s expense.

5.0	Method of Measurement.  Measurement will be in accordance with Sec 613 and as follows.  Final measurement of the completed repair area will not be made except for authorized changes during construction, or where appreciable errors are found in the quantity specified in the job order.  Any revision or correction will be computed and added to or deducted from the job order quantity.

6.0	Basis of Payment.  Accepted quantities of full depth pavement repair will be paid for at the fixed unit price multiplied by the Normal, Nighttime or Weekend Adjustment Factor, as mutually agreed upon in the Job Order in accordance with Sec 613.

6.1	Payment for the accepted quantity of Full Depth Pavement Repair on a Job Order with greater than 500 Square Yards and with a thickness greater than 12 inches will be made at an adjusted unit price in accordance with Sec 104.3.

EE.	MOBILIZATION

Delete Sec 618.2 and substitute the following:

618.2	Basis of Payment.  Payment shall be made for mobilization as provided for in the Job Order as follows:

Item 618-99.02	Mobilization-Full Depth Repair		Each

FF.	SUPPLEMENTAL REVISIONS

(to be inserted by Central Office)

GG.	CONCRETE MASONRY REPAIR

Delete paragraphs 704.4.1.6.2 and substitute the following:

704.4.1.6.2 Deck Repairs. The minimum depth of repair for repairing concrete deck (half-soling), approach slab repair or modified deck repair shall expose the upper layer of the top mat of reinforcing steel.  All repair areas shall completely expose 100 percent of the reinforcing steel providing one inch (25 mm) clearance around all bars, regardless of observed bond or condition.

Delete paragraph 704.5.1 and substitute the following:

704.5.1 Repairing concrete deck (half-soling), approach slab repair, deck repair with void tube replacement, full depth repair, modified deck repair, superstructure repair (unformed) and substructure repair (formed and unformed) will be measured to the nearest square foot (0.1 m2).

Amend Sec 704 to include the following:

704.3.10	Approach Slab Repair.  This work shall consist of partial removal and replacement of approach slab concrete in the required areas.

HH.	PREVIOUS JOB ORDER  INFORMATION

1.0  Previous Job Orders.  Job order information, consisting of quantities and pay items that were issued for past contracts will be available from the Project Contact upon the bidder’s written request.  This information does not constitute part of the bid or contract documents.  It is provided for the bidder’s use during bid preparation, and shall not be considered a representation of actual job orders to be issued during construction for this contract. Furnishing this information does not relieve a bidder or contractor from the responsibility of estimating the number and types of job orders that will be issued for future contracts.  The bidder or contractor shall assume the risk of error if the information is used for any purposes for which the information was not intended.  The Commission makes no representation as to the accuracy or reliability of the information, since the information may not be representative of the sealed contract documents.  Any assumption the bidder or contractor may make from this information is at the bidder or contractor's risk; none are intended by the Missouri Highways and Transportation Commission.  The bidder or contractor assumes the sole risk of liability or loss if the bidder or contractor does rely on this information to its detriment, delay or loss.

II. 	SAFETY PLAN

1.0  Description.  This contractor shall submit to the engineer a project Safety Plan (SP) for all work performed by the contractor and all subcontractors.  The purpose of the SP is to encourage and enable all work to be performed in the safest possible manner and that all parties involved are aware of their individual responsibility for safety on the jobsite.

1.1  The SP shall be completed by the contractor and provided to the engineer prior to the beginning of any construction activity or phase on the project.

1.2  The contractor shall designate a person to serve as Project Safety Manager (PSM). The PSM shall be responsible for implementing and overseeing the SP. The PSM is not required to be present on the project at all times, but must be available to address safety issues and needs.

1.3  The PSM shall make revisions to the SP as necessary.  Any new project activities or phases shall be included in the SP prior to work beginning on that activity or phase.

1.4  An example Safety Plan is available at:

http://www.modot.mo.gov/business/contractor_resources/bid_opening_info/bidGenInfo.shtml

2.0 Emergency Preparedness.  The SP shall outline and detail for all workers, the specific procedures and actions necessary to respond to a jobsite emergency and the measures taken to communicate these requirements to all workers.

2.1  The SP shall include a list of local emergency contacts including phone numbers.  A copy of the emergency contact list shall be accessible to workers.

2.2  In the case where there is no cellular or land line phone service at the jobsite, the SP shall identify how to reach the nearest available phone service.

3.0  Project Safety Analysis.  The SP should contain a basic Project Safety Analysis (PSA) that outlines the actions necessary to complete each activity or phase of the project.  The SP shall include a general description of the primary activities or steps required to safely complete the project.

3.1  Each activity should also include a general description of the work involved along with the known risks associated with the activity.  In addition the PSA should outline the controls for those risks, including any Personal Protection Equipment (PPE) requirements for that activity or phase, and whether or not the activity or phase requires a specific safety meeting prior to beginning the activity or phase.

3.2  Submittal of the PSA for all activities or phases is not required with the initial submittal of the SP; however, the PSA for each activity or phase shall be completed prior to the beginning of that activity or phase.

4.0  Safety Meetings. The SP shall include the types of safety meetings that will be required of and conducted by the contractor.

5.0  Safety Training.   The SP shall identify the required safety training provided to the contractor’s personnel.  The contractor shall require that the appropriate safety training for the contractor’s personnel is completed prior to the beginning of work on each activity or phase.

5.1   The SP shall identify the recommended safety training needs and PPE for MoDOT employees who will be exposed to the work activities.   MoDOT will provide safety training and PPE to MoDOT employees based on MoDOT safety policies.

6.0  Payment.  There will be no direct payment for compliance with this Safety Plan provision.

JJ.	RAILROAD REQUIREMENTS

1.0  The right of way of various Railroads, herein called "Railroad", are located within the limits of this project.  However, this project has been developed with the specific intention that no involvement with the Railroad’s facilities, traffic or right of way is required for the performance of the contractual work herein.  The work to be performed over the Railroad’s right of way shall not interfere with the Railroad’s operations or facilities.  Under these circumstances, the requirements of Sec 104.12.3, Sec 104.12.8 through 104.12.10.5 (inclusive), and Sec 107.13.4 shall not apply.

2.0  Should the contractor violate this condition of no railroad involvement, all terms and conditions of the interaction with the Railroad shall be solely between the Railroad and the contractor.

LL.	SAFETY REQUIREMENTS

Delete Sec 616.3.1 and substitute the following:

616.3.1  All workers within highway right of way shall wear approved ANSI/ISEA 107 Performance Class 2 or 3 safety apparel and more specifically as follows:

616.3.1.1  Daytime Flagger.  During daytime activities, flaggers shall wear a high visibility hard hat, safety glasses, a Performance Class 3 top OR a Performance Class 2 top, and safety footwear.  Hard hats other than high visibility orange or green shall be covered with a high visibility covering.

616.3.1.2  Daytime Worker.  During daytime activities, workers shall wear a hard hat, safety glasses, a Performance Class 3 top OR a Performance Class 2 top, and safety footwear.

616.3.1.3  Nighttime Flagger. During nighttime activities, flaggers shall wear a high visibility/reflective hard hat, safety glasses, a Performance Class 3 top AND Class E bottoms, OR Performance Class 2 top AND Class E bottoms, and safety footwear.  Hard hats shall be reflective or covered with a high visibility covering.

616.3.1.4  Nighttime Worker. During nighttime activities, workers shall wear a hard hat, safety glasses, a Performance Class 3 top OR Performance Class 2 top AND Class E bottoms, and safety footwear.

Note: A graphic representation of the various PPE as described above can be found in the “Additional Information” portion of these provisions.  A color representation can be found on the MoDOT website at: http://tinyurl.com/Safe-Apparel.

GRAPHIC REPRESENTATION OF PERSONAL PROTECTIVE EQUIPMENT

# Text boxes

616.3.1.1

616.3.1.2

616.3.1.3

616.3.1.4