## Sheet1
MISSOURI DEPARTMENT OF TRANSPORTATION
Local Public Agency (LPA) Final PS&E Submittal Checklist (revised 5/16/13)
| Project Name: | [5 empty] | Date Received:
Project Sponsor:
Federal Project #:
Line No. | Item | Topic | Reference | LPA Responsibility | LPA Initial | Location within submittal (i.e. page number) to be filled out by LPA or Consultant | MoDOT District Staff Responsibility | MoDOT District Initial | In Fig. 136.9.3 Bid Proposal Boilerplate?
Certification
1 | Certification | Certification | EPG 136.9.2.11 EPG 136.7.3 | LPA to fill out and submit the LPA certification of PS&E Form (Fig 136.9.5) to certify that the PS&E meet all federal and state laws. |  |  | MoDOT - District - review for required items. |  | NO
Required Submittals (if applicable for the project)
2 | Supporting documentation to proposal | Section 106 Clearance | EPG 136.9.2.1 EPG 136.6 | Section 106 - SHPO Clearance, if applicable. |  |  | MoDOT - District - review for required items. |  | NO
3 | Proposal/Supporting Documentation | Section 404 Permits | EPG 136.9.2.1 EPG 136.6 | 404 COE Permit/401 Water Quality (if applicable)** This should be included in the proposal. |  |  | MoDOT - District - review for required items. |  | NO
4 | Supporting documentation to proposal | USF&W/T&E | EPG 136.9.2.1 EPG 136.6 | United States Fish & Wildlife (USF&W) Threatened & Endangered Species (T&E) Clearance, if applicable. |  |  | MoDOT - District - review for required items. |  | NO
5 | Supporting documentation to proposal | MDC Heritage Review | EPG 136.9.2.1 EPG 136.6 | Missouri Department of Conservation (MDC) Heritage Review, if applicable. |  |  | MoDOT - District - review for required items. |  | NO
6 | Supporting documentation to proposal | 100-year floodplain and regulatory floodway | EPG 136.9.2.1 44 CFR Parts 59-78 EPG 136.6 | Flood Plain Development Permit, if applicable. |  |  | MoDOT - District - review for required items. |  | NO
7 | Supporting documentation to proposal | Farmland Protection Policy Act | EPG 136.9.2.1 EPG 136.6 | Farmland Conversion Impact Rating Form, if applicable. |  |  | MoDOT - District - review for required items. |  | NO
8 | Supporting documentation to proposal | NEPA Classification | EPG 136.9.2.1 EPG 136.6 | Include NEPA classification documentation |  |  | MoDOT - District - review for required items. |  | NO
8a | Supporting documentation to proposal | Hazardous Waste | EPG 136.9.2.1 EPG 136.6.4.10 | All lead paint and asbestos inspection report MUST be in the bid proposal. |  |  | MoDOT - District - review for required items. |  | NO
9 | Supporting documentation to proposal | Right of Way | EPG 136.9.2.2 EPG 136.8 23 CFR 635.309 | Final Right of Way Certification |  |  | MoDOT - District - review for required items. |  | NO
10 | Supporting documentation to proposal | Utility | EPG 136.9.2.3 EPG 136.7.2.6 23 CFR 635.309 | Utility Relocation - Status Letter from Applicable Agencies, if applicable. Fig 136.9.6 |  |  | MoDOT - District - review for required items. |  | NO
11 | Supporting documentation to proposal | Railroad | EPG 136.9.2.4 EPG 136.7.2.5 23 CFR 635.309 | Approval letter from Railroad, if applicable. |  |  | MoDOT - District - review for required items. |  | NO
12 | Supporting documentation to proposal | Bridge Submittals | EPG 136.9.2.5 EPG 136.7.2.2.7 | LPA to submit appropriate documents, see EPG for further guidance. |  |  | MoDOT - District - review for required items. |  | NO
13 | Supporting documentation to proposal | Bridge Submittals | EPG 136.9.2.5 EPG 136.7.2.2.7 | Approval letter from Drainage District, if applicable. (SE district bridge replacement only) |  |  | MoDOT - District - review for required items. |  | NO
14 | Supporting documentation to proposal | Public Interest Findings for Proprietary Items | EPG 136.9.2.6 EPG 136.7.2.8 EPG 136.9.4.1.2.7 | LPA to submit appropriate documents, see EPG for further guidance. |  |  | MoDOT - District - review for required items. |  | NO
15 | Supporting documentation to proposal | Design Exceptions | EPG 136.9.2.7 EPG 136.7.2.7 | LPA to submit appropriate documents, see EPG for further guidance. |  |  | MoDOT - District - review for required items. |  | NO
16 | Supporting documentation to proposal | Work by Local Forces | EPG 136.9.2.8 EPG 136.3.12 | LPA to submit appropriate documents, see EPG for further guidance. |  |  | MoDOT - District - review for required items. |  | NO
17 | Supporting documentation to proposal | ADA Certification | EPG 136.9.2.10 EPG 136.7.2.4 | Fig 136.9.12 |  | THIS IS NO LONGER NEEDED. | MoDOT - District - review for required items. |  | NO
18 | Supporting documentation to proposal | ADA Checklist | EPG 136.9.2.10 EPG 136.7.2.4 | Fig 136.9.4 |  |  | MoDOT - District - review for required items. |  | NO
19 | Required documents for locally proposed NBI Structures | Bridge | EPG 136.7.2.2.6.3 EPG 136.7.2.2.6.4 | Completed SI&A Load Rating Calc & Summary |  |  | MoDOT - District - review for required items. |  | NO
Plans
20 | Plans | Plan Requirements | EPG 136.9.3 EPG 136.7.2.1.6 | Title Sheet MUST have: Federal Project #, location map and local official(s) signatures. |  |  | MoDOT - District - review for required items. |  | NO
21 | Plans | Professional Engineer Signature | EPG 136.9.3 EPG 136.7.2.1.6 | Title Sheet, all plan sheets and cover sheet of the proposal MUST be signed and sealed by engineer of record and the title sheet is signed by the LPA. |  |  | MoDOT - District - review for required items. |  | NO
22 | Plans | Traffic Control | EPG 136.7.2.1.4 MUTCD | The local agency shall develop and implement a Transportation Management Plan (TMP) in sustained consultation with all stakeholders for each project. The TMP shall conform to the guidelines set forth in Chapter 6 of the Manual on Uniform Traffic Control Devices (MUTCD). |  |  | MoDOT - District - review for required items. |  | NO
23 | Plans | Bridge | EPG 136.7.2.2.6.2 | Pertinent design criteria, appropriate data and information to ensure accurate and competitive bids |  |  | MoDOT - District - review for required items. |  | NO
Bid Documents - Bid Proposal Required Provisions - See Federal Project Bid Proposal Boilerplate Fig 136.9.3
24 | Proposal | Checklist of Requirements for Contractor to be considered "responsive" aka Bidder's Checklist | 23 CFR 635.112(h) | Bid Proposal must clearly identify requirements which the bidder must assure in order to make the bid responsive. |  |  | MoDOT - District - review for required items. |  | YES
25 | Proposal | Period of Performance (also known as Contract Time) | MoDOT Spec 108 EPG 136.9.4.1.1.1 | Proposal must include language indicating the allowed construction timeframe. |  |  | MoDOT - District - review for required items. |  | YES
26 | Proposal | Liquidated Damages | EPG 136.9.4.1.1.2 23 CFR 635.127 MoDOT Spec 108.8 | Bid Proposal must include liquidated damages rate table. |  |  | MoDOT - District - review for required items. |  | YES
27 | Proposal | Bid Bond(Guaranty) | EPG 136.9.4.1.1.3 49 CFR 18.36 MoDOT Spec 102.9 | Bid Proposal must include Bid Bond. |  |  | MoDOT - District - review for required items. |  | YES
28 | Proposal | Affirmative Action - Equal Opportunity Employer (EEO) | MoDOT Spec 102.18.1 41 CFR 60 EPG 136.9.4.1.1.4 | Bid Proposal must include EEO provisions. If using the Federal Project Bid Proposal Boilerplate, this is covered under Section (6) and there would be no need to submit this information separately. |  |  | MoDOT - District - review for required items. |  | YES
29 | Proposal | Affirmative Action - Subcontractor Certification | EPG 136.9.4.1.1.4 | Bid Proposal must include the affirmative action form Fig 136.9.2. If using the Federal Project Bid Proposal Boilerplate, this is covered under Section (6) and there would be no need to submit this information separately. |  |  | MoDOT - District - review for required items. |  | YES
30 | Proposal | Suspension and Debarment | 23 CFR 635.112 49 CFR 29 EPG 136.9.4.1.1.5 MoDOT Spec 102.18.2 | Bid Proposal must state contractors who are currently suspended, debarred or voluntarily excluded under 2 CFR part 180, or otherwise determined to be ineligible shall be prohibited from participating in the Federal-Aid Highway Program. If using the Federal Project Bid Proposal Boilerplate, this is covered under Section (6) and there would be no need to re-state this elsewhere in the bid proposal. |  |  | MoDOT - District - review for required items. |  | YES
31 | Proposal | Anti-Collusion | EPG 136.9.4.1.1.6 23 CFR 635.112(f) MoDOT Spec 102.18.3 | Bid Proposal must include anti-collusion statement and form. If using the Federal Project Bid Proposal Boilerplate, this is covered under Section (6) and there would be no need to submit this information separately or re-state is elsewhere in the bid proposal. |  |  | MoDOT - District - review for required items. |  | YES
32 | Proposal | Lobby Certification | MoDOT Spec 102.18.4 49 CFR 20 EPG 136.9.4.1.1.7 | Submit Certification in Bid Documents. If using the Federal Project Bid Proposal Boilerplate, this is covered under Section (6) and there would be no need to submit this information separately. |  |  | MoDOT - District - review for required items. |  | YES
33 | Proposal | Civil Rights | EPG 136.9.4.1.1.8 23 CFR 635.112(d) | Bid Proposal must include Title VI Civil Rights Assurances |  |  | MoDOT - District - review for required items. |  | YES
34 | Proposal | Right to Inspect Work | EPG 136.9.4.1.1.9 MoDOT Spec 105.10 | The project Job Special Provisions or drawings shall stipulate that MoDOT and FHWA may make inspections of the work and that the contractor shall grant them access to all parts of the work. |  |  | MoDOT - District - review for required items. |  | YES
35 | Proposal | Materials Inpsection Technician Certification | EPG 136.11.17.1 | Bid Proposal must state that all technicians who perform, or are required by the FHWA to witness, such sampling and testing shall be deemed as qualified by virtue of successfully completing the requirements of EPG 106.18 Technician Certification Program, for that specific technical area. |  |  | MoDOT - District - review for required items. |  | YES
36 | Proposal | Federal/State Wage Rates | EPG 136.9.4.1.1.10 RsMO 290.263 | When state and federal wage rates are both required the higher of the two for each job classification should be used. |  |  | MoDOT - District - review for required items. |  | YES
37 | Proposal | State Wage Rates | EPG 136.9.4.1.1.10 8 CSR 30-3 | The local agency must request an Annual State Wage Determination for each contract from the Industrial Commission, Missouri Department of Labor and Industrial Relations (DOLIR), Box 449, Jefferson City, Missouri 65102 or by calling (573) 751-3403. |  |  | MoDOT - District - review for required items. |  | NO Insert current rates
38 | Proposal | Prevailing Minimum Wage (Davis-Bacon) | EPG 136.9.4.1.1.10 23 USC 113 29 CFR 5 | Bid Proposal must include Federal Davis-Bacon prevailing wage rate determinations on all federal contracts except when the project is located off the federal-aid highway system. Local projects that are located on roadways classified as local roads or rural minor collectors are exempt from the Federal Wage Rate requirement. However, other federal-aid provisions still apply. |  |  | MoDOT - District - review for required items. |  | NO Insert current rates
39 | Proposal | E-Verify | RsMO 285.530 EPG 136.9.4.1.1.11 | Bid Proposal must note requirements regarding Federal Work Authorization Program and list Federal website for E-Verify. Supporting documentation must include Affidavit for compliance & MOU. |  |  | MoDOT - District - review for required items. |  | YES
40 | Proposal | OSHA Training | RsMO 292.675 EPG 136.9.4.1.1.12 | OSHA Training Requirements are stated in proposal. |  |  | MoDOT - District - review for required items. |  | YES
41 | Proposal | Buy America | MoDOT Spec 106.9 49 USC 501 23 CFR 635.410 EPG 136.9.4.1.1.13 | Bid Proposal must include Buy America provisions. |  |  | MoDOT - District - review for required items. |  | YES
42 | Proposal | Contractor Requirements | EPG 136.9.4.1.1.14 MoDOT Spec 102.2 | Bid Proposal must stipulate that the prime contractor must have a fully responsive contractor questionnaire on file with the Missouri Highways and Transportation Commission (MHTC) at least seven (7) days prior to the bid opening date if this project involves roadway or bridge work. The following sentence could be inserted into the contract that would allow contractors not on the listing to submit a bid for the project. “Sec 102.2 of the Missouri Standard Specifications for Highway Construction will be waived for this project.” This statement should only be used on proposed improvements that do not contain roadway or bridge construction (i.e., landscaping, sidewalks, bicycle path, etc.). If this waiver is not inserted in the contract and the bidder is not on MoDOT’s listing, the bidder cannot be awarded the project. |  |  | MoDOT - District - review for required items. |  | YES
43 | Proposal | Contractor Requirements | EPG 136.9.4.1.1.14 23 CFR 635.116 | The bid proposal must stipulate that the prime contractor on a project must perform with its own organization, contract work amounting to not less than 30% of the total original contract price. |  |  | MoDOT - District - review for required items. |  | YES
44 | Proposal | Subcontracting | EPG 136.9.4.1.1.14 23 CFR 635.116 MoDOT Spec 108.1 | The bid proposal must stipulate that second-tier subcontracting will not be permitted on the project. |  |  | MoDOT - District - review for required items. |  | YES
45 | Proposal | DBE Provisions | EPG 136.9.4.1.1.15 49 CFR 26 MoDOT Spec 102.17 | Bid Proposal must include the DBE provisions Fig 136.9.8 |  |  | MoDOT - District - review for required items. |  | NO Insert current provisions found in Fig. 136.9.8
46 | Proposal | DBE Forms | EPG 136.9.4.1.1.15 | Bid Proposal must include current version of DBE Forms Fig 136.9.9 |  |  | MoDOT - District - review for required items. |  | NO Insert current provisions found in Fig. 136.9.9
47 | Proposal | On the Job Training (OJT) | 23 CFR 230 EPG 136.9.4.1.1.16 MoDOT Spec 102.17 | Bid Proposal must include the OJT Training Special Provision (TSP) only when a goal has been established. |  |  | MoDOT - District - review for required items. |  | NO Insert current provisions found in Missouri Spec Book
48 | Proposal | Addenda | EPG 136.9.4.1.1.17 23 CFR 635.112 | Bid Proposal must include instructions on acknowledgement of addenda. |  |  | MoDOT - District - review for required items. |  | YES
49 | Proposal | Bid Award | EPG 136.9.4.1.1.19 23 CFR 635.114(a) MoDOT Spec 103.2.1 | Bid Proposal must state the bid will be awarded to the "lowest, responsive, responsible bidder". |  |  | MoDOT - District - review for required items. |  | YES
50 | Proposal | Bid Form | EPG 136.9.4.1.1.20 | The bid proposal will also need to include an itemized listing of all pay items included in the project, quantities of each individual pay item and blanks for the contractor to submit a unit price (and extension) for each pay item. (No Lump Sum Contracts) |  |  | MoDOT - District - review for required items. |  | NO Insert current LPA bid forms
51 | Proposal | FHWA Form 1273 | EPG 136.9.4.1.1.21 23 CFR 633 | Bid Proposal must include FHWA 1273 Contract Provisions Fig 136.9.7 |  |  | MoDOT - District - review for required items. |  | NO Insert current form found in Fig. 136.9.7
52 | Proposal | Changed Conditions Clauses | EPG 136.9.4.1.1.22 | Standardized changed condition clauses are required to be included in all contracts. The Missouri Standard Specifications and the Standard Specifications for Public Works Construction (Green Book) contain standard changed condition clauses. If a LPA chooses to use a different standard specifications book other than MoDOT’s, the federal regulations shall still apply. |  |  | MoDOT - District - review for required items. |  | NO Covered only if using MoDOT Standard Specs
53 | Proposal | Differing Site Conditions Clauses | EPG 136.9.4.1.1.22.1 | Required if Changed Condition Clauses are required. |  |  | MoDOT - District - review for required items. |  | NO Covered only if using MoDOT Standard Specs
54 | Proposal | Suspension of Work Ordered by the Engineer | EPG 136.9.4.1.1.22.2 | Required if Changed Condition Clauses are required. |  |  | MoDOT - District - review for required items. |  | NO Covered only if using MoDOT Standard Specs
55 | Proposal | Material Changes in the Scope of Work | EPG 136.9.4.1.1.22.3 | Required if Changed Condition Clauses are required. |  |  | MoDOT - District - review for required items. |  | NO Covered only if using MoDOT Standard Specs
Bid Documents - Bid Proposal Restricted Provisions
56 | Proposal | Retainage | RsMO 34.057 MoDOT Spec 109.9 EPG 136.9.4.1.2.1 | Retainage of contractor payment is not to be automatically applied to projects as a matter of course. However, the PS&E should clearly state that in accordance with the Missouri Prompt Pay Act (34.057 RSMo), the owner may withhold payment for any of the reasons outlined in RsMO 34.057, or as determined by the engineer. |  |  | MoDOT - District - review for required items. |  | NO
57 | Proposal | Contractor Warranty | EPG 136.9.4.1.2.2 23 CFR 635.413 | No contractor guarantee's/warranties allowed |  |  | MoDOT - District - review for required items. |  | NO
58 | Proposal | Professional Licensure, Certification, Business Licensure and Work Permits | EPG 136.9.4.1.2.3 | Permitting and licensing criteria that unduly restrict or limit any firm’s ability to bid on and receive award of federal-aid projects will not be approved. All permitting and licensing must be approved by MoDOT. |  |  | MoDOT - District - review for required items. |  | NO
59 | Proposal | Bidder Qualification Language | EPG 136.9.4.1.2.4 | All qualifications must be completed PRIOR to bid opening. The bidder qualification language can reside in the bid proposal as long as the bidders are informed PRIOR to bid opening in the notice to contractors. In short, the pre-qualification language can be in both the notice/advertisement and the bid proposal but the language is required to be in the notice and is optional for the bid proposal. |  |  | MoDOT - District - review for required items. |  | NO
60 | Proposal | Project Labor Agreements | EPG 136.9.4.1.2.5 | Essentially, executive agencies may not require or prohibit contractors to enter into PLAs. Agencies also may not discriminate against contractors based on PLAs. In addition, despite the limits on executive agencies, contractors are not barred from freely agreeing to PLAs. |  |  | MoDOT - District - review for required items. |  | NO
61 | Proposal | Local Preferences | EPG 136.9.4.1.2.6 | On all federally funded construction projects, materials produced within the state or local area shall not be favored over comparable materials produced outside of the state or local area. |  |  | MoDOT - District - review for required items. |  | NO
62 | Proposal | Proprietary Items | EPG 136.9.4.1.2.7 23 CFR 635.411 EPG 136.7.2.8 | Generally, on federal aid projects, the use of trade names in plans and specifications is not allowed except as outlined in EPG 136.7.2.8. |  |  | MoDOT - District - review for required items. |  | NO
63 | Proposal | Signing Restrictions | EPG 136.9.4.1.2.8 | The contract shall not include promotional or other informational signs regarding such matters as identification of public officials, contractors, organizational affiliations, and related logos and symbols. |  |  | MoDOT - District - review for required items. |  | NO
64 | Proposal | Employ Missouri | RsMO 290.570 EPG 136.9.4.1.2.9 | This can only be used on State funds not on federally funded projects. Provision stating that when unemployment is > 5% they must employ Missouri citizens. |  |  | MoDOT - District - review for required items. |  | NO
Specifications
65 | Specifications | Spec Requirements | EPG 136.9.4.2 EPG 136.7.3 | When referencing Missouri Standard Specifications for Highway Construction - Current Edition, MUST be specific on the edition date. |  |  | MoDOT - District - review for required items. |  | YES
66 | Specifications | Spec Requirements | EPG 136.9.4.2 EPG 136.7.3 | The specification used shall be referenced on both the drawings and the specifications package as the basic standard for materials and construction - except as modified or superseded by job special provisions or other specifications included in the specifications package. |  |  | MoDOT - District - review for required items. |  | NO
67 | Specifications | Job/Technical Specifications | EPG 136.9.4.2 EPG 136.7.3.1 | All identified JSP's must be included in the bid proposal. |  |  | MoDOT - District - review for required items. |  | NO Must be inserted
68 | Required JSP's | Traffic Control | EPG 136.7.3.1.2.1.1 | If a project contains traffic control, a Traffic Control JSP is required |  |  | MoDOT - District - review for required items. |  | NO Must be inserted
69 | Required JSP's | Contractor Furnished Borrow | EPG 136.7.3.1.2.1.2 | If the specifications call for contractor-furnished borrow, the bid proposal must include the Guidelines for Obtaining Environmental Clearance JSP. |  |  | MoDOT - District - review for required items. |  | NO Must be inserted
70 | Required JSP's | ADA | EPG 136.7.3.1.2.1.3 | If a project contains any items with ADA components, the ADA JSP is required . |  |  | MoDOT - District - review for required items. |  | YES
71 | Required JSP's | Lump Sum Items | EPG 136.7.3.1.2.1.4 | If there are lump sum items in the contract, a JSP for each Lump Sum item is required. |  |  | MoDOT - District - review for required items. |  | NO Must be inserted
72 | Required JSP's | Utility Relocation | EPG 136.7.3.1.2.1.5 | If a project contains any utility relocations and/or adjustments, a Utility JSP is required. |  |  | MoDOT - District - review for required items. |  | YES
73 | Required JSP's | Right of Way Clearance | EPG 136.7.3.1.2.1.6 | If right of way is not cleared prior to bid opening, a JSP is required and must explain how this right of way clearance will affect the contractor and when the right of way is expected to be cleared. |  |  | MoDOT - District - review for required items. |  | NO Must be inserted
74 | Required JSP's | Railroad | EPG 136.7.3.1.2.1.7 | If there is a railroad agreement associated with the project and there are issues that the contractor needs to be aware of a JSP is required. If a railroad flagger is required for the project, a JSP is required and it must indicated who is responsible for funding the flagging operation. |  |  | MoDOT - District - review for required items. |  | NO Must be inserted
75 | Required JSP's | Bridge Material Inspection/Acceptance | EPG 136.7.3.1.2.1.8 | The LPA has the option as to whether or not they intend to do inspection at a fabrication shop during the manufacture of fabricated bridge elements being supplied for the job. When the LPA decides not to inspect at the fabrication shop, the following specifications regarding acceptance of fabricated structural members shall be included (when appropriate) as job special provisions . |  |  | MoDOT - District - review for required items. |  | NO Must be inserted
76 | Required JSP's | Alternate Bidding | EPG 136.7.3.1.2.1.9 | If a project contains any alternate or optional bidding, a JSP is required |  |  | MoDOT - District - review for required items. |  | NO Must be inserted
Standard Plans
77 | Required Documentation | Standard Plans | EPG 136.9.4.3 EPG 136.7.3.2 | The bid proposal must clearly indicate that standard plans which are in effect. In addition, if more than one is referenced, the order of precedence must be stipulated. |  |  | MoDOT - District - review for required items. |  | NO
Estimate
78 | Estimate | Engineer's Estimate | EPG 136.9.5 EPG 136.7.4 | An engineer's estimate, showing estimated quantities, unit prices and extended totals shall be submitted to MoDOT with the detailed plans. Subtotals shall be shown for roadway items, bridge, signing/striping/signals/lighting, landscaping/streetscaping, utilities (reimbursable with federal participation) and bicycle/pedestrian facilities . The engineer's estimate should be treated as a confidential document. Any knowledge of the estimate may cause unbalanced bids or provide a contractor who has knowledge of the engineer's estimate an advantage. |  |  | MoDOT - District - review for required items. |  | NO
Note on I32: holtsj1: