## LPA Consultant Invoice
LPA Consultant Services Invoice
INVOICE
Invoice Date: |  |  |  |  | 2012-07-05
Invoice Number: |  |  |  |  | 2
Billing Period: |  |  |  |  | 6-1-12 Thru 6-30-12
Federal Project Number: |  |  |  |  | STP-9999 (999)
Revised Sept 5, 2012
Section 1: Project Information
LPA Information
Local Agency (LPA) Name: |  |  | City of Nowhere
LPA Address: |  |  | 1111 West 3rd Street
LPA Person of Responsible Charge: |  |  | John Smith
LPA Contact Phone: |  |  | 573-555-5555
LPA Contact Email: |  |  | johnsmith@nowhere.com
Consultant Information
Consultant Firm Name: |  |  | ABC Engineering Inc.
Consultant Contact Name: |  |  | Jane Doe
Address 1: |  |  | 105 East Delaware
Address 2: |  |  | PO Box 1555
City, State, Zip: |  |  | Somewhere, MO 65555
Phone Number: |  |  | 573-555-4444
Contact Email: |  |  | janedoe@abc.com
Consultant Project No.: |  |  | A-111-NMO
Project Information
Project Description: |  |  | Sidewalk project from oak st to maple street
Project County: |  |  | Oregon county
Federal Project Number: |  |  | STP-9999 (999)
LPA Project Number: |  |  | X111-998
PE Federal Obligation Date: |  |  | 2012-04-01
Federal Funding Category(s): |  |  | STP
Engineering Services Contract Information
ESC Execution Date: |  |  | 2012-05-01
ESC Completion Date for PE Work Only: |  |  | 2012-11-01
ESC Completion Date for CE Work Only: |  |  | n/a
Original ESC Contract Amount: |  |  | 162200
Supplemental No._1_ Amount: |  |  | 7000
Supplemental No.__ Amount:
Supplemental No.__ Amount:
Maximum Amount for ESC: |  |  | 169200
LPA Consultant Services Invoice
INVOICE
Invoice Date: |  |  |  |  | 2012-07-05
Invoice Number: |  |  |  |  | 2
Billing Period: |  |  |  |  | 6-1-12 Thru 6-30-12
Federal Project Number: |  |  |  |  | STP-9999 (999)
Section 2: Billing Summary
Total Direct Salaries (see Section 3) |  |  | 2085
Overhead |  | 125% | 2606.25
|  |  | Subtotal 1 |  | 4691.25
Total Fixed Fee in Contract |  | 7200
Total Fixed Fee for this billing period |  |  | 700
Total Fixed Fee billed to date (including this period) |  | 975
|  |  | Subtotal 2 |  | 700
Total Direct Costs (see Section 3) |  |  | 5541.37
|  |  | Subtotal 3 |  | 5541.37
Total for this invoice |  |  |  |  | 10932.62
Less non-participating costs paid with local funds only |  |  |  |  | 0
TOTAL federal reimbursable amount (amount to be paid by MoDOT/FHWA typically 80%) |  |  |  |  | 8746.1
Previously Total Invoiced Amount |  | 2750.87
Total Billed to Date (including this invoice) |  | 13683.49
Previously Total Non-Participating Costs |  | 1125.65
Total Non-Participating Costs Billed to Date |  | 1125.65
Total Federal Reimbursable Amt to Date |  | 10046.272
LPA Consultant Services Invoice
INVOICE
Invoice Date: |  |  |  |  | 2012-07-05
Invoice Number: |  |  |  |  | 2
Billing Period: |  |  |  |  | 6-1-12 Thru 6-30-12
Federal Project Number: |  |  |  |  | STP-9999 (999)
Section 3: Project Cost Breakdown
DIRECT SALARIES
Task Description/Employee/Employee job Title | HOURS | RATE | AMOUNT
Prelim Plan/Stan Jones/Engr I | 60 | 25.5 | 1530
Surveying/Albert Smith/Surveyor II | 30 | 18.5 | 555
0
0
0
0
0
0
0
| Total Direct Salaries due this invoice |  | 2085
DIRECT COSTS-Sub-consultants & Other direct costs
Task Description/Sub-consultant firm name (**Denotes DBE Sub) |  |  | AMOUNT
Geotech Investigation/Soils-R-Us** |  |  | 5500
Other Direct Costs
Printing |  |  | 41.37
|  | Total Direct costs due this invoice |  | 5541.37
LPA Consultant Services Invoice
INVOICE
Invoice Date: |  |  |  |  | 2012-07-05
Invoice Number: |  |  |  |  | 2
Billing Period: |  |  |  |  | 6-1-12 Thru 6-30-12
Federal Project Number: |  |  |  |  | STP-9999 (999)
Section 4: Progress Report - % Complete & DBE
Total Costs (includes Salaries, Sub-consultants, Direct Costs, Overhead & Fixed Fee)
Task | Total Budgeted | Total Expended to Date | Percent Expended (Budgeted/ Expended) | Estimate % Task Complete (Deliverables)
Prelim Plans | 7500 | 3812.12 | 50.83% | 50
Final Plans | 36500 | 0 | 0% | 0
Surveying | 2500 | 555 | 22.2% | 25
Geotech | 18000 | 5500 | 30.56% | 50
Printing | 500 | 41.37 | 8.274% | 0
Supplemental #1- ROW Acquisition | 7000 | 0 | 0%
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
Overhead | 90000 | 2800 | 3.111%
Fixed Fee | 7200 | 975 | 13.54%
TOTAL | 169200 | 13683.49 | 8.087%
DBE Verification – Summary To Date
DBE Goal = | 10%
Prime Consultant Contract Total = | 169200
DBE Target $ Amount = | 16920
DBE Sub-Consultant | Subcontract Amount | Total $ Billed to Date | Overall DBE % Met to Date
Soils-R-Us | 18000 | 5500
Total DBE Contract $ | 18000
Total $ Billed to Date |  | 5500
DBE % Met to Date |  |  | 3.251%
Progress Report – Narrative
Surveying - have started and will finish by 7/31/12. Prelim Plans have started and are 50% complete. A set of prelim plans will be sent to MoDOT on 8/1/12 for review. Geotech field investigations are underway with approx 50% completed. A report will be submitted to MoDOT by 10/1/12. We are tracking to exceed our DBE goal of 10%, to date we have met 3.25% of the 10% goal and expect to meet approx 11% by contract completion.