Change Order Approval Level Determination

Change Order approval levels are automatically set by the construction management system.  All change orders must be approved at Level 1 (Resident Engineer).  If a given change order exceeds the criteria in the chart below, it would also need to be approved at the additional Level(s) shown.  The values shown are absolute values.  For example; an underrun of $80,000.00 on a single bid item would push the change order to Level 2.  The criteria that requires the highest level approval always prevails over other criteria.  The approval level for a change order marked “Combination” is determined by the various independent components of the change order.  FHWA always approves change order for full oversight jobs.

| Value of Contract: | Less than or Equal to $500,000.00 |  |  |  |  | Over $500,000.00 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Type of Change Order | Change Order Amount | OR | Change Order Amount as a % of Contract Bid | OR | Single Bid Item Change Amount | Change Order Amount | OR | Change Order Amount as a % of Contract Bid | OR | Single Bid Item Change Amount | Approval Level |
| Extra Work | >$50,000.00 | OR | >50% | OR | > $50,000.00 | > $50,000.00 | OR | >25% | OR | > $50,000.00 | 2 |
|  | >$100,000.00 | OR | >50% | OR | >$100,000.00 | >$100,000.00 | OR | >25% | OR | >$100,000.00 | 3 |
|  | >$1,000,000.00 | OR | >50% | OR | >$1,000,000.00 | >$1,000,000.00 | OR | >25% | OR | >$1,000,000.00 | 4 |
| Final | > $50,000.00 | OR | >50% | OR | >$50,000.00 | > $50,000.00 | OR | >25% | OR | > $50,000.00 | 2 |
| Quantities | >$100,000.00 | OR | >50% | OR | >$100,000.00 | >$100,000.00 | OR | >25% | OR | >$100,000.00 | 3 |
|  | >$1,000,000.00 | OR | >50% | OR | >$1,000,000.00 | >$1,000,000.00 | OR | >25% | OR | >$1,000,000.00 | 4 |
| Time | Always |  | Goes |  | Up | Always |  | Goes |  | Up | 2 |
| Extension | Always |  | Goes |  | Up | Always |  | Goes |  | Up | 3 |
|  | Over |  | 999 |  | Days | Over |  | 999 |  | Days | 4 |
| Overrun/ | >$50,000.00 | OR | >50% | OR | > $50,000.00 | > $50,000.00 | OR | >25% | OR | > $50,000.00 | 2 |
| Underrun | >$100,000.00 | OR | >50% | OR | >$100,000.00 | >$100,000.00 | OR | >25% | OR | >$100,000.00 | 3 |
|  | >$1,000,000.00 | OR | >50% | OR | >$1,000,000.00 | >$1,000,000.00 | OR | >25% | OR | >$1,000,000.00 | 4 |
| Value | Always |  | Goes |  | Up | Always |  | Goes |  | Up | 2 |
| Engineering | Always |  | Goes |  | Up | Always |  | Goes |  | Up | 3 |

Note: The Resident Engineer is the highest level approver on a “zero dollar” change order, which is defined as covering the direct substitution of a particular line item with a contingent item, not generating an additional cost or cost reduction.