## All Districts
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | Still a PODI | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Design Build Procurement;#AJR Approval;#Bridge 90% Review;#Interstate Designation Request |  | AJR (if required), Bridge and Roadway 90% plans, Interstate De-designation, Funding review, T&E review, NEPA EA review/approval, Design-Build procurement |  |  |  | FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. |  | 2021-09-20 17:44 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3109 | N/A | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. Project involves twin bridges A1293 in the NB and SB lanes. | Andrew |  | Bridge Replacement | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Schedule;#Project Administration;#Local Considerations;#Program Involvement Findings | Complexity: Likely to include head to head traffic on Interstate. Schedule: Scheduled bridge work has risk of delayed completion. Local considerations: Work Zone complexity will significantly impact traffic. |  |  |  | Title VI |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Due to Covid-19 travel restrictions, no construction inspections were performed on this project. No PoDI activity occurred during PY21. The project is nearly completed so this project will not be retained as a PoDI in FY 22. |  | 2021-09-29 15:32 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3110 | 0292195 | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Atchison | 2020-03-20 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental & Stakeholders;#Funding | Construction inspection to include focused review checklists and a bridge inspection. |  |  | Construction inspection to include focused review checklists and a bridge inspection.. | Construction Inspections;#Work Zone/TMP;#Buy America;#Erosion Control;#Bridge Inspection |  | Construction inspection to include focused review checklists and a bridge inspection. | FY 21: The project has been awarded and construction started in the Spring of 2021. No PoDI activity was performed due to the COVID pandemic travel restrictions. The project has been retained as a construction PoDI for FY 22. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1P3378 | not assigned | Rt. 136 Flood Resiliency Permanent Repair | Flood Resiliency Permanent Repair from Mo. River to I-29 near Rock Port. Atchison County | Atchison | 2022-04-15 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Local Considerations;#Funding | ER funded flood resiliency project. | Core Team Member;#Design 90% Review |  | Review of 90% Plans and compare to approved DDIR. |  |  |  | FY21: Reviewed resiliency proposal and DDIR and had multiple meetings to discuss the benefit/cost analysis expectations. Approved DDIR and resiliency proposal. |  | 2021-09-23 14:46 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-02-25 | Pavement and Bridge | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. | Final Design;#Plan, Specification, & Estimate Development;#Advertising & Award;#Core Team Member;#Special Funding | Design Preliminary Plans;#Conceptual Report Review;#Environmental Commitments | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting. | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Environmental Commitments;#Buy America |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | Not Assigned | J2I3274 | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | MONTGOMERY |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3029 | 0444188 | J6I3029 I-44 at I-270 and Meramec River Bridge |  | St. Louis |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | FALSE | FY21;#FY20;#PY19 | [8 empty] | FY 2021 Reviewed and approved 5 change orders with no issues. LP-CUF Reviews still need to be performed for DW Mertzke,Petro legistics, and Prestige truking. Project ending 2/2022. |  | 2021-09-24 10:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3309 | 0703276 | J2I3309 | Pavement improvements from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | MONTGOMERY |  | Pavement Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3310 | 0703286 | J2I3310 | Pavement resurfacing from the Callaway County line to 2 miles east of Rte. F near High Hill. | MONTGOMERY |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | Conceptual Report Review |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review;#Civil Rights/Cert Payroll |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 | Scoping for interchange improvements at Stracks Church County Road near Wright City. | WARREN |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3043 | 0471083 | J2P3043 | Interchange improvements at Rte. 61 in Troy. Project involves bridge A2604. | LINCOLN |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | MONTGOMERY |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#AJR Approval |  | Title VI |  |  |  |  | 2021-09-29 15:37 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3156 | 0544065 | J2P3156 | Add roundabout at Rte. 19 north junction (Basinger Corner) north of Laddonia. $2,346,000 Open Container funds. | Audrain |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Urgency;#Environmental and Stakeholders |  |  |  |  | Construction Inspections |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3259 | 0614179 | J2P3259 | Pavement resurfacing on northbound lanes from Rte. V to 0.4 mile south of Rte. UU in Pike County near Bowling Green. | Lincoln |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity |  |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll;#Pavement/Materials Review |  |  |  |  | 2021-09-23 14:25 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3357 | 0791082 | J2P3357 | Bridge replacement over Lyon Street, Warren Barrett Drive, Burlington Northern Santa Fe Railroad and Bear Creek 0.4 mile north of Rte. T in Hannibal. | MARION |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Program Involvement Findings |  | Core Team Member;#Design Preliminary Plans;#Differing Eligibilities Review |  |  | Title VI |  |  |  |  | 2021-09-29 15:34 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3447 | Not Assigned | J2P3447 | Scoping for roadway improvement between Bus. 54 and Rte. 79 in Louisiana. | Audrain |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member | [7 empty] | 2021-09-23 14:12 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2S3221 J2P3222 J2P3 | S201034 / 13620 | J2S3221 / J2P3222 / J2P3224 |  | SCHUYLER |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-29 07:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval |  | The previously approved AJR will be reevaluated and updated. Title VI review. | [5 empty] | 2021-09-29 15:56 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3226 J2I3226B | 0703279 | Rte. I-70, Mineola Hill Truck Climbing Lanes |  | Montgomery | 2021-07-01 | Reconstruction | Pursley, Charles (FHWA);#37 | Yes | FALSE | FY21 | [8 empty] | Project is under construction. I have attended a weekly project status update meeting to track the project progress through construction. Weekly meetings have not been held since December 2020. I have not approved any change orders or VECPs since October 1. Those activities were complete last PY. The final quarterly project QC/QMmeeting was held on June 23, 2021. I atended as well as the Paement and Materiasl Specialist. |  | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I2006 | 0351291 | Add interchange south of Rte. 92 at 19th Street in Kearney. | New Interchange on I-35 at Kearney | Clay | 2022-02-25 | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Local Considerations;#National/Regional Significance;#Program Involvement Findings | New interchange construction with a Diverging Diamond interchange configuration and new bridge. |  |  |  | Title VI |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | The project has been delayed due to ROW acquisition delays, therefore no construction activities have been performed. The project is expected to be let in early 2022. Significant utility relocation is required before construction begins so the main construction will likely occur in FY23. Will consider including as a PoDI during FY23. |  | 2021-09-29 15:29 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | N/A | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY21 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification could require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#Design 90% Review;#AJR Approval;#Design Exception Approval;#Differing Eligibilities Review |  | Core team member. NEPA review and approval. AJR or Traffic Safety and Operational Analysis will likely be required. 90% Plans review and design exception approval. |  |  |  | FHWA has participated in 3 core team meetings and have offered feedback on the level of documentation and analysis needed for multiple interchange configurations. A separate meeting with the HQ Major project specialist was held to confirm that this project was not considered a Major Project as defined by FHWA and will not need a FP nor Major Project Plan. This information was shared with MoDOT. |  | 2021-09-29 08:11 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3189 | 4351323 | I-435 Bridge over the Missouri River in Kansas City, MO | Bridge deck replacement at the Missouri River. Project involves twin bridges A0767. | Clay | 2019-05-17 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Other;#Urgency;#Complexity;#Local Considerations;#Program Involvement Findings | Schedule: Work zone impacts will be significant and will require expedited construction. Local Consideration: Work zone impacts will be regionally significant. |  |  |  | Work Zone/TMP;#Title VI |  | Construction inspections to include a focused checklist for Work Zone Traffic Control. | FY 21: Due to Covid-19 travel restrictions, no construction inspections were performed on this project. There has been no PoDI involvement this performance year. The project is scheduled to be completed at the end of 2021 and it will be retained as a PoDI project to include a work zone traffic control review. |  | 2021-09-29 16:08 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4P2237 | S300097 | J4P2237- I-49 Outer Roads Conversion to from One-way to Two-way | Conversion of the outer roads of I-49 to two-way traffic on the east outer road from Rt. 150 to Blue Ridge Boulevard and on the west outer road from Blue Ridge Boulevard to 0.5 miles north of Rt. 150 in Grandview. | Jackson | 2023-09-30 |  | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Project Administration;#Local Considerations;#Program Involvement Findings | Large complex local project using the Design-Build delivery method with limited experience by City staff. ROW and Utility impacts that could impace schedule. Complex traffic control during construction with significant traffic impacts on the local and interstate highways. | Contract Administration;#AJR Approval | Environmental Commitments;#AJR Approval;#Design Build AAS Concur;#Design Build Certification;#Design Build Procurement;#FMIS Authorization |  | Title VI;#Work Zone/TMP |  | Construction inspections. Focused Reviews on Title VI and Work Zone Traffic Control. FHWA will continue to provide feedback on proposed revisions to the approved AJR and will coordinate with MoDOT and the City on these changes and any required approval. | Reviewed all books of Draft RFP and provided comments on Books 1 and 2, and ITP. • During the confidential one-one-one meetings, I coordinated review of potential AJR deviations with Division staff and leadership. Reviewed proposed TS&O reports and offered feedback and concerns to MoDOT on all three teams’ draft submittals. • Worked with Mike Landvik and Jim Stevenson to develop a draft LPA Design-Build checklist template for use on future LPA Design-Build projects. • Provided recommendations on how to structure the RFP documents when these were in the early stages of development. Assured that federal requirements were conveyed and followed. • Coordinated involvement on an ADA concern from both Civil Rights and Environmental staff members from MoDOT and FHWA to assure that the decision by the City to modify the sidewalk requirements in the RFP did not violate NEPA and/or ADA requirements. • Reviewed and approved the final RFP for release and facilitated the FMIS construction authorization. This took quite a bit of time since the process for approval was different than traditional D-B-B project authorizations. I provided guidance on the RFP certification letter and what needed to be included in the submittal. MoDOT and the City were very appreciative of this guidance and involvement. • Reviewed the proposals and participated in the proposal evaluation process and offered feedback on how FHWA could concur in the project award. Concurred in project award. Reviewed proposed AJR changes and offered valuable feedback. Coordinated a meeting to convey FHWA expectations on the criteria for acceptance of a proposed AJR revision involving a proposed roundabout in lieu of the approved configuration.s expectation |  | 2021-09-29 15:57 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900391 | 9900391 | TAP 9900 (391) LPA: NE District - CONSTRUCTION |  | TROY |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#PY20;#PY19 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance;#Scoping;#Special Funding;#Bridge TSandL |  | Change Order Approval;#Work Zone/TMP;#Civil Rights/Cert Payroll;#Erosion Control;#DBE Goals;#Buy America;#Title VI |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21: Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21. Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. Reviewed and provided comments to revised project AJR and issued approval. Submitted all required monthly project reports through September, 2021. Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan in coordination with the Division Office Pavement and Materials Engineer. |  | 2021-09-29 15:58 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. |  | 2021-09-27 15:19 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397,J5I3572, | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. | Design PSandE Review |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:22 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3369 | S402035 | 5S3369 - Central District ADA Improvements - Alternate Project Delivery Method | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address Route: Various nonstandard ADA facilities at various locations in the Central and Northwest Districts. | Various | 2021-11-01 | ADA/Sidewalk | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#Design Build AAS Concur | Design Build Procurement;#Design Build Certification |  | Construction Inspections;#Work Zone/TMP;#ADA |  |  | FY2021-The DB team spent a lot of time refining the project scope. I attended several core team meetings and provided a lot of guidance and advice on the DB process as well as NEPA compliance. The RFQ has been developed and the RFP is being finalized. I reviewed these document and provided input and guidance. FY2022 - |  | 2021-09-27 15:26 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Other;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#TSandO Approval;#Design Exception Approval;#Differing Eligibilities Review | [6 empty] | VE Study scheduled / OINCC submittal / Major Project | 2021-09-29 17:00 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900086 | 9900086 | TAP 9900(086) LPA: NE District - CONSTRUCTION |  | CITY OF EAST PRAIRIE |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2090 | 2705360 | J6I2090 | Bridge replacement, bridge rehabilitation and pavement repair over Conway Road and New Ballas Road and bridge rehabilitation for I-270 mainline and ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052, A4654, A4657, A4580 and A4581. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations |  | Core Team Member;#TSandO Approval;#Design Exception Approval;#Design Preliminary Plans |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:01 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2222 | 0641061 | J6I2222 I-64 at 22nd and Jefferson | Modify interchange configuration between 18th Street and Garrison Avenue. Project involves bridges A1523, A1501, A1528, A0840, and A0838. $7,900,000 Cost Share and $7,900,000 Land Clearance for Redevelopment Authority funds. | St. Louis City | 2020-05-15 | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Schedule;#Cost;#Urgency;#Environmental & Stakeholders;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 7 change orders with no comments. Reviewed and approved 2 VECP with no comments. The VECPs were previously discussed in the PAVE that was held after award and before NTP. LP-Project has 3 trainee spots of 1000 hours each. Prime says they will not use trainees until summer 2021. Project is scheduled to be completed 6/2022. CUF still needed for D&K Welding. FY 2022 |  | 2021-09-29 17:02 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 & J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Local Considerations |  | Core Team Member | Core Team Member |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:13 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | B015001 | B015001 | Camden Co. Bridge Replacement on Willow Creek Road |  | Camden |  |  | Pursley, Charles (FHWA);#37 | No | FALSE | FY21 | [8 empty] | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  | Bridge 90% Review;#Design Exception Approval;#Design 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design 90% Review;#Design Exception Approval;#Bridge 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2021-09-28 10:36 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5P3337 | 0543193 | Missouri River Bridge in Jefferson Cit | Bridge rehabilitation over Missouri River. Project involves bridges A4497 and L0550. | Cole, Callaway |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Complexity;#Schedule;#National/Regional Significance;#Local Considerations | [9 empty] | 2021-09-28 20:20 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3269 | S401083 | J5S3269 | Pave Resurfacing from Bus 44 to Rt J, Includes Pave Inprove on Rt H from Rt 17 to End of State Maintenance | Pulaski |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3296 | 0171015 | J9P3296 - Program Development | Pavement Improvements from Route 106 in Summersville to Route 160 Near West Plains, 34.064 miles | TEXAS |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 3219702 | 3219702 | 3219702 | Design to Replace Old Dilapidated Sidewalks Along Main from 15th to 11 St | Jasper |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [5 empty] | FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination. FY 2022 |  | 2021-09-29 06:44 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments | [6 empty] | Part of I-270 North Major project / EA reval | 2021-09-29 07:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3201 | 4952604 | J6I3201 LPA David Hoekel Parkway I-70 Interchange Phase 1 and Phase 2 | Payment to Wentzville for adding interchange west of Point Prairie Road. $5,000,000 Cost Share funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Environmental and Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 8 change orders with no issues. No VECP's have been submitted and none are expected. LP- A CUF review is need for Columbia Curb and Gutter. Project has an OJT Goal of 1 trainee for 1000 hours. Contractor says they are looking for a trainee to use summer 2021. Project closing is delayed until 11/2021. FY 2022 |  | 2021-09-29 06:50 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 Rte N EA | Scoping for environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | New Construction | Peters, Taylor (FHWA);#43 | No | FALSE | FY21 | Environmental & Stakeholders |  | EA/EIS Public Involvement | EA/EIS Public Involvement | [6 empty] | 2021-09-29 07:32 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval;#Core Team Member;#Design Preliminary Plans;#ATC;#FMIS Authorization;#CMAQ Project Review;#Design 90% Review | AJR Approval;#Design Build Certification;#FMIS Authorization;#CMAQ Project Review;#Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America;#Pavement/Materials Review;#Quality Control;#Bridge Inspection;#Title VI |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed. FY 2022 |  | 2021-09-29 15:59 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 & J6I3500 | 2553052 &255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Cost;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review | Core Team Member;#Design Preliminary Plans;#Design PSandE Review;#Other |  | Construction Inspections;#Work Zone/TMP;#Bridge Inspection |  |  |  | VE Study | 2021-09-29 06:57 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:30 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P2321 J6P2321B | 0471072 0471080 | FY 2014 TIGER VI J6P2321 & J6P2321B: MO-47 - Bridge over Missouri River | FY 2014 TIGER ​Replace bridge over the Missouri River from Rte. 94 to Fifth Street in Washington. Cost share: $500,000 city of Washington, $250,000 Franklin County and $50,000 Warren County. | Franklin | 2016-05-20 | Bridge Replacement | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#PY20;#PY19;#PY18;#PY17;#PY16;#FY22 | Funding;#Other |  |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY2021 The project is substantially complete with aethetic lighting still be completed. Due to COVID restrictions, the subcontractor has not been able to travel. All TIGER funds have been expended. Project is submitting all quarterly reports and performance measure reports on time as required. FY2022 |  | 2021-09-29 06:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3233 | not assigned | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371) | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371). Excludes bridge along Missouri River in St. Joseph. | Andrew | 2020-06-19 | Resurfacing | Irving, Kevin (FHWA);#29 | Yes | FALSE | FY21 | Complexity;#Schedule;#Local Considerations | Contract Administration. Pavement and materials quality. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. |  |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. | Due to Covid-19 travel restrictions, construction inspections could not be performed on this project. There were no project actions on this project during FY 21. The project has been completed and therefore will not be carried over as a PoDI in FY 22. |  | 2021-09-21 18:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member | Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Title VI |  |  |  |  | 2021-09-29 15:53 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:15 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 | Environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-28 20:23 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build AAS Concur | Design Build Certification |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:28 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3167 | 0073024 | Rte. 7 and South Ave. Signalization Improvements | Add a signalized intersection at Rte. 7 intersection sidewalk connections (Blue Springs) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | This project was originally programmed as an LPA project sponsored by the City of Blue Springs with the TIP #625033. It was later combined with a MoDOT sponsored project under the TIP #690490 and MoDOT Job Number 4S3167. FMIS action completed 5/14/21. The integration of the LPA CMAQ project into the MoDOT project was correctly programmed and the FMIS action aligned with the programming actions. . |  | 2021-09-28 19:38 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0601 | 711063 | 7P0601 - Rte. I-49 Missouri Arkansas Connector | Bella Vista Bypass Connection for New I-49 | McDonald | 2021-09-30 | New Construction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Program Involvement Findings | Construction of new interstate section using BUILD funding |  | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization |  | Interstate Designation Request;#Title VI | Change Order Approval;#VECP Approval;#Environmental Commitments;#Special Funding |  | FY2021 Project is under construction. I have reviewed and approved 3 VECPs and 10 change orders since October 1. Additional change orders and VECPs were approved last PY.I prepared the final inspection report to document interstate standards. I have assited with preparing the request for acceptance into the Interstate system. FY2022 |  | 2021-09-29 15:31 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 7302674 | 7302674 | CMAQ - 7302(674) Intersection Improvements | CMAQ - 7302(674) Intersection Improvements - Intersection Improvement, Traffic Signals, Roadway Realignment | St. Charles |  | Reconstruction | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  |  | Design 90% Review | PE work has been completed. ROW authorization in FMIS on 8/14/20 |  |  |  | The project description in the FMIS action and EWG TIP are aligned. A FMIS action on 7/9/21 extended the construction award date by 12 months (July 2022). The EWG FY2022-2025 TIP update to be approved by the EWG in October 2021 reflects the new construction award program year of 2022. |  | 2021-09-28 19:34 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations | Bridge replacement using ATC |  | ATC |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:47 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I0445 | 0442293 | Rte. I-44, Webster Co. New Interchange in Marshfield - LPA Administered |  | Webster | 2021-07-27 |  | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | Yes | TRUE | FY21 | Program Involvement Findings |  |  |  |  | Title VI |  |  | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-29 15:35 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 |  | J9P3122 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [7 empty] | 2021-09-23 13:19 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 | Chester Bridge | Perry | 2022-06-22 | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Scoping;#Conceptual Report Review;#Design Build Procurement;#Design Build Certification;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#FMIS Authorization;#Conditional Clearance | [7 empty] | 2021-09-24 09:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 |  | J9P3305 | Scoping for bridge improvements over Current River and Round Spring. | SHANNON |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#Bridge TSandL;#Environmental Commitments | Core Team Member;#Conceptual Report Review;#Bridge TSandL | [6 empty] | 2021-09-23 13:20 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3584 | 0604090 | J9P3584 | Future I-57 and US60; Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds | NEW MADRID |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Scoping;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:36 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | BUTLER |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | BUTLER |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 | AJR Approval;#Design Preliminary Plans;#Conceptual Report Review | Conceptual Report Review;#Design Preliminary Plans;#AJR Approval |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Buy America;#Civil Rights/Cert Payroll |  |  | Provided recommnedation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 |  | J9P3751 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval | [6 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3764 |  | J9P3764 | Future I-57 Phase 1B Add lanes and outer roads to upgrade corridor to freeway standards from County RoadB 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Urgency;#Funding;#Environmental and Stakeholders;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:27 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3232 J9S3232B | S701051/S703077 | J9S3232 & J9S3232B | Bootheel Bridge Bundle Design-Build | VARIOUS |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Environmental and Stakeholders;#Corporate Actions;#Local Considerations | Bundle Bridge project in rural area | Design Build Certification;#Design Build Procurement;#Design Build AAS Concur;#Design Exception Approval | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval |  | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America |  |  | Provided guidance on the Design-Build process. |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 |  | J9S3381 | Bridge replacement over Black River. Project involves bridge K0263. | Butler |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 2700509 | 2700509 - City of Fulton AID Demonstration | Bridge Replacement on 2nd ST Bridge over Stinson Creek and Stinson Creek Greenway, Bridge No. 1555011 located on State Route O in the City of Fulton. Accelerated Innovation Deployment (AID Demonstration program) | Callaway |  | Bridge Replacement | Pursley, Charles (FHWA);#37;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Discretionary Grant and Financing;#Project Administration;#Program Involvement Findings |  | Design Preliminary Plans;#Design 90% Review;#Special Funding;#Differing Eligibilities Review |  |  | Work Zone/TMP;#Bridge Inspection |  |  |  |  | 2021-09-29 08:05 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  | Design PSandE Review;#Design PSandE Approval;#Environmental Commitments;#Core Team Member;#Design Preliminary Plans;#Other |  | Construction Inspections;#Erosion Control;#Civil Rights/Cert Payroll;#Work Zone/TMP;#Buy America |  | Construction inspections with focused review checklists. | FY 20 and FY 21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ. Submitted all monthly BUILD reports as required. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  | Design Preliminary Plans;#Design 90% Review;#Design PSandE Approval | Design Preliminary Plans;#Design 90% Review |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted. FY 2022 |  | 2021-09-29 06:56 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | LPA City of O'Fallon I-70 at Bryan Road |  | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [6 empty] | no funds yet | 2021-09-29 07:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  | Environmental Commitments;#Design Preliminary Plans | Design Build Procurement;#Design Build Certification |  | Environmental Commitments;#Special Funding;#Construction Inspections;#Title VI |  |  | The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. It is nearing completion and should be ready for execution soon. |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 & JP3496B | S502067 S502089 | J6P3496 & JP3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member | [7 empty] | 2021-09-29 07:29 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5903803 | 5903803 - Jefferson Avenue Foot Bridge Over BNSF Railroad in Springfield | Rehabilitate the Jefferson Avenue foot bridge and provide ADA access | Greene | 2021-11-01 | Bridge Rehabilitation | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Project Administration;#Program Involvement Findings |  |  | Design PSandE Review |  | Construction Inspections;#Buy America;#Title VI |  |  |  |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5640613 | 5640613 City of St. Peters | City of St. Peters Jungermann Road Bridge over branch of Spencer Creek, replace culverts (23077 & 23079) - 6563-15 | St. Charles |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Schedule;#Project Administration;#Local Considerations | LPA project, utility related time extension and problematic contractor |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY 2021 Reviewed 3 change orders. Multiple discussions held on time extensions, LDs, and possible claim along with the format and eligibility of the change orders. 2 of the change orders were approved. The LPA has needed a lot of direction since this project had huge impacts to schedule and budget due to utilities. LP- CUF has been conduted for XL Contracting. No OJT hours on project. FY 2022 |  | 2021-09-25 09:41 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#PY20;#FY20;#FY22 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2021-09-25 10:16 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526 | 0552121 | J6I3526 | Scoping for corridor improvements along the I-55 corridor from 0.5 mile north of Rte. Z to 1 mile south of Rte. 67. Potential Design-Build project. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:14 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5417604 5417605 | 5417604 & 5417605 LPA City of St. Louis Jefferson/22nd Improvements | LPA City of St. Louis Jefferson/22nd Improvements | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Project Administration;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Design Exception Approval;#Design Preliminary Plans;#Design 90% Review |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Buy America;#Civil Rights/Cert Payroll;#Title VI |  |  | FY 2021 90% final plan package reviewed and multiple comments submitted including Buy America, proprietary items, traffic control, etc. No Design Exceptions have been submitted and none are expected. Most of the comments from the preliminary plan review were addressed. Project was giving conditional PS&E approval and FMIS authorization/obligation with a long list of conditions. MoDOT is monitoring the conditions. FY 2022 |  | 2021-09-29 16:02 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NA | NA | Pedestrian and Bikeways Improvements | Connect existing bikeways on 11th street and 12th street (Kansas City) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | TRUE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | No FMIS ACTION to-date. KC District staff indicate that this project will be authorized and funds obligated in the early Spring (2022). |  | 2021-09-27 13:25 | McMahon, Bradley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3359 | 0444204 | J6I3359 | Scoping for pedestrian studies at Selma Avenue Overpass and I-55 at Daycare Overpass. Project involves pedestrian bridges A1729 and A0619. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#Environmental Commitments | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | Project Authorization and Project Agreements;#Project Planning & Programming;#Project Financing;#Special Funding;#FMIS Authorization |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added: Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted. MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. Reviewed the consultant solicitation document issued by MoDOT. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J6P3510 | not assigned | J6P3510 | Scoping for ADA Transition Plan improvements at various locations in the St. Louis District. Potential DesignBuild project. | Various |  | ADA/Sidewalk | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | Not assigned | N/A | I-29 near Ambassador Drive, Permit Project | Potential Permit Project near KCI Airport at I-29 and Route D interchange near Ambassador Drive. | Platte |  | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE |  | Local Considerations;#Other | Proposed Dogbone Roundabout interchange at I-29 and Rt. D with connection to a development property. | TSandO Approval |  | Meetings and Review and approval of a TS&O report. | [5 empty] | 2021-09-23 14:59 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 | Scoping for interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#AJR Approval;#Design Exception Approval | [6 empty] | System to System Interchange / EIS reval | 2021-09-29 07:33 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3661 | not assigned | J6P3661 | Scoping for corridor improvements from Rte. 100 to I-44. Project involves various bridges | Franklin |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | Scoping for capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## Central
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | Still a PODI | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  |  | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. |  | 2021-09-27 15:19 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 4300112 | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  | Design PSandE Review;#Design PSandE Approval;#Environmental Commitments;#Core Team Member;#Design Preliminary Plans;#Other |  | Construction Inspections;#Erosion Control;#Civil Rights/Cert Payroll;#Work Zone/TMP;#Buy America |  | Construction inspections with focused review checklists. | FY 20 and FY 21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ. Submitted all monthly BUILD reports as required. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5617602 5617603 | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  | Design Preliminary Plans;#Design 90% Review;#Design PSandE Approval | Design Preliminary Plans;#Design 90% Review |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted. FY 2022 |  | 2021-09-29 06:56 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5901816 | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  | Design Build Procurement;#Environmental Commitments;#Design Preliminary Plans;#Design Build Certification | Design Build Procurement;#Design Build Certification |  | Environmental Commitments;#Special Funding;#Construction Inspections;#Title VI |  |  | The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. It is nearing completion and should be ready for execution soon. |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5903803 | 5903803 | 5903803 - Jefferson Avenue Foot Bridge Over BNSF Railroad in Springfield | Rehabilitate the Jefferson Avenue foot bridge and provide ADA access | Greene | 2021-11-01 | Bridge Rehabilitation | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Project Administration;#Program Involvement Findings |  | Design PSandE Review | Design PSandE Review |  | Construction Inspections;#Buy America;#Title VI |  |  |  |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Design Build Procurement;#AJR Approval;#Bridge 90% Review;#Interstate Designation Request |  | AJR (if required), Bridge and Roadway 90% plans, Interstate De-designation, Funding review, T&E review, NEPA EA review/approval, Design-Build procurement |  |  |  | FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. |  | 2021-09-20 17:44 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3029 | 0444188 | J6I3029 I-44 at I-270 and Meramec River Bridge |  | St. Louis |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | FALSE | FY21;#FY20;#PY19 | [8 empty] | FY 2021 Reviewed and approved 5 change orders with no issues. LP-CUF Reviews still need to be performed for DW Mertzke,Petro legistics, and Prestige truking. Project ending 2/2022. |  | 2021-09-24 10:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3109 | N/A | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. Project involves twin bridges A1293 in the NB and SB lanes. | Andrew |  | Bridge Replacement | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Schedule;#Project Administration;#Local Considerations;#Program Involvement Findings | Complexity: Likely to include head to head traffic on Interstate. Schedule: Scheduled bridge work has risk of delayed completion. Local considerations: Work Zone complexity will significantly impact traffic. | Contract Administration;#Construction Inspection & Quality |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Title VI |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Due to Covid-19 travel restrictions, no construction inspections were performed on this project. No PoDI activity occurred during PY21. The project is nearly completed so this project will not be retained as a PoDI in FY 22. |  | 2021-09-29 15:32 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3110 | 0292195 | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Atchison | 2020-03-20 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental & Stakeholders;#Funding | Construction inspection to include focused review checklists and a bridge inspection. |  |  | Construction inspection to include focused review checklists and a bridge inspection.. | Construction Inspections;#Work Zone/TMP;#Buy America;#Erosion Control;#Bridge Inspection |  | Construction inspection to include focused review checklists and a bridge inspection. | FY 21: The project has been awarded and construction started in the Spring of 2021. No PoDI activity was performed due to the COVID pandemic travel restrictions. The project has been retained as a construction PoDI for FY 22. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1P3378 | not assigned | Rt. 136 Flood Resiliency Permanent Repair | Flood Resiliency Permanent Repair from Mo. River to I-29 near Rock Port. Atchison County | Atchison | 2022-04-15 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Local Considerations;#Funding | ER funded flood resiliency project. | Design 90% Review |  | Review of 90% Plans and compare to approved DDIR. |  |  |  | FY21: Reviewed resiliency proposal and DDIR and had multiple meetings to discuss the benefit/cost analysis expectations. Approved DDIR and resiliency proposal. |  | 2021-09-23 14:46 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-02-25 | Pavement and Bridge | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. | Final Design;#Plan, Specification, & Estimate Development;#Advertising & Award;#Core Team Member;#Special Funding | Design Preliminary Plans;#Conceptual Report Review;#Environmental Commitments | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting. | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Environmental Commitments;#Buy America |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | Not Assigned | J2I3274 | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | MONTGOMERY |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3309 | 0703276 | J2I3309 | Pavement improvements from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | MONTGOMERY |  | Pavement Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3310 | 0703286 | J2I3310 | Pavement resurfacing from the Callaway County line to 2 miles east of Rte. F near High Hill. | MONTGOMERY |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | Conceptual Report Review |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review;#Civil Rights/Cert Payroll |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 | Scoping for interchange improvements at Stracks Church County Road near Wright City. | WARREN |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3043 | 0471083 | J2P3043 | Interchange improvements at Rte. 61 in Troy. Project involves bridge A2604. | LINCOLN |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2S3221 J2P3222 J2P3 | S201034 / 13620 | J2S3221 / J2P3222 / J2P3224 |  | SCHUYLER |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-29 07:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | MONTGOMERY |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#AJR Approval |  | Title VI |  |  |  |  | 2021-09-29 15:37 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3226 J2I3226B | 0703279 | Rte. I-70, Mineola Hill Truck Climbing Lanes |  | Montgomery | 2021-07-01 | Reconstruction | Pursley, Charles (FHWA);#37 | Yes | FALSE | FY21 | [8 empty] | Project is under construction. I have attended a weekly project status update meeting to track the project progress through construction. Weekly meetings have not been held since December 2020. I have not approved any change orders or VECPs since October 1. Those activities were complete last PY. The final quarterly project QC/QMmeeting was held on June 23, 2021. I atended as well as the Paement and Materiasl Specialist. |  | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3156 | 0544065 | J2P3156 | Add roundabout at Rte. 19 north junction (Basinger Corner) north of Laddonia. $2,346,000 Open Container funds. | Audrain |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Urgency;#Environmental and Stakeholders |  |  |  |  | Construction Inspections |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3259 | 0614179 | J2P3259 | Pavement resurfacing on northbound lanes from Rte. V to 0.4 mile south of Rte. UU in Pike County near Bowling Green. | Lincoln |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity |  |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll;#Pavement/Materials Review |  |  |  |  | 2021-09-23 14:25 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3357 | 0791082 | J2P3357 | Bridge replacement over Lyon Street, Warren Barrett Drive, Burlington Northern Santa Fe Railroad and Bear Creek 0.4 mile north of Rte. T in Hannibal. | MARION |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Program Involvement Findings |  | Core Team Member;#Design Preliminary Plans;#Differing Eligibilities Review |  |  | Title VI |  |  |  |  | 2021-09-29 15:34 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3447 | Not Assigned | J2P3447 | Scoping for roadway improvement between Bus. 54 and Rte. 79 in Louisiana. | Audrain |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member | [7 empty] | 2021-09-23 14:12 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900391 | 9900391 | TAP 9900 (391) LPA: NE District - CONSTRUCTION |  | TROY |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval |  | The previously approved AJR will be reevaluated and updated. Title VI review. | [5 empty] | 2021-09-29 15:56 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I2006 | 0351291 | Add interchange south of Rte. 92 at 19th Street in Kearney. | New Interchange on I-35 at Kearney | Clay | 2022-02-25 | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Local Considerations;#National/Regional Significance;#Program Involvement Findings | New interchange construction with a Diverging Diamond interchange configuration and new bridge. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | Work Zone/TMP;#Title VI |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | The project has been delayed due to ROW acquisition delays, therefore no construction activities have been performed. The project is expected to be let in early 2022. Significant utility relocation is required before construction begins so the main construction will likely occur in FY23. Will consider including as a PoDI during FY23. |  | 2021-09-29 15:29 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | N/A | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY21 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification could require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#Design 90% Review;#AJR Approval;#Design Exception Approval;#Differing Eligibilities Review |  | Core team member. NEPA review and approval. AJR or Traffic Safety and Operational Analysis will likely be required. 90% Plans review and design exception approval. |  |  |  | FHWA has participated in 3 core team meetings and have offered feedback on the level of documentation and analysis needed for multiple interchange configurations. A separate meeting with the HQ Major project specialist was held to confirm that this project was not considered a Major Project as defined by FHWA and will not need a FP nor Major Project Plan. This information was shared with MoDOT. |  | 2021-09-29 08:11 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3189 | 4351323 | I-435 Bridge over the Missouri River in Kansas City, MO | Bridge deck replacement at the Missouri River. Project involves twin bridges A0767. | Clay | 2019-05-17 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Other;#Urgency;#Complexity;#Local Considerations;#Program Involvement Findings | Schedule: Work zone impacts will be significant and will require expedited construction. Local Consideration: Work zone impacts will be regionally significant. |  |  | Construction inspection to include focused checklist for Work Zone Traffic Control. | Work Zone/TMP;#Title VI |  | Construction inspections to include a focused checklist for Work Zone Traffic Control. | FY 21: Due to Covid-19 travel restrictions, no construction inspections were performed on this project. There has been no PoDI involvement this performance year. The project is scheduled to be completed at the end of 2021 and it will be retained as a PoDI project to include a work zone traffic control review. |  | 2021-09-29 16:08 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4P2237 | S300097 | J4P2237- I-49 Outer Roads Conversion to from One-way to Two-way | Conversion of the outer roads of I-49 to two-way traffic on the east outer road from Rt. 150 to Blue Ridge Boulevard and on the west outer road from Blue Ridge Boulevard to 0.5 miles north of Rt. 150 in Grandview. | Jackson | 2023-09-30 |  | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Project Administration;#Local Considerations;#Program Involvement Findings | Large complex local project using the Design-Build delivery method with limited experience by City staff. ROW and Utility impacts that could impace schedule. Complex traffic control during construction with significant traffic impacts on the local and interstate highways. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Contract Administration;#Other | Environmental Commitments;#AJR Approval;#Design Build AAS Concur;#Design Build Certification;#Design Build Procurement;#FMIS Authorization |  | Title VI;#Work Zone/TMP |  | Construction inspections. Focused Reviews on Title VI and Work Zone Traffic Control. FHWA will continue to provide feedback on proposed revisions to the approved AJR and will coordinate with MoDOT and the City on these changes and any required approval. | Reviewed all books of Draft RFP and provided comments on Books 1 and 2, and ITP. • During the confidential one-one-one meetings, I coordinated review of potential AJR deviations with Division staff and leadership. Reviewed proposed TS&O reports and offered feedback and concerns to MoDOT on all three teams’ draft submittals. • Worked with Mike Landvik and Jim Stevenson to develop a draft LPA Design-Build checklist template for use on future LPA Design-Build projects. • Provided recommendations on how to structure the RFP documents when these were in the early stages of development. Assured that federal requirements were conveyed and followed. • Coordinated involvement on an ADA concern from both Civil Rights and Environmental staff members from MoDOT and FHWA to assure that the decision by the City to modify the sidewalk requirements in the RFP did not violate NEPA and/or ADA requirements. • Reviewed and approved the final RFP for release and facilitated the FMIS construction authorization. This took quite a bit of time since the process for approval was different than traditional D-B-B project authorizations. I provided guidance on the RFP certification letter and what needed to be included in the submittal. MoDOT and the City were very appreciative of this guidance and involvement. • Reviewed the proposals and participated in the proposal evaluation process and offered feedback on how FHWA could concur in the project award. Concurred in project award. Reviewed proposed AJR changes and offered valuable feedback. Coordinated a meeting to convey FHWA expectations on the criteria for acceptance of a proposed AJR revision involving a proposed roundabout in lieu of the approved configuration.s expectation |  | 2021-09-29 15:57 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900086 | 9900086 | TAP 9900(086) LPA: NE District - CONSTRUCTION |  | CITY OF EAST PRAIRIE |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#PY20;#PY19 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. | Innovative Contracting/Design Build;#Contract Administration;#Construction Inspection & Quality;#Other;#Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance;#Scoping;#Special Funding;#Bridge TSandL |  | Change Order Approval;#Work Zone/TMP;#Civil Rights/Cert Payroll;#Erosion Control;#DBE Goals;#Buy America;#Title VI |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21: Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21. Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. Reviewed and provided comments to revised project AJR and issued approval. Submitted all required monthly project reports through September, 2021. Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan in coordination with the Division Office Pavement and Materials Engineer. |  | 2021-09-29 15:58 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397,J5I3572, | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. | Design PSandE Review |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:22 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3369 | S402035 | 5S3369 - Central District ADA Improvements - Alternate Project Delivery Method | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address Route: Various nonstandard ADA facilities at various locations in the Central and Northwest Districts. | Various | 2021-11-01 | ADA/Sidewalk | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#Design Build AAS Concur | Design Build Procurement;#Design Build Certification |  | Construction Inspections;#Work Zone/TMP;#ADA |  |  | FY2021-The DB team spent a lot of time refining the project scope. I attended several core team meetings and provided a lot of guidance and advice on the DB process as well as NEPA compliance. The RFQ has been developed and the RFP is being finalized. I reviewed these document and provided input and guidance. FY2022 - |  | 2021-09-27 15:26 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | B015001 | B015001 | Camden Co. Bridge Replacement on Willow Creek Road |  | Camden |  |  | Pursley, Charles (FHWA);#37 | No | FALSE | FY21 | [8 empty] | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 2700509 | 2700509 - City of Fulton AID Demonstration | Bridge Replacement on 2nd ST Bridge over Stinson Creek and Stinson Creek Greenway, Bridge No. 1555011 located on State Route O in the City of Fulton. Accelerated Innovation Deployment (AID Demonstration program) | Callaway |  | Bridge Replacement | Pursley, Charles (FHWA);#37;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Discretionary Grant and Financing;#Project Administration;#Program Involvement Findings |  | Design Preliminary Plans;#Design 90% Review;#Special Funding;#Differing Eligibilities Review |  |  | Work Zone/TMP;#Bridge Inspection |  |  |  |  | 2021-09-29 08:05 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5P3337 | 0543193 | Missouri River Bridge in Jefferson Cit | Bridge rehabilitation over Missouri River. Project involves bridges A4497 and L0550. | Cole, Callaway |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Complexity;#Schedule;#National/Regional Significance;#Local Considerations | [9 empty] | 2021-09-28 20:20 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3269 | S401083 | J5S3269 | Pave Resurfacing from Bus 44 to Rt J, Includes Pave Inprove on Rt H from Rt 17 to End of State Maintenance | Pulaski |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3296 | 0171015 | J9P3296 - Program Development | Pavement Improvements from Route 106 in Summersville to Route 160 Near West Plains, 34.064 miles | TEXAS |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 3219702 | 3219702 | 3219702 | Design to Replace Old Dilapidated Sidewalks Along Main from 15th to 11 St | Jasper |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Other;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#TSandO Approval;#Design Exception Approval;#Differing Eligibilities Review | [6 empty] | VE Study scheduled / OINCC submittal / Major Project | 2021-09-29 17:00 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2090 | 2705360 | J6I2090 | Bridge replacement, bridge rehabilitation and pavement repair over Conway Road and New Ballas Road and bridge rehabilitation for I-270 mainline and ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052, A4654, A4657, A4580 and A4581. | St. Louis |  | Bridge Replacement |  | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations |  | Core Team Member;#TSandO Approval;#Design Exception Approval;#Design Preliminary Plans |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:01 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2222 | 0641061 | J6I2222 I-64 at 22nd and Jefferson | Modify interchange configuration between 18th Street and Garrison Avenue. Project involves bridges A1523, A1501, A1528, A0840, and A0838. $7,900,000 Cost Share and $7,900,000 Land Clearance for Redevelopment Authority funds. | St. Louis City | 2020-05-15 | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Schedule;#Cost;#Urgency;#Environmental & Stakeholders;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 7 change orders with no comments. Reviewed and approved 2 VECP with no comments. The VECPs were previously discussed in the PAVE that was held after award and before NTP. LP-Project has 3 trainee spots of 1000 hours each. Prime says they will not use trainees until summer 2021. Project is scheduled to be completed 6/2022. CUF still needed for D&K Welding. FY 2022 |  | 2021-09-29 17:02 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 Rte N EA | Scoping for environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | New Construction | Peters, Taylor (FHWA);#43 | No | FALSE | FY21 | Environmental & Stakeholders |  | EA/EIS Public Involvement | EA/EIS Public Involvement | [6 empty] | 2021-09-29 07:32 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 & J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Local Considerations |  | Core Team Member | Core Team Member |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:13 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  | Bridge 90% Review;#Design Exception Approval;#Design 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design 90% Review;#Design Exception Approval;#Bridge 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2021-09-28 10:36 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [5 empty] | FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination. FY 2022 |  | 2021-09-29 06:44 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments | [6 empty] | Part of I-270 North Major project / EA reval | 2021-09-29 07:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3233 | not assigned | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371) | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371). Excludes bridge along Missouri River in St. Joseph. | Andrew | 2020-06-19 | Resurfacing | Irving, Kevin (FHWA);#29 | Yes | FALSE | FY21 | Complexity;#Schedule;#Local Considerations | Contract Administration. Pavement and materials quality. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. |  |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. | Due to Covid-19 travel restrictions, construction inspections could not be performed on this project. There were no project actions on this project during FY 21. The project has been completed and therefore will not be carried over as a PoDI in FY 22. |  | 2021-09-21 18:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3201 | 4952604 | J6I3201 LPA David Hoekel Parkway I-70 Interchange Phase 1 and Phase 2 | Payment to Wentzville for adding interchange west of Point Prairie Road. $5,000,000 Cost Share funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Environmental and Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 8 change orders with no issues. No VECP's have been submitted and none are expected. LP- A CUF review is need for Columbia Curb and Gutter. Project has an OJT Goal of 1 trainee for 1000 hours. Contractor says they are looking for a trainee to use summer 2021. Project closing is delayed until 11/2021. FY 2022 |  | 2021-09-29 06:50 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval;#Core Team Member;#Design Preliminary Plans;#ATC;#FMIS Authorization;#CMAQ Project Review;#Design 90% Review | AJR Approval;#Design Build Certification;#FMIS Authorization;#CMAQ Project Review;#Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America;#Pavement/Materials Review;#Quality Control;#Bridge Inspection;#Title VI |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed. FY 2022 |  | 2021-09-29 15:59 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 & J6I3500 | 2553052 &255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Cost;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review | Core Team Member;#Design Preliminary Plans;#Design PSandE Review;#Other |  | Construction Inspections;#Work Zone/TMP;#Bridge Inspection |  |  |  | VE Study | 2021-09-29 06:57 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:30 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3167 | 0073024 | Rte. 7 and South Ave. Signalization Improvements | Add a signalized intersection at Rte. 7 intersection sidewalk connections (Blue Springs) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | This project was originally programmed as an LPA project sponsored by the City of Blue Springs with the TIP #625033. It was later combined with a MoDOT sponsored project under the TIP #690490 and MoDOT Job Number 4S3167. FMIS action completed 5/14/21. The integration of the LPA CMAQ project into the MoDOT project was correctly programmed and the FMIS action aligned with the programming actions. . |  | 2021-09-28 19:38 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P2321 J6P2321B | 0471072 0471080 | FY 2014 TIGER VI J6P2321 & J6P2321B: MO-47 - Bridge over Missouri River | FY 2014 TIGER ​Replace bridge over the Missouri River from Rte. 94 to Fifth Street in Washington. Cost share: $500,000 city of Washington, $250,000 Franklin County and $50,000 Warren County. | Franklin | 2016-05-20 | Bridge Replacement | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#PY20;#PY19;#PY18;#PY17;#PY16;#FY22 | Funding;#Other |  |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY2021 The project is substantially complete with aethetic lighting still be completed. Due to COVID restrictions, the subcontractor has not been able to travel. All TIGER funds have been expended. Project is submitting all quarterly reports and performance measure reports on time as required. FY2022 |  | 2021-09-29 06:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 7302674 | 7302674 | CMAQ - 7302(674) Intersection Improvements | CMAQ - 7302(674) Intersection Improvements - Intersection Improvement, Traffic Signals, Roadway Realignment | St. Charles |  | Reconstruction | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  |  | Design 90% Review | PE work has been completed. ROW authorization in FMIS on 8/14/20 |  |  |  | The project description in the FMIS action and EWG TIP are aligned. A FMIS action on 7/9/21 extended the construction award date by 12 months (July 2022). The EWG FY2022-2025 TIP update to be approved by the EWG in October 2021 reflects the new construction award program year of 2022. |  | 2021-09-28 19:34 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member | Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Title VI |  |  |  |  | 2021-09-29 15:53 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:15 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 | Environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-28 20:23 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build AAS Concur;#Design Build Certification | Design Build Certification |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:28 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0601 | 711063 | 7P0601 - Rte. I-49 Missouri Arkansas Connector | Bella Vista Bypass Connection for New I-49 | McDonald | 2021-09-30 | New Construction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Program Involvement Findings | Construction of new interstate section using BUILD funding | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization |  | Environmental Commitments;#Special Funding;#Change Order Approval;#VECP Approval;#Interstate Designation Request;#Title VI | Change Order Approval;#VECP Approval;#Environmental Commitments;#Special Funding |  | FY2021 Project is under construction. I have reviewed and approved 3 VECPs and 10 change orders since October 1. Additional change orders and VECPs were approved last PY.I prepared the final inspection report to document interstate standards. I have assited with preparing the request for acceptance into the Interstate system. FY2022 |  | 2021-09-29 15:31 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations | Bridge replacement using ATC | ATC | ATC |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:47 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I0445 | 0442293 | Rte. I-44, Webster Co. New Interchange in Marshfield - LPA Administered |  | Webster | 2021-07-27 |  | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | Yes | TRUE | FY21 | Program Involvement Findings |  |  |  |  | Title VI |  |  | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-29 15:35 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 |  | J9P3122 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [7 empty] | 2021-09-23 13:19 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 | Chester Bridge | Perry | 2022-06-22 | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Scoping;#Conceptual Report Review;#Design Build Procurement;#Design Build Certification;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#FMIS Authorization;#Conditional Clearance | [7 empty] | 2021-09-24 09:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 |  | J9P3305 | Scoping for bridge improvements over Current River and Round Spring. | SHANNON |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#Bridge TSandL;#Environmental Commitments | Core Team Member;#Conceptual Report Review;#Bridge TSandL | [6 empty] | 2021-09-23 13:20 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3584 | 0604090 | J9P3584 | Future I-57 and US60; Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds | NEW MADRID |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Scoping;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:36 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | BUTLER |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | BUTLER |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 | AJR Approval;#Design Preliminary Plans;#Conceptual Report Review | Conceptual Report Review;#Design Preliminary Plans;#AJR Approval |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Buy America;#Civil Rights/Cert Payroll |  |  | Provided recommnedation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 |  | J9P3751 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval | [6 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3764 |  | J9P3764 | Future I-57 Phase 1B Add lanes and outer roads to upgrade corridor to freeway standards from County RoadB 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Urgency;#Funding;#Environmental and Stakeholders;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:27 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | LPA City of O'Fallon I-70 at Bryan Road |  | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [6 empty] | no funds yet | 2021-09-29 07:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3232 J9S3232B | S701051/S703077 | J9S3232 & J9S3232B | Bootheel Bridge Bundle Design-Build | VARIOUS |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Environmental and Stakeholders;#Corporate Actions;#Local Considerations | Bundle Bridge project in rural area | Design Build Certification;#Design Build Procurement;#Design Build AAS Concur;#Design Exception Approval | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval |  | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America |  |  | Provided guidance on the Design-Build process. |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 & JP3496B | S502067 S502089 | J6P3496 & JP3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member | [7 empty] | 2021-09-29 07:29 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 |  | J9S3381 | Bridge replacement over Black River. Project involves bridge K0263. | Butler |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Schedule;#Environmental and Stakeholders;#Local Considerations | [9 empty] | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5640613 | 5640613 City of St. Peters | City of St. Peters Jungermann Road Bridge over branch of Spencer Creek, replace culverts (23077 & 23079) - 6563-15 | St. Charles County |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Schedule;#Project Administration;#Local Considerations | LPA project, utility related time extension and problematic contractor |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY 2021 Reviewed 3 change orders. Multiple discussions held on time extensions, LDs, and possible claim along with the format and eligibility of the change orders. 2 of the change orders were approved. The LPA has needed a lot of direction since this project had huge impacts to schedule and budget due to utilities. LP- CUF has been conduted for XL Contracting. No OJT hours on project. FY 2022 |  | 2021-09-25 09:41 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#PY20;#FY20;#FY22 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2021-09-25 10:16 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526 | 0552121 | J6I3526 | Scoping for corridor improvements along the I-55 corridor from 0.5 mile north of Rte. Z to 1 mile south of Rte. 67. Potential Design-Build project. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | 696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:14 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | n/a | 5417604 5417605 | 5417604 & 5417605 LPA City of St. Louis Jefferson/22nd Improvements | LPA City of St. Louis Jefferson/22nd Improvements | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Project Administration;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Design Exception Approval;#Design Preliminary Plans;#Design 90% Review |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Buy America;#Civil Rights/Cert Payroll;#Title VI |  |  | FY 2021 90% final plan package reviewed and multiple comments submitted including Buy America, proprietary items, traffic control, etc. No Design Exceptions have been submitted and none are expected. Most of the comments from the preliminary plan review were addressed. Project was giving conditional PS&E approval and FMIS authorization/obligation with a long list of conditions. MoDOT is monitoring the conditions. FY 2022 |  | 2021-09-29 16:02 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NA | NA | Pedestrian and Bikeways Improvements | Connect existing bikeways on 11th street and 12th street (Kansas City) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | TRUE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | No FMIS ACTION to-date. KC District staff indicate that this project will be authorized and funds obligated in the early Spring (2022). |  | 2021-09-27 13:25 | McMahon, Bradley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3359 | 0444204 | J6I3359 | Scoping for pedestrian studies at Selma Avenue Overpass and I-55 at Daycare Overpass. Project involves pedestrian bridges A1729 and A0619. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#Environmental Commitments | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | Project Authorization and Project Agreements;#Project Planning & Programming;#Project Financing;#Special Funding;#FMIS Authorization |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added: Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted. MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. Reviewed the consultant solicitation document issued by MoDOT. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J6P3510 | not assigned | J6P3510 | Scoping for ADA Transition Plan improvements at various locations in the St. Louis District. Potential DesignBuild project. | Various |  | ADA/Sidewalk | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | Not assigned | N/A | I-29 near Ambassador Drive, Permit Project | Potential Permit Project near KCI Airport at I-29 and Route D interchange near Ambassador Drive. | Platte |  | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE |  | Local Considerations;#Other | Proposed Dogbone Roundabout interchange at I-29 and Rt. D with connection to a development property. | TSandO Approval |  | Meetings and Review and approval of a TS&O report. | [5 empty] | 2021-09-23 14:59 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 | Scoping for interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#AJR Approval;#Design Exception Approval | [6 empty] | System to System Interchange / EIS reval | 2021-09-29 07:33 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
|  |  | J2P3347 | [5 empty] | No | TRUE | [11 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3661 | not assigned | J6P3661 | Scoping for corridor improvements from Rte. 100 to I-44. Project involves various bridges | Franklin |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | Scoping for capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## KC
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | Still a PODI | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | 2700509 | 2700509 | 2700509 - City of Fulton AID Demonstration | Bridge Replacement on 2nd ST Bridge over Stinson Creek and Stinson Creek Greenway, Bridge No. 1555011 located on State Route O in the City of Fulton. Accelerated Innovation Deployment (AID Demonstration program) | Callaway |  | Bridge Replacement | Pursley, Charles (FHWA);#37;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Discretionary Grant and Financing;#Project Administration;#Program Involvement Findings |  | Design Preliminary Plans;#Design 90% Review;#Special Funding;#Differing Eligibilities Review |  |  | Work Zone/TMP;#Bridge Inspection |  |  |  |  | 2021-09-29 08:05 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 4300112 | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  | Design PSandE Review;#Design PSandE Approval;#Environmental Commitments;#Core Team Member;#Design Preliminary Plans;#Other |  | Construction Inspections;#Erosion Control;#Civil Rights/Cert Payroll;#Work Zone/TMP;#Buy America |  | Construction inspections with focused review checklists. | FY 20 and FY 21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ. Submitted all monthly BUILD reports as required. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5617602 5617603 | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  | Design Preliminary Plans;#Design 90% Review;#Design PSandE Approval | Design Preliminary Plans;#Design 90% Review |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted. FY 2022 |  | 2021-09-29 06:56 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5901816 | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  | Design Build Procurement;#Environmental Commitments;#Design Preliminary Plans;#Design Build Certification | Design Build Procurement;#Design Build Certification |  | Environmental Commitments;#Special Funding;#Construction Inspections;#Title VI |  |  | The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. It is nearing completion and should be ready for execution soon. |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5903803 | 5903803 | 5903803 - Jefferson Avenue Foot Bridge Over BNSF Railroad in Springfield | Rehabilitate the Jefferson Avenue foot bridge and provide ADA access | Greene | 2021-11-01 | Bridge Rehabilitation | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Project Administration;#Program Involvement Findings |  | Design PSandE Review | Design PSandE Review |  | Construction Inspections;#Buy America;#Title VI |  |  |  |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Design Build Procurement;#AJR Approval;#Bridge 90% Review;#Interstate Designation Request |  | AJR (if required), Bridge and Roadway 90% plans, Interstate De-designation, Funding review, T&E review, NEPA EA review/approval, Design-Build procurement |  |  |  | FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. |  | 2021-09-20 17:44 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3029 | 0444188 | J6I3029 I-44 at I-270 and Meramec River Bridge |  | St. Louis |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | FALSE | FY21;#FY20;#PY19 | [8 empty] | FY 2021 Reviewed and approved 5 change orders with no issues. LP-CUF Reviews still need to be performed for DW Mertzke,Petro legistics, and Prestige truking. Project ending 2/2022. |  | 2021-09-24 10:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3109 | N/A | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. Project involves twin bridges A1293 in the NB and SB lanes. | Andrew |  | Bridge Replacement | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Schedule;#Project Administration;#Local Considerations;#Program Involvement Findings | Complexity: Likely to include head to head traffic on Interstate. Schedule: Scheduled bridge work has risk of delayed completion. Local considerations: Work Zone complexity will significantly impact traffic. | Contract Administration;#Construction Inspection & Quality |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Title VI |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Due to Covid-19 travel restrictions, no construction inspections were performed on this project. No PoDI activity occurred during PY21. The project is nearly completed so this project will not be retained as a PoDI in FY 22. |  | 2021-09-29 15:32 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3110 | 0292195 | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Atchison | 2020-03-20 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental & Stakeholders;#Funding | Construction inspection to include focused review checklists and a bridge inspection. |  |  | Construction inspection to include focused review checklists and a bridge inspection.. | Construction Inspections;#Work Zone/TMP;#Buy America;#Erosion Control;#Bridge Inspection |  | Construction inspection to include focused review checklists and a bridge inspection. | FY 21: The project has been awarded and construction started in the Spring of 2021. No PoDI activity was performed due to the COVID pandemic travel restrictions. The project has been retained as a construction PoDI for FY 22. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1P3378 | not assigned | Rt. 136 Flood Resiliency Permanent Repair | Flood Resiliency Permanent Repair from Mo. River to I-29 near Rock Port. Atchison County | Atchison | 2022-04-15 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Local Considerations;#Funding | ER funded flood resiliency project. | Design 90% Review |  | Review of 90% Plans and compare to approved DDIR. |  |  |  | FY21: Reviewed resiliency proposal and DDIR and had multiple meetings to discuss the benefit/cost analysis expectations. Approved DDIR and resiliency proposal. |  | 2021-09-23 14:46 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-02-25 | Pavement and Bridge | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. | Final Design;#Plan, Specification, & Estimate Development;#Advertising & Award;#Core Team Member;#Special Funding | Design Preliminary Plans;#Conceptual Report Review;#Environmental Commitments | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting. | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Environmental Commitments;#Buy America |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | Not Assigned | J2I3274 | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | MONTGOMERY |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3309 | 0703276 | J2I3309 | Pavement improvements from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | MONTGOMERY |  | Pavement Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3310 | 0703286 | J2I3310 | Pavement resurfacing from the Callaway County line to 2 miles east of Rte. F near High Hill. | MONTGOMERY |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | Conceptual Report Review |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review;#Civil Rights/Cert Payroll |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 | Scoping for interchange improvements at Stracks Church County Road near Wright City. | WARREN |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3043 | 0471083 | J2P3043 | Interchange improvements at Rte. 61 in Troy. Project involves bridge A2604. | LINCOLN |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2S3221 J2P3222 J2P3 | S201034 / 13620 | J2S3221 / J2P3222 / J2P3224 |  | SCHUYLER |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-29 07:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | MONTGOMERY |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#AJR Approval |  | Title VI |  |  |  |  | 2021-09-29 15:37 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3226 J2I3226B | 0703279 | Rte. I-70, Mineola Hill Truck Climbing Lanes |  | Montgomery | 2021-07-01 | Reconstruction | Pursley, Charles (FHWA);#37 | Yes | FALSE | FY21 | [8 empty] | Project is under construction. I have attended a weekly project status update meeting to track the project progress through construction. Weekly meetings have not been held since December 2020. I have not approved any change orders or VECPs since October 1. Those activities were complete last PY. The final quarterly project QC/QMmeeting was held on June 23, 2021. I atended as well as the Paement and Materiasl Specialist. |  | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3156 | 0544065 | J2P3156 | Add roundabout at Rte. 19 north junction (Basinger Corner) north of Laddonia. $2,346,000 Open Container funds. | Audrain |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Urgency;#Environmental and Stakeholders |  |  |  |  | Construction Inspections |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3259 | 0614179 | J2P3259 | Pavement resurfacing on northbound lanes from Rte. V to 0.4 mile south of Rte. UU in Pike County near Bowling Green. | Lincoln |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity |  |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll;#Pavement/Materials Review |  |  |  |  | 2021-09-23 14:25 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3357 | 0791082 | J2P3357 | Bridge replacement over Lyon Street, Warren Barrett Drive, Burlington Northern Santa Fe Railroad and Bear Creek 0.4 mile north of Rte. T in Hannibal. | MARION |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Program Involvement Findings |  | Core Team Member;#Design Preliminary Plans;#Differing Eligibilities Review |  |  | Title VI |  |  |  |  | 2021-09-29 15:34 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3447 | Not Assigned | J2P3447 | Scoping for roadway improvement between Bus. 54 and Rte. 79 in Louisiana. | Audrain |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member | [7 empty] | 2021-09-23 14:12 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900391 | 9900391 | TAP 9900 (391) LPA: NE District - CONSTRUCTION |  | TROY |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval |  | The previously approved AJR will be reevaluated and updated. Title VI review. | [5 empty] | 2021-09-29 15:56 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I2006 | 0351291 | Add interchange south of Rte. 92 at 19th Street in Kearney. | New Interchange on I-35 at Kearney | Clay | 2022-02-25 | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Local Considerations;#National/Regional Significance;#Program Involvement Findings | New interchange construction with a Diverging Diamond interchange configuration and new bridge. |  |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | Title VI |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | The project has been delayed due to ROW acquisition delays, therefore no construction activities have been performed. The project is expected to be let in early 2022. Significant utility relocation is required before construction begins so the main construction will likely occur in FY23. Will consider including as a PoDI during FY23. |  | 2021-09-29 15:29 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | N/A | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY21 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification could require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#Design 90% Review;#AJR Approval;#Design Exception Approval;#Differing Eligibilities Review |  | Core team member. NEPA review and approval. AJR or Traffic Safety and Operational Analysis will likely be required. 90% Plans review and design exception approval. |  |  |  | FHWA has participated in 3 core team meetings and have offered feedback on the level of documentation and analysis needed for multiple interchange configurations. A separate meeting with the HQ Major project specialist was held to confirm that this project was not considered a Major Project as defined by FHWA and will not need a FP nor Major Project Plan. This information was shared with MoDOT. |  | 2021-09-29 08:11 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3189 | 4351323 | I-435 Bridge over the Missouri River in Kansas City, MO | Bridge deck replacement at the Missouri River. Project involves twin bridges A0767. | Clay | 2019-05-17 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Other;#Urgency;#Complexity;#Local Considerations;#Program Involvement Findings | Schedule: Work zone impacts will be significant and will require expedited construction. Local Consideration: Work zone impacts will be regionally significant. |  |  | Construction inspection to include focused checklist for Work Zone Traffic Control. | Work Zone/TMP;#Title VI |  | Construction inspections to include a focused checklist for Work Zone Traffic Control. | FY 21: Due to Covid-19 travel restrictions, no construction inspections were performed on this project. There has been no PoDI involvement this performance year. The project is scheduled to be completed at the end of 2021 and it will be retained as a PoDI project to include a work zone traffic control review. |  | 2021-09-29 16:08 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4P2237 | S300097 | J4P2237- I-49 Outer Roads Conversion to from One-way to Two-way | Conversion of the outer roads of I-49 to two-way traffic on the east outer road from Rt. 150 to Blue Ridge Boulevard and on the west outer road from Blue Ridge Boulevard to 0.5 miles north of Rt. 150 in Grandview. | Jackson | 2023-09-30 |  | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Project Administration;#Local Considerations;#Program Involvement Findings | Large complex local project using the Design-Build delivery method with limited experience by City staff. ROW and Utility impacts that could impace schedule. Complex traffic control during construction with significant traffic impacts on the local and interstate highways. | Contract Administration;#AJR Approval | Environmental Commitments;#AJR Approval;#Design Build AAS Concur;#Design Build Certification;#Design Build Procurement;#FMIS Authorization |  | Title VI;#Work Zone/TMP |  | Construction inspections. Focused Reviews on Title VI and Work Zone Traffic Control. FHWA will continue to provide feedback on proposed revisions to the approved AJR and will coordinate with MoDOT and the City on these changes and any required approval. | Reviewed all books of Draft RFP and provided comments on Books 1 and 2, and ITP. • During the confidential one-one-one meetings, I coordinated review of potential AJR deviations with Division staff and leadership. Reviewed proposed TS&O reports and offered feedback and concerns to MoDOT on all three teams’ draft submittals. • Worked with Mike Landvik and Jim Stevenson to develop a draft LPA Design-Build checklist template for use on future LPA Design-Build projects. • Provided recommendations on how to structure the RFP documents when these were in the early stages of development. Assured that federal requirements were conveyed and followed. • Coordinated involvement on an ADA concern from both Civil Rights and Environmental staff members from MoDOT and FHWA to assure that the decision by the City to modify the sidewalk requirements in the RFP did not violate NEPA and/or ADA requirements. • Reviewed and approved the final RFP for release and facilitated the FMIS construction authorization. This took quite a bit of time since the process for approval was different than traditional D-B-B project authorizations. I provided guidance on the RFP certification letter and what needed to be included in the submittal. MoDOT and the City were very appreciative of this guidance and involvement. • Reviewed the proposals and participated in the proposal evaluation process and offered feedback on how FHWA could concur in the project award. Concurred in project award. Reviewed proposed AJR changes and offered valuable feedback. Coordinated a meeting to convey FHWA expectations on the criteria for acceptance of a proposed AJR revision involving a proposed roundabout in lieu of the approved configuration.s expectation |  | 2021-09-29 15:57 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900086 | 9900086 | TAP 9900(086) LPA: NE District - CONSTRUCTION |  | CITY OF EAST PRAIRIE |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#PY20;#PY19 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. |  | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance;#Scoping;#Special Funding;#Bridge TSandL |  | Change Order Approval;#Work Zone/TMP;#Civil Rights/Cert Payroll;#Erosion Control;#DBE Goals;#Buy America;#Title VI |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21: Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21. Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. Reviewed and provided comments to revised project AJR and issued approval. Submitted all required monthly project reports through September, 2021. Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan in coordination with the Division Office Pavement and Materials Engineer. |  | 2021-09-29 15:58 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  | Project Authorization and Project Agreements;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. |  | 2021-09-27 15:19 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397,J5I3572, | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. | Design PSandE Review |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:22 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | B015001 | B015001 | Camden Co. Bridge Replacement on Willow Creek Road |  | Camden |  |  | Pursley, Charles (FHWA);#37 | No | FALSE | FY21 | [8 empty] | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3369 | S402035 | 5S3369 - Central District ADA Improvements - Alternate Project Delivery Method | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address Route: Various nonstandard ADA facilities at various locations in the Central and Northwest Districts. | Various | 2021-11-01 | ADA/Sidewalk | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#Design Build AAS Concur | Design Build Procurement;#Design Build Certification |  | Construction Inspections;#Work Zone/TMP;#ADA |  |  | FY2021-The DB team spent a lot of time refining the project scope. I attended several core team meetings and provided a lot of guidance and advice on the DB process as well as NEPA compliance. The RFQ has been developed and the RFP is being finalized. I reviewed these document and provided input and guidance. FY2022 - |  | 2021-09-27 15:26 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5P3337 | 0543193 | Missouri River Bridge in Jefferson Cit | Bridge rehabilitation over Missouri River. Project involves bridges A4497 and L0550. | Cole, Callaway |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Complexity;#Schedule;#National/Regional Significance;#Local Considerations | [9 empty] | 2021-09-28 20:20 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3269 | S401083 | J5S3269 | Pave Resurfacing from Bus 44 to Rt J, Includes Pave Inprove on Rt H from Rt 17 to End of State Maintenance | Pulaski |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3296 | 0171015 | J9P3296 - Program Development | Pavement Improvements from Route 106 in Summersville to Route 160 Near West Plains, 34.064 miles | TEXAS |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 3219702 | 3219702 | 3219702 | Design to Replace Old Dilapidated Sidewalks Along Main from 15th to 11 St | Jasper |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Other;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#TSandO Approval;#Design Exception Approval;#Differing Eligibilities Review | [6 empty] | VE Study scheduled / OINCC submittal / Major Project | 2021-09-29 17:00 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2090 | 2705360 | J6I2090 | Bridge replacement, bridge rehabilitation and pavement repair over Conway Road and New Ballas Road and bridge rehabilitation for I-270 mainline and ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052, A4654, A4657, A4580 and A4581. | St. Louis |  | Bridge Replacement |  | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations |  | Core Team Member;#TSandO Approval;#Design Exception Approval;#Design Preliminary Plans |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:01 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2222 | 0641061 | J6I2222 I-64 at 22nd and Jefferson | Modify interchange configuration between 18th Street and Garrison Avenue. Project involves bridges A1523, A1501, A1528, A0840, and A0838. $7,900,000 Cost Share and $7,900,000 Land Clearance for Redevelopment Authority funds. | St. Louis City | 2020-05-15 | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Schedule;#Cost;#Urgency;#Environmental & Stakeholders;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 7 change orders with no comments. Reviewed and approved 2 VECP with no comments. The VECPs were previously discussed in the PAVE that was held after award and before NTP. LP-Project has 3 trainee spots of 1000 hours each. Prime says they will not use trainees until summer 2021. Project is scheduled to be completed 6/2022. CUF still needed for D&K Welding. FY 2022 |  | 2021-09-29 17:02 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 Rte N EA | Scoping for environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | New Construction | Peters, Taylor (FHWA);#43 | No | FALSE | FY21 | Environmental & Stakeholders |  | EA/EIS Public Involvement | EA/EIS Public Involvement | [6 empty] | 2021-09-29 07:32 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 & J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Local Considerations |  | Core Team Member | Core Team Member |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:13 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  | Bridge 90% Review;#Design Exception Approval;#Design 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design 90% Review;#Design Exception Approval;#Bridge 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2021-09-28 10:36 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [5 empty] | FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination. FY 2022 |  | 2021-09-29 06:44 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments | [6 empty] | Part of I-270 North Major project / EA reval | 2021-09-29 07:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3233 | not assigned | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371) | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371). Excludes bridge along Missouri River in St. Joseph. | Andrew | 2020-06-19 | Resurfacing | Irving, Kevin (FHWA);#29 | Yes | FALSE | FY21 | Complexity;#Schedule;#Local Considerations | Contract Administration. Pavement and materials quality. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. |  |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. | Due to Covid-19 travel restrictions, construction inspections could not be performed on this project. There were no project actions on this project during FY 21. The project has been completed and therefore will not be carried over as a PoDI in FY 22. |  | 2021-09-21 18:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3201 | 4952604 | J6I3201 LPA David Hoekel Parkway I-70 Interchange Phase 1 and Phase 2 | Payment to Wentzville for adding interchange west of Point Prairie Road. $5,000,000 Cost Share funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Environmental and Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 8 change orders with no issues. No VECP's have been submitted and none are expected. LP- A CUF review is need for Columbia Curb and Gutter. Project has an OJT Goal of 1 trainee for 1000 hours. Contractor says they are looking for a trainee to use summer 2021. Project closing is delayed until 11/2021. FY 2022 |  | 2021-09-29 06:50 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval;#Core Team Member;#Design Preliminary Plans;#ATC;#FMIS Authorization;#CMAQ Project Review;#Design 90% Review | AJR Approval;#Design Build Certification;#FMIS Authorization;#CMAQ Project Review;#Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America;#Pavement/Materials Review;#Quality Control;#Bridge Inspection;#Title VI |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed. FY 2022 |  | 2021-09-29 15:59 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 & J6I3500 | 2553052 &255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Cost;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review | Core Team Member;#Design Preliminary Plans;#Design PSandE Review;#Other |  | Construction Inspections;#Work Zone/TMP;#Bridge Inspection |  |  |  | VE Study | 2021-09-29 06:57 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:30 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3167 | 0073024 | Rte. 7 and South Ave. Signalization Improvements | Add a signalized intersection at Rte. 7 intersection sidewalk connections (Blue Springs) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | This project was originally programmed as an LPA project sponsored by the City of Blue Springs with the TIP #625033. It was later combined with a MoDOT sponsored project under the TIP #690490 and MoDOT Job Number 4S3167. FMIS action completed 5/14/21. The integration of the LPA CMAQ project into the MoDOT project was correctly programmed and the FMIS action aligned with the programming actions. . |  | 2021-09-28 19:38 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P2321 J6P2321B | 0471072 0471080 | FY 2014 TIGER VI J6P2321 & J6P2321B: MO-47 - Bridge over Missouri River | FY 2014 TIGER ​Replace bridge over the Missouri River from Rte. 94 to Fifth Street in Washington. Cost share: $500,000 city of Washington, $250,000 Franklin County and $50,000 Warren County. | Franklin | 2016-05-20 | Bridge Replacement | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#PY20;#PY19;#PY18;#PY17;#PY16;#FY22 | Funding;#Other |  |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY2021 The project is substantially complete with aethetic lighting still be completed. Due to COVID restrictions, the subcontractor has not been able to travel. All TIGER funds have been expended. Project is submitting all quarterly reports and performance measure reports on time as required. FY2022 |  | 2021-09-29 06:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 7302674 | 7302674 | CMAQ - 7302(674) Intersection Improvements | CMAQ - 7302(674) Intersection Improvements - Intersection Improvement, Traffic Signals, Roadway Realignment | St. Charles |  | Reconstruction | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  |  | Design 90% Review | PE work has been completed. ROW authorization in FMIS on 8/14/20 |  |  |  | The project description in the FMIS action and EWG TIP are aligned. A FMIS action on 7/9/21 extended the construction award date by 12 months (July 2022). The EWG FY2022-2025 TIP update to be approved by the EWG in October 2021 reflects the new construction award program year of 2022. |  | 2021-09-28 19:34 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member | Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Title VI |  |  |  |  | 2021-09-29 15:53 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:15 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 | Environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-28 20:23 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build AAS Concur;#Design Build Certification | Design Build Certification |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:28 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0601 | 711063 | 7P0601 - Rte. I-49 Missouri Arkansas Connector | Bella Vista Bypass Connection for New I-49 | McDonald | 2021-09-30 | New Construction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Program Involvement Findings | Construction of new interstate section using BUILD funding | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization |  | Environmental Commitments;#Special Funding;#Change Order Approval;#VECP Approval;#Interstate Designation Request;#Title VI | Change Order Approval;#VECP Approval;#Environmental Commitments;#Special Funding |  | FY2021 Project is under construction. I have reviewed and approved 3 VECPs and 10 change orders since October 1. Additional change orders and VECPs were approved last PY.I prepared the final inspection report to document interstate standards. I have assited with preparing the request for acceptance into the Interstate system. FY2022 |  | 2021-09-29 15:31 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations | Bridge replacement using ATC | ATC | ATC |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:47 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I0445 | 0442293 | Rte. I-44, Webster Co. New Interchange in Marshfield - LPA Administered |  | Webster | 2021-07-27 |  | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | Yes | TRUE | FY21 | Program Involvement Findings |  |  |  |  | Title VI |  |  | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-29 15:35 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 |  | J9P3122 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [7 empty] | 2021-09-23 13:19 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 | Chester Bridge | Perry | 2022-06-22 | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Scoping;#Conceptual Report Review;#Design Build Procurement;#Design Build Certification;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#FMIS Authorization;#Conditional Clearance | [7 empty] | 2021-09-24 09:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 |  | J9P3305 | Scoping for bridge improvements over Current River and Round Spring. | SHANNON |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#Bridge TSandL;#Environmental Commitments | Core Team Member;#Conceptual Report Review;#Bridge TSandL | [6 empty] | 2021-09-23 13:20 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3584 | 0604090 | J9P3584 | Future I-57 and US60; Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds | NEW MADRID |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Scoping;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:36 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | BUTLER |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | BUTLER |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 | AJR Approval;#Design Preliminary Plans;#Conceptual Report Review | Conceptual Report Review;#Design Preliminary Plans;#AJR Approval |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Buy America;#Civil Rights/Cert Payroll |  |  | Provided recommnedation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 |  | J9P3751 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval | [6 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3764 |  | J9P3764 | Future I-57 Phase 1B Add lanes and outer roads to upgrade corridor to freeway standards from County RoadB 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Urgency;#Funding;#Environmental and Stakeholders;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:27 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | LPA City of O'Fallon I-70 at Bryan Road |  | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [6 empty] | no funds yet | 2021-09-29 07:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3232 J9S3232B | S701051/S703077 | J9S3232 & J9S3232B | Bootheel Bridge Bundle Design-Build | VARIOUS |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Environmental and Stakeholders;#Corporate Actions;#Local Considerations | Bundle Bridge project in rural area | Design Build Certification;#Design Build Procurement;#Design Build AAS Concur;#Design Exception Approval | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval |  | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America |  |  | Provided guidance on the Design-Build process. |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 & JP3496B | S502067 S502089 | J6P3496 & JP3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member | [7 empty] | 2021-09-29 07:29 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 |  | J9S3381 | Bridge replacement over Black River. Project involves bridge K0263. | Butler |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Schedule;#Environmental and Stakeholders;#Local Considerations | [9 empty] | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5640613 | 5640613 City of St. Peters | City of St. Peters Jungermann Road Bridge over branch of Spencer Creek, replace culverts (23077 & 23079) - 6563-15 | St. Charles County |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Schedule;#Project Administration;#Local Considerations | LPA project, utility related time extension and problematic contractor |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY 2021 Reviewed 3 change orders. Multiple discussions held on time extensions, LDs, and possible claim along with the format and eligibility of the change orders. 2 of the change orders were approved. The LPA has needed a lot of direction since this project had huge impacts to schedule and budget due to utilities. LP- CUF has been conduted for XL Contracting. No OJT hours on project. FY 2022 |  | 2021-09-25 09:41 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#PY20;#FY20;#FY22 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2021-09-25 10:16 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526 | 0552121 | J6I3526 | Scoping for corridor improvements along the I-55 corridor from 0.5 mile north of Rte. Z to 1 mile south of Rte. 67. Potential Design-Build project. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | 696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:14 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | n/a | 5417604 5417605 | 5417604 & 5417605 LPA City of St. Louis Jefferson/22nd Improvements | LPA City of St. Louis Jefferson/22nd Improvements | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Project Administration;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Design Exception Approval;#Design Preliminary Plans;#Design 90% Review |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Buy America;#Civil Rights/Cert Payroll;#Title VI |  |  | FY 2021 90% final plan package reviewed and multiple comments submitted including Buy America, proprietary items, traffic control, etc. No Design Exceptions have been submitted and none are expected. Most of the comments from the preliminary plan review were addressed. Project was giving conditional PS&E approval and FMIS authorization/obligation with a long list of conditions. MoDOT is monitoring the conditions. FY 2022 |  | 2021-09-29 16:02 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NA | NA | Pedestrian and Bikeways Improvements | Connect existing bikeways on 11th street and 12th street (Kansas City) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | TRUE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | No FMIS ACTION to-date. KC District staff indicate that this project will be authorized and funds obligated in the early Spring (2022). |  | 2021-09-27 13:25 | McMahon, Bradley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3359 | 0444204 | J6I3359 | Scoping for pedestrian studies at Selma Avenue Overpass and I-55 at Daycare Overpass. Project involves pedestrian bridges A1729 and A0619. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#Environmental Commitments | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | Project Authorization and Project Agreements;#Project Planning & Programming;#Project Financing;#Special Funding;#FMIS Authorization |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added: Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted. MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. Reviewed the consultant solicitation document issued by MoDOT. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J6P3510 | not assigned | J6P3510 | Scoping for ADA Transition Plan improvements at various locations in the St. Louis District. Potential DesignBuild project. | Various |  | ADA/Sidewalk | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | Not assigned | N/A | I-29 near Ambassador Drive, Permit Project | Potential Permit Project near KCI Airport at I-29 and Route D interchange near Ambassador Drive. | Platte |  | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE |  | Local Considerations;#Other | Proposed Dogbone Roundabout interchange at I-29 and Rt. D with connection to a development property. | TSandO Approval |  | Meetings and Review and approval of a TS&O report. | [5 empty] | 2021-09-23 14:59 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 | Scoping for interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#AJR Approval;#Design Exception Approval | [6 empty] | System to System Interchange / EIS reval | 2021-09-29 07:33 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
|  |  | J2P3347 | [5 empty] | No | TRUE | [11 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3661 | not assigned | J6P3661 | Scoping for corridor improvements from Rte. 100 to I-44. Project involves various bridges | Franklin |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | Scoping for capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## NE
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | Still a PODI | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | 2700509 | 2700509 | 2700509 - City of Fulton AID Demonstration | Bridge Replacement on 2nd ST Bridge over Stinson Creek and Stinson Creek Greenway, Bridge No. 1555011 located on State Route O in the City of Fulton. Accelerated Innovation Deployment (AID Demonstration program) | Callaway |  | Bridge Replacement | Pursley, Charles (FHWA);#37;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Discretionary Grant and Financing;#Project Administration;#Program Involvement Findings |  | Design Preliminary Plans;#Design 90% Review;#Special Funding;#Differing Eligibilities Review |  |  | Work Zone/TMP;#Bridge Inspection |  |  |  |  | 2021-09-29 08:05 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 4300112 | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  | Design PSandE Review;#Design PSandE Approval;#Environmental Commitments;#Core Team Member;#Design Preliminary Plans;#Other |  | Construction Inspections;#Erosion Control;#Civil Rights/Cert Payroll;#Work Zone/TMP;#Buy America |  | Construction inspections with focused review checklists. | FY 20 and FY 21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ. Submitted all monthly BUILD reports as required. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5617602 5617603 | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  | Design Preliminary Plans;#Design 90% Review;#Design PSandE Approval | Design Preliminary Plans;#Design 90% Review |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted. FY 2022 |  | 2021-09-29 06:56 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5901816 | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  | Design Build Procurement;#Environmental Commitments;#Design Preliminary Plans;#Design Build Certification | Design Build Procurement;#Design Build Certification |  | Environmental Commitments;#Special Funding;#Construction Inspections;#Title VI |  |  | The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. It is nearing completion and should be ready for execution soon. |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5903803 | 5903803 | 5903803 - Jefferson Avenue Foot Bridge Over BNSF Railroad in Springfield | Rehabilitate the Jefferson Avenue foot bridge and provide ADA access | Greene | 2021-11-01 | Bridge Rehabilitation | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Project Administration;#Program Involvement Findings |  | Design PSandE Review | Design PSandE Review |  | Construction Inspections;#Buy America;#Title VI |  |  |  |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Design Build Procurement;#AJR Approval;#Bridge 90% Review;#Interstate Designation Request |  | AJR (if required), Bridge and Roadway 90% plans, Interstate De-designation, Funding review, T&E review, NEPA EA review/approval, Design-Build procurement |  |  |  | FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. |  | 2021-09-20 17:44 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3029 | 0444188 | J6I3029 I-44 at I-270 and Meramec River Bridge |  | St. Louis |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | FALSE | FY21;#FY20;#PY19 | [8 empty] | FY 2021 Reviewed and approved 5 change orders with no issues. LP-CUF Reviews still need to be performed for DW Mertzke,Petro legistics, and Prestige truking. Project ending 2/2022. |  | 2021-09-24 10:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3109 | N/A | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. Project involves twin bridges A1293 in the NB and SB lanes. | Andrew |  | Bridge Replacement | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Schedule;#Project Administration;#Local Considerations;#Program Involvement Findings | Complexity: Likely to include head to head traffic on Interstate. Schedule: Scheduled bridge work has risk of delayed completion. Local considerations: Work Zone complexity will significantly impact traffic. | Contract Administration;#Construction Inspection & Quality |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Title VI |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Due to Covid-19 travel restrictions, no construction inspections were performed on this project. No PoDI activity occurred during PY21. The project is nearly completed so this project will not be retained as a PoDI in FY 22. |  | 2021-09-29 15:32 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3110 | 0292195 | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Atchison | 2020-03-20 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental & Stakeholders;#Funding | Construction inspection to include focused review checklists and a bridge inspection. |  |  | Construction inspection to include focused review checklists and a bridge inspection.. | Construction Inspections;#Work Zone/TMP;#Buy America;#Erosion Control;#Bridge Inspection |  | Construction inspection to include focused review checklists and a bridge inspection. | FY 21: The project has been awarded and construction started in the Spring of 2021. No PoDI activity was performed due to the COVID pandemic travel restrictions. The project has been retained as a construction PoDI for FY 22. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1P3378 | not assigned | Rt. 136 Flood Resiliency Permanent Repair | Flood Resiliency Permanent Repair from Mo. River to I-29 near Rock Port. Atchison County | Atchison | 2022-04-15 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Local Considerations;#Funding | ER funded flood resiliency project. | Design 90% Review |  | Review of 90% Plans and compare to approved DDIR. |  |  |  | FY21: Reviewed resiliency proposal and DDIR and had multiple meetings to discuss the benefit/cost analysis expectations. Approved DDIR and resiliency proposal. |  | 2021-09-23 14:46 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-02-25 | Pavement and Bridge | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. | Final Design;#Plan, Specification, & Estimate Development;#Advertising & Award;#Core Team Member;#Special Funding | Design Preliminary Plans;#Conceptual Report Review;#Environmental Commitments | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting. | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Environmental Commitments;#Buy America |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | Not Assigned | J2I3274 | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | MONTGOMERY |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3309 | 0703276 | J2I3309 | Pavement improvements from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | MONTGOMERY |  | Pavement Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3310 | 0703286 | J2I3310 | Pavement resurfacing from the Callaway County line to 2 miles east of Rte. F near High Hill. | MONTGOMERY |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | Conceptual Report Review |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review;#Civil Rights/Cert Payroll |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 | Scoping for interchange improvements at Stracks Church County Road near Wright City. | WARREN |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3043 | 0471083 | J2P3043 | Interchange improvements at Rte. 61 in Troy. Project involves bridge A2604. | LINCOLN |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2S3221 J2P3222 J2P3 | S201034 / 13620 | J2S3221 / J2P3222 / J2P3224 |  | SCHUYLER |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-29 07:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | MONTGOMERY |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#AJR Approval |  | Title VI |  |  |  |  | 2021-09-29 15:37 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3226 J2I3226B | 0703279 | Rte. I-70, Mineola Hill Truck Climbing Lanes |  | Montgomery | 2021-07-01 | Reconstruction | Pursley, Charles (FHWA);#37 | Yes | FALSE | FY21 | [8 empty] | Project is under construction. I have attended a weekly project status update meeting to track the project progress through construction. Weekly meetings have not been held since December 2020. I have not approved any change orders or VECPs since October 1. Those activities were complete last PY. The final quarterly project QC/QMmeeting was held on June 23, 2021. I atended as well as the Paement and Materiasl Specialist. |  | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3156 | 0544065 | J2P3156 | Add roundabout at Rte. 19 north junction (Basinger Corner) north of Laddonia. $2,346,000 Open Container funds. | Audrain |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Urgency;#Environmental and Stakeholders |  |  |  |  | Construction Inspections |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3259 | 0614179 | J2P3259 | Pavement resurfacing on northbound lanes from Rte. V to 0.4 mile south of Rte. UU in Pike County near Bowling Green. | Lincoln |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity |  |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll;#Pavement/Materials Review |  |  |  |  | 2021-09-23 14:25 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3357 | 0791082 | J2P3357 | Bridge replacement over Lyon Street, Warren Barrett Drive, Burlington Northern Santa Fe Railroad and Bear Creek 0.4 mile north of Rte. T in Hannibal. | MARION |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Program Involvement Findings |  | Core Team Member;#Design Preliminary Plans;#Differing Eligibilities Review |  |  | Title VI |  |  |  |  | 2021-09-29 15:34 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3447 | Not Assigned | J2P3447 | Scoping for roadway improvement between Bus. 54 and Rte. 79 in Louisiana. | Audrain |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member | [7 empty] | 2021-09-23 14:12 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900391 | 9900391 | TAP 9900 (391) LPA: NE District - CONSTRUCTION |  | TROY |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval |  | The previously approved AJR will be reevaluated and updated. Title VI review. | [5 empty] | 2021-09-29 15:56 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I2006 | 0351291 | Add interchange south of Rte. 92 at 19th Street in Kearney. | New Interchange on I-35 at Kearney | Clay | 2022-02-25 | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Local Considerations;#National/Regional Significance;#Program Involvement Findings | New interchange construction with a Diverging Diamond interchange configuration and new bridge. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | Work Zone/TMP;#Title VI |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | The project has been delayed due to ROW acquisition delays, therefore no construction activities have been performed. The project is expected to be let in early 2022. Significant utility relocation is required before construction begins so the main construction will likely occur in FY23. Will consider including as a PoDI during FY23. |  | 2021-09-29 15:29 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | N/A | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY21 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification could require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#Design 90% Review;#AJR Approval;#Design Exception Approval;#Differing Eligibilities Review |  | Core team member. NEPA review and approval. AJR or Traffic Safety and Operational Analysis will likely be required. 90% Plans review and design exception approval. |  |  |  | FHWA has participated in 3 core team meetings and have offered feedback on the level of documentation and analysis needed for multiple interchange configurations. A separate meeting with the HQ Major project specialist was held to confirm that this project was not considered a Major Project as defined by FHWA and will not need a FP nor Major Project Plan. This information was shared with MoDOT. |  | 2021-09-29 08:11 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3189 | 4351323 | I-435 Bridge over the Missouri River in Kansas City, MO | Bridge deck replacement at the Missouri River. Project involves twin bridges A0767. | Clay | 2019-05-17 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Other;#Urgency;#Complexity;#Local Considerations;#Program Involvement Findings | Schedule: Work zone impacts will be significant and will require expedited construction. Local Consideration: Work zone impacts will be regionally significant. |  |  | Construction inspection to include focused checklist for Work Zone Traffic Control. | Work Zone/TMP;#Title VI |  | Construction inspections to include a focused checklist for Work Zone Traffic Control. | FY 21: Due to Covid-19 travel restrictions, no construction inspections were performed on this project. There has been no PoDI involvement this performance year. The project is scheduled to be completed at the end of 2021 and it will be retained as a PoDI project to include a work zone traffic control review. |  | 2021-09-29 16:08 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4P2237 | S300097 | J4P2237- I-49 Outer Roads Conversion to from One-way to Two-way | Conversion of the outer roads of I-49 to two-way traffic on the east outer road from Rt. 150 to Blue Ridge Boulevard and on the west outer road from Blue Ridge Boulevard to 0.5 miles north of Rt. 150 in Grandview. | Jackson | 2023-09-30 |  | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Project Administration;#Local Considerations;#Program Involvement Findings | Large complex local project using the Design-Build delivery method with limited experience by City staff. ROW and Utility impacts that could impace schedule. Complex traffic control during construction with significant traffic impacts on the local and interstate highways. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Contract Administration;#Other | Environmental Commitments;#AJR Approval;#Design Build AAS Concur;#Design Build Certification;#Design Build Procurement;#FMIS Authorization |  | Title VI;#Work Zone/TMP |  | Construction inspections. Focused Reviews on Title VI and Work Zone Traffic Control. FHWA will continue to provide feedback on proposed revisions to the approved AJR and will coordinate with MoDOT and the City on these changes and any required approval. | Reviewed all books of Draft RFP and provided comments on Books 1 and 2, and ITP. • During the confidential one-one-one meetings, I coordinated review of potential AJR deviations with Division staff and leadership. Reviewed proposed TS&O reports and offered feedback and concerns to MoDOT on all three teams’ draft submittals. • Worked with Mike Landvik and Jim Stevenson to develop a draft LPA Design-Build checklist template for use on future LPA Design-Build projects. • Provided recommendations on how to structure the RFP documents when these were in the early stages of development. Assured that federal requirements were conveyed and followed. • Coordinated involvement on an ADA concern from both Civil Rights and Environmental staff members from MoDOT and FHWA to assure that the decision by the City to modify the sidewalk requirements in the RFP did not violate NEPA and/or ADA requirements. • Reviewed and approved the final RFP for release and facilitated the FMIS construction authorization. This took quite a bit of time since the process for approval was different than traditional D-B-B project authorizations. I provided guidance on the RFP certification letter and what needed to be included in the submittal. MoDOT and the City were very appreciative of this guidance and involvement. • Reviewed the proposals and participated in the proposal evaluation process and offered feedback on how FHWA could concur in the project award. Concurred in project award. Reviewed proposed AJR changes and offered valuable feedback. Coordinated a meeting to convey FHWA expectations on the criteria for acceptance of a proposed AJR revision involving a proposed roundabout in lieu of the approved configuration.s expectation |  | 2021-09-29 15:57 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900086 | 9900086 | TAP 9900(086) LPA: NE District - CONSTRUCTION |  | CITY OF EAST PRAIRIE |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#PY20;#PY19 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. | Innovative Contracting/Design Build;#Contract Administration;#Construction Inspection & Quality;#Other;#Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance;#Scoping;#Special Funding;#Bridge TSandL |  | Change Order Approval;#Work Zone/TMP;#Civil Rights/Cert Payroll;#Erosion Control;#DBE Goals;#Buy America;#Title VI |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21: Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21. Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. Reviewed and provided comments to revised project AJR and issued approval. Submitted all required monthly project reports through September, 2021. Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan in coordination with the Division Office Pavement and Materials Engineer. |  | 2021-09-29 15:58 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  | Project Authorization and Project Agreements;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. |  | 2021-09-27 15:19 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397,J5I3572, | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. | Design PSandE Review |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:22 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | B015001 | B015001 | Camden Co. Bridge Replacement on Willow Creek Road |  | Camden |  |  | Pursley, Charles (FHWA);#37 | No | FALSE | FY21 | [8 empty] | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3369 | S402035 | 5S3369 - Central District ADA Improvements - Alternate Project Delivery Method | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address Route: Various nonstandard ADA facilities at various locations in the Central and Northwest Districts. | Various | 2021-11-01 | ADA/Sidewalk | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#Design Build AAS Concur | Design Build Procurement;#Design Build Certification |  | Construction Inspections;#Work Zone/TMP;#ADA |  |  | FY2021-The DB team spent a lot of time refining the project scope. I attended several core team meetings and provided a lot of guidance and advice on the DB process as well as NEPA compliance. The RFQ has been developed and the RFP is being finalized. I reviewed these document and provided input and guidance. FY2022 - |  | 2021-09-27 15:26 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5P3337 | 0543193 | Missouri River Bridge in Jefferson Cit | Bridge rehabilitation over Missouri River. Project involves bridges A4497 and L0550. | Cole, Callaway |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Complexity;#Schedule;#National/Regional Significance;#Local Considerations | [9 empty] | 2021-09-28 20:20 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3269 | S401083 | J5S3269 | Pave Resurfacing from Bus 44 to Rt J, Includes Pave Inprove on Rt H from Rt 17 to End of State Maintenance | Pulaski |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3296 | 0171015 | J9P3296 - Program Development | Pavement Improvements from Route 106 in Summersville to Route 160 Near West Plains, 34.064 miles | TEXAS |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 3219702 | 3219702 | 3219702 | Design to Replace Old Dilapidated Sidewalks Along Main from 15th to 11 St | Jasper |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Other;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#TSandO Approval;#Design Exception Approval;#Differing Eligibilities Review | [6 empty] | VE Study scheduled / OINCC submittal / Major Project | 2021-09-29 17:00 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2090 | 2705360 | J6I2090 | Bridge replacement, bridge rehabilitation and pavement repair over Conway Road and New Ballas Road and bridge rehabilitation for I-270 mainline and ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052, A4654, A4657, A4580 and A4581. | St. Louis |  | Bridge Replacement |  | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations |  | Core Team Member;#TSandO Approval;#Design Exception Approval;#Design Preliminary Plans |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:01 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2222 | 0641061 | J6I2222 I-64 at 22nd and Jefferson | Modify interchange configuration between 18th Street and Garrison Avenue. Project involves bridges A1523, A1501, A1528, A0840, and A0838. $7,900,000 Cost Share and $7,900,000 Land Clearance for Redevelopment Authority funds. | St. Louis City | 2020-05-15 | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Schedule;#Cost;#Urgency;#Environmental & Stakeholders;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 7 change orders with no comments. Reviewed and approved 2 VECP with no comments. The VECPs were previously discussed in the PAVE that was held after award and before NTP. LP-Project has 3 trainee spots of 1000 hours each. Prime says they will not use trainees until summer 2021. Project is scheduled to be completed 6/2022. CUF still needed for D&K Welding. FY 2022 |  | 2021-09-29 17:02 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 Rte N EA | Scoping for environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | New Construction | Peters, Taylor (FHWA);#43 | No | FALSE | FY21 | Environmental & Stakeholders |  | EA/EIS Public Involvement | EA/EIS Public Involvement | [6 empty] | 2021-09-29 07:32 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 & J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Local Considerations |  | Core Team Member | Core Team Member |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:13 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  | Bridge 90% Review;#Design Exception Approval;#Design 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design 90% Review;#Design Exception Approval;#Bridge 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2021-09-28 10:36 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [5 empty] | FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination. FY 2022 |  | 2021-09-29 06:44 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments | [6 empty] | Part of I-270 North Major project / EA reval | 2021-09-29 07:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3233 | not assigned | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371) | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371). Excludes bridge along Missouri River in St. Joseph. | Andrew | 2020-06-19 | Resurfacing | Irving, Kevin (FHWA);#29 | Yes | FALSE | FY21 | Complexity;#Schedule;#Local Considerations | Contract Administration. Pavement and materials quality. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. |  |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. | Due to Covid-19 travel restrictions, construction inspections could not be performed on this project. There were no project actions on this project during FY 21. The project has been completed and therefore will not be carried over as a PoDI in FY 22. |  | 2021-09-21 18:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3201 | 4952604 | J6I3201 LPA David Hoekel Parkway I-70 Interchange Phase 1 and Phase 2 | Payment to Wentzville for adding interchange west of Point Prairie Road. $5,000,000 Cost Share funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Environmental and Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 8 change orders with no issues. No VECP's have been submitted and none are expected. LP- A CUF review is need for Columbia Curb and Gutter. Project has an OJT Goal of 1 trainee for 1000 hours. Contractor says they are looking for a trainee to use summer 2021. Project closing is delayed until 11/2021. FY 2022 |  | 2021-09-29 06:50 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval;#Core Team Member;#Design Preliminary Plans;#ATC;#FMIS Authorization;#CMAQ Project Review;#Design 90% Review | AJR Approval;#Design Build Certification;#FMIS Authorization;#CMAQ Project Review;#Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America;#Pavement/Materials Review;#Quality Control;#Bridge Inspection;#Title VI |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed. FY 2022 |  | 2021-09-29 15:59 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 & J6I3500 | 2553052 &255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Cost;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review | Core Team Member;#Design Preliminary Plans;#Design PSandE Review;#Other |  | Construction Inspections;#Work Zone/TMP;#Bridge Inspection |  |  |  | VE Study | 2021-09-29 06:57 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:30 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3167 | 0073024 | Rte. 7 and South Ave. Signalization Improvements | Add a signalized intersection at Rte. 7 intersection sidewalk connections (Blue Springs) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | This project was originally programmed as an LPA project sponsored by the City of Blue Springs with the TIP #625033. It was later combined with a MoDOT sponsored project under the TIP #690490 and MoDOT Job Number 4S3167. FMIS action completed 5/14/21. The integration of the LPA CMAQ project into the MoDOT project was correctly programmed and the FMIS action aligned with the programming actions. . |  | 2021-09-28 19:38 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P2321 J6P2321B | 0471072 0471080 | FY 2014 TIGER VI J6P2321 & J6P2321B: MO-47 - Bridge over Missouri River | FY 2014 TIGER ​Replace bridge over the Missouri River from Rte. 94 to Fifth Street in Washington. Cost share: $500,000 city of Washington, $250,000 Franklin County and $50,000 Warren County. | Franklin | 2016-05-20 | Bridge Replacement | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#PY20;#PY19;#PY18;#PY17;#PY16;#FY22 | Funding;#Other |  |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY2021 The project is substantially complete with aethetic lighting still be completed. Due to COVID restrictions, the subcontractor has not been able to travel. All TIGER funds have been expended. Project is submitting all quarterly reports and performance measure reports on time as required. FY2022 |  | 2021-09-29 06:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 7302674 | 7302674 | CMAQ - 7302(674) Intersection Improvements | CMAQ - 7302(674) Intersection Improvements - Intersection Improvement, Traffic Signals, Roadway Realignment | St. Charles |  | Reconstruction | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  |  | Design 90% Review | PE work has been completed. ROW authorization in FMIS on 8/14/20 |  |  |  | The project description in the FMIS action and EWG TIP are aligned. A FMIS action on 7/9/21 extended the construction award date by 12 months (July 2022). The EWG FY2022-2025 TIP update to be approved by the EWG in October 2021 reflects the new construction award program year of 2022. |  | 2021-09-28 19:34 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member | Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Title VI |  |  |  |  | 2021-09-29 15:53 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:15 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 | Environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-28 20:23 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build AAS Concur;#Design Build Certification | Design Build Certification |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:28 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0601 | 711063 | 7P0601 - Rte. I-49 Missouri Arkansas Connector | Bella Vista Bypass Connection for New I-49 | McDonald | 2021-09-30 | New Construction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Program Involvement Findings | Construction of new interstate section using BUILD funding | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization |  | Environmental Commitments;#Special Funding;#Change Order Approval;#VECP Approval;#Interstate Designation Request;#Title VI | Change Order Approval;#VECP Approval;#Environmental Commitments;#Special Funding |  | FY2021 Project is under construction. I have reviewed and approved 3 VECPs and 10 change orders since October 1. Additional change orders and VECPs were approved last PY.I prepared the final inspection report to document interstate standards. I have assited with preparing the request for acceptance into the Interstate system. FY2022 |  | 2021-09-29 15:31 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations | Bridge replacement using ATC | ATC | ATC |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:47 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I0445 | 0442293 | Rte. I-44, Webster Co. New Interchange in Marshfield - LPA Administered |  | Webster | 2021-07-27 |  | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | Yes | TRUE | FY21 | Program Involvement Findings |  |  |  |  | Title VI |  |  | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-29 15:35 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 |  | J9P3122 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [7 empty] | 2021-09-23 13:19 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 | Chester Bridge | Perry | 2022-06-22 | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Scoping;#Conceptual Report Review;#Design Build Procurement;#Design Build Certification;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#FMIS Authorization;#Conditional Clearance | [7 empty] | 2021-09-24 09:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 |  | J9P3305 | Scoping for bridge improvements over Current River and Round Spring. | SHANNON |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#Bridge TSandL;#Environmental Commitments | Core Team Member;#Conceptual Report Review;#Bridge TSandL | [6 empty] | 2021-09-23 13:20 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3584 | 0604090 | J9P3584 | Future I-57 and US60; Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds | NEW MADRID |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Scoping;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:36 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | BUTLER |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | BUTLER |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 | AJR Approval;#Design Preliminary Plans;#Conceptual Report Review | Conceptual Report Review;#Design Preliminary Plans;#AJR Approval |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Buy America;#Civil Rights/Cert Payroll |  |  | Provided recommnedation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 |  | J9P3751 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval | [6 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3764 |  | J9P3764 | Future I-57 Phase 1B Add lanes and outer roads to upgrade corridor to freeway standards from County RoadB 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Urgency;#Funding;#Environmental and Stakeholders;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:27 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | LPA City of O'Fallon I-70 at Bryan Road |  | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [6 empty] | no funds yet | 2021-09-29 07:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3232 J9S3232B | S701051/S703077 | J9S3232 & J9S3232B | Bootheel Bridge Bundle Design-Build | VARIOUS |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Environmental and Stakeholders;#Corporate Actions;#Local Considerations | Bundle Bridge project in rural area | Design Build Certification;#Design Build Procurement;#Design Build AAS Concur;#Design Exception Approval | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval |  | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America |  |  | Provided guidance on the Design-Build process. |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 & JP3496B | S502067 S502089 | J6P3496 & JP3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member | [7 empty] | 2021-09-29 07:29 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 |  | J9S3381 | Bridge replacement over Black River. Project involves bridge K0263. | Butler |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Schedule;#Environmental and Stakeholders;#Local Considerations | [9 empty] | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5640613 | 5640613 City of St. Peters | City of St. Peters Jungermann Road Bridge over branch of Spencer Creek, replace culverts (23077 & 23079) - 6563-15 | St. Charles County |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Schedule;#Project Administration;#Local Considerations | LPA project, utility related time extension and problematic contractor |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY 2021 Reviewed 3 change orders. Multiple discussions held on time extensions, LDs, and possible claim along with the format and eligibility of the change orders. 2 of the change orders were approved. The LPA has needed a lot of direction since this project had huge impacts to schedule and budget due to utilities. LP- CUF has been conduted for XL Contracting. No OJT hours on project. FY 2022 |  | 2021-09-25 09:41 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#PY20;#FY20;#FY22 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2021-09-25 10:16 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526 | 0552121 | J6I3526 | Scoping for corridor improvements along the I-55 corridor from 0.5 mile north of Rte. Z to 1 mile south of Rte. 67. Potential Design-Build project. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | 696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:14 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | n/a | 5417604 5417605 | 5417604 & 5417605 LPA City of St. Louis Jefferson/22nd Improvements | LPA City of St. Louis Jefferson/22nd Improvements | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Project Administration;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Design Exception Approval;#Design Preliminary Plans;#Design 90% Review |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Buy America;#Civil Rights/Cert Payroll;#Title VI |  |  | FY 2021 90% final plan package reviewed and multiple comments submitted including Buy America, proprietary items, traffic control, etc. No Design Exceptions have been submitted and none are expected. Most of the comments from the preliminary plan review were addressed. Project was giving conditional PS&E approval and FMIS authorization/obligation with a long list of conditions. MoDOT is monitoring the conditions. FY 2022 |  | 2021-09-29 16:02 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NA | NA | Pedestrian and Bikeways Improvements | Connect existing bikeways on 11th street and 12th street (Kansas City) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | TRUE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | No FMIS ACTION to-date. KC District staff indicate that this project will be authorized and funds obligated in the early Spring (2022). |  | 2021-09-27 13:25 | McMahon, Bradley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3359 | 0444204 | J6I3359 | Scoping for pedestrian studies at Selma Avenue Overpass and I-55 at Daycare Overpass. Project involves pedestrian bridges A1729 and A0619. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#Environmental Commitments | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | Project Authorization and Project Agreements;#Project Planning & Programming;#Project Financing;#Special Funding;#FMIS Authorization |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added: Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted. MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. Reviewed the consultant solicitation document issued by MoDOT. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J6P3510 | not assigned | J6P3510 | Scoping for ADA Transition Plan improvements at various locations in the St. Louis District. Potential DesignBuild project. | Various |  | ADA/Sidewalk | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | Not assigned | N/A | I-29 near Ambassador Drive, Permit Project | Potential Permit Project near KCI Airport at I-29 and Route D interchange near Ambassador Drive. | Platte |  | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE |  | Local Considerations;#Other | Proposed Dogbone Roundabout interchange at I-29 and Rt. D with connection to a development property. | TSandO Approval |  | Meetings and Review and approval of a TS&O report. | [5 empty] | 2021-09-23 14:59 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 | Scoping for interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#AJR Approval;#Design Exception Approval | [6 empty] | System to System Interchange / EIS reval | 2021-09-29 07:33 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
|  |  | J2P3347 | [5 empty] | No | TRUE | [11 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3661 | not assigned | J6P3661 | Scoping for corridor improvements from Rte. 100 to I-44. Project involves various bridges | Franklin |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | Scoping for capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## NW
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | Still a PODI | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | 2700509 | 2700509 | 2700509 - City of Fulton AID Demonstration | Bridge Replacement on 2nd ST Bridge over Stinson Creek and Stinson Creek Greenway, Bridge No. 1555011 located on State Route O in the City of Fulton. Accelerated Innovation Deployment (AID Demonstration program) | Callaway |  | Bridge Replacement | Pursley, Charles (FHWA);#37;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Discretionary Grant and Financing;#Project Administration;#Program Involvement Findings |  | Design Preliminary Plans;#Design 90% Review;#Special Funding;#Differing Eligibilities Review |  |  | Work Zone/TMP;#Bridge Inspection |  |  |  |  | 2021-09-29 08:05 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Design Build Procurement;#AJR Approval;#Bridge 90% Review;#Interstate Designation Request |  | AJR (if required), Bridge and Roadway 90% plans, Interstate De-designation, Funding review, T&E review, NEPA EA review/approval, Design-Build procurement |  |  |  | FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. |  | 2021-09-20 17:44 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5617602 5617603 | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  | Design Preliminary Plans;#Design 90% Review;#Design PSandE Approval | Design Preliminary Plans;#Design 90% Review |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted. FY 2022 |  | 2021-09-29 06:56 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5901816 | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  | Design Build Procurement;#Environmental Commitments;#Design Preliminary Plans;#Design Build Certification | Design Build Procurement;#Design Build Certification |  | Environmental Commitments;#Special Funding;#Construction Inspections;#Title VI |  |  | The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. It is nearing completion and should be ready for execution soon. |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5903803 | 5903803 | 5903803 - Jefferson Avenue Foot Bridge Over BNSF Railroad in Springfield | Rehabilitate the Jefferson Avenue foot bridge and provide ADA access | Greene | 2021-11-01 | Bridge Rehabilitation | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Project Administration;#Program Involvement Findings |  | Design PSandE Review | Design PSandE Review |  | Construction Inspections;#Buy America;#Title VI |  |  |  |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3109 | N/A | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. Project involves twin bridges A1293 in the NB and SB lanes. | Andrew |  | Bridge Replacement | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Schedule;#Project Administration;#Local Considerations;#Program Involvement Findings | Complexity: Likely to include head to head traffic on Interstate. Schedule: Scheduled bridge work has risk of delayed completion. Local considerations: Work Zone complexity will significantly impact traffic. |  |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Title VI |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Due to Covid-19 travel restrictions, no construction inspections were performed on this project. No PoDI activity occurred during PY21. The project is nearly completed so this project will not be retained as a PoDI in FY 22. |  | 2021-09-29 15:32 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3029 | 0444188 | J6I3029 I-44 at I-270 and Meramec River Bridge |  | St. Louis |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | FALSE | FY21;#FY20;#PY19 | [8 empty] | FY 2021 Reviewed and approved 5 change orders with no issues. LP-CUF Reviews still need to be performed for DW Mertzke,Petro legistics, and Prestige truking. Project ending 2/2022. |  | 2021-09-24 10:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3110 | 0292195 | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Atchison | 2020-03-20 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental & Stakeholders;#Funding | Construction inspection to include focused review checklists and a bridge inspection. |  |  | Construction inspection to include focused review checklists and a bridge inspection.. | Construction Inspections;#Work Zone/TMP;#Buy America;#Erosion Control;#Bridge Inspection |  | Construction inspection to include focused review checklists and a bridge inspection. | FY 21: The project has been awarded and construction started in the Spring of 2021. No PoDI activity was performed due to the COVID pandemic travel restrictions. The project has been retained as a construction PoDI for FY 22. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1P3378 | not assigned | Rt. 136 Flood Resiliency Permanent Repair | Flood Resiliency Permanent Repair from Mo. River to I-29 near Rock Port. Atchison County | Atchison | 2022-04-15 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Local Considerations;#Funding | ER funded flood resiliency project. | Core Team Member;#Design 90% Review |  | Review of 90% Plans and compare to approved DDIR. |  |  |  | FY21: Reviewed resiliency proposal and DDIR and had multiple meetings to discuss the benefit/cost analysis expectations. Approved DDIR and resiliency proposal. |  | 2021-09-23 14:46 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-02-25 | Pavement and Bridge | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. | Final Design;#Plan, Specification, & Estimate Development;#Advertising & Award;#Core Team Member;#Special Funding | Design Preliminary Plans;#Conceptual Report Review;#Environmental Commitments | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting. | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Environmental Commitments;#Buy America |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  | Design PSandE Review;#Design PSandE Approval;#Environmental Commitments;#Core Team Member;#Design Preliminary Plans;#Other |  | Construction Inspections;#Erosion Control;#Civil Rights/Cert Payroll;#Work Zone/TMP;#Buy America |  | Construction inspections with focused review checklists. | FY 20 and FY 21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ. Submitted all monthly BUILD reports as required. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | Not Assigned | J2I3274 | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | MONTGOMERY |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3309 | 0703276 | J2I3309 | Pavement improvements from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | MONTGOMERY |  | Pavement Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3310 | 0703286 | J2I3310 | Pavement resurfacing from the Callaway County line to 2 miles east of Rte. F near High Hill. | MONTGOMERY |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | Conceptual Report Review |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review;#Civil Rights/Cert Payroll |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 | Scoping for interchange improvements at Stracks Church County Road near Wright City. | WARREN |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3043 | 0471083 | J2P3043 | Interchange improvements at Rte. 61 in Troy. Project involves bridge A2604. | LINCOLN |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2S3221 J2P3222 J2P3 | S201034 / 13620 | J2S3221 / J2P3222 / J2P3224 |  | SCHUYLER |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-29 07:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | MONTGOMERY |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#AJR Approval |  | Title VI |  |  |  |  | 2021-09-29 15:37 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3226 J2I3226B | 0703279 | Rte. I-70, Mineola Hill Truck Climbing Lanes |  | Montgomery | 2021-07-01 | Reconstruction | Pursley, Charles (FHWA);#37 | Yes | FALSE | FY21 | [8 empty] | Project is under construction. I have attended a weekly project status update meeting to track the project progress through construction. Weekly meetings have not been held since December 2020. I have not approved any change orders or VECPs since October 1. Those activities were complete last PY. The final quarterly project QC/QMmeeting was held on June 23, 2021. I atended as well as the Paement and Materiasl Specialist. |  | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3156 | 0544065 | J2P3156 | Add roundabout at Rte. 19 north junction (Basinger Corner) north of Laddonia. $2,346,000 Open Container funds. | Audrain |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Urgency;#Environmental and Stakeholders |  |  |  |  | Construction Inspections |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3259 | 0614179 | J2P3259 | Pavement resurfacing on northbound lanes from Rte. V to 0.4 mile south of Rte. UU in Pike County near Bowling Green. | Lincoln |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity |  |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll;#Pavement/Materials Review |  |  |  |  | 2021-09-23 14:25 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3357 | 0791082 | J2P3357 | Bridge replacement over Lyon Street, Warren Barrett Drive, Burlington Northern Santa Fe Railroad and Bear Creek 0.4 mile north of Rte. T in Hannibal. | MARION |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Program Involvement Findings |  | Core Team Member;#Design Preliminary Plans;#Differing Eligibilities Review |  |  | Title VI |  |  |  |  | 2021-09-29 15:34 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3447 | Not Assigned | J2P3447 | Scoping for roadway improvement between Bus. 54 and Rte. 79 in Louisiana. | Audrain |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member | [7 empty] | 2021-09-23 14:12 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900391 | 9900391 | TAP 9900 (391) LPA: NE District - CONSTRUCTION |  | TROY |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval |  | The previously approved AJR will be reevaluated and updated. Title VI review. | [5 empty] | 2021-09-29 15:56 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I2006 | 0351291 | Add interchange south of Rte. 92 at 19th Street in Kearney. | New Interchange on I-35 at Kearney | Clay | 2022-02-25 | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Local Considerations;#National/Regional Significance;#Program Involvement Findings | New interchange construction with a Diverging Diamond interchange configuration and new bridge. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | Work Zone/TMP;#Title VI |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | The project has been delayed due to ROW acquisition delays, therefore no construction activities have been performed. The project is expected to be let in early 2022. Significant utility relocation is required before construction begins so the main construction will likely occur in FY23. Will consider including as a PoDI during FY23. |  | 2021-09-29 15:29 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | N/A | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY21 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification could require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#Design 90% Review;#AJR Approval;#Design Exception Approval;#Differing Eligibilities Review |  | Core team member. NEPA review and approval. AJR or Traffic Safety and Operational Analysis will likely be required. 90% Plans review and design exception approval. |  |  |  | FHWA has participated in 3 core team meetings and have offered feedback on the level of documentation and analysis needed for multiple interchange configurations. A separate meeting with the HQ Major project specialist was held to confirm that this project was not considered a Major Project as defined by FHWA and will not need a FP nor Major Project Plan. This information was shared with MoDOT. |  | 2021-09-29 08:11 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3189 | 4351323 | I-435 Bridge over the Missouri River in Kansas City, MO | Bridge deck replacement at the Missouri River. Project involves twin bridges A0767. | Clay | 2019-05-17 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Other;#Urgency;#Complexity;#Local Considerations;#Program Involvement Findings | Schedule: Work zone impacts will be significant and will require expedited construction. Local Consideration: Work zone impacts will be regionally significant. |  |  | Construction inspection to include focused checklist for Work Zone Traffic Control. | Work Zone/TMP;#Title VI |  | Construction inspections to include a focused checklist for Work Zone Traffic Control. | FY 21: Due to Covid-19 travel restrictions, no construction inspections were performed on this project. There has been no PoDI involvement this performance year. The project is scheduled to be completed at the end of 2021 and it will be retained as a PoDI project to include a work zone traffic control review. |  | 2021-09-29 16:08 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4P2237 | S300097 | J4P2237- I-49 Outer Roads Conversion to from One-way to Two-way | Conversion of the outer roads of I-49 to two-way traffic on the east outer road from Rt. 150 to Blue Ridge Boulevard and on the west outer road from Blue Ridge Boulevard to 0.5 miles north of Rt. 150 in Grandview. | Jackson | 2023-09-30 |  | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Project Administration;#Local Considerations;#Program Involvement Findings | Large complex local project using the Design-Build delivery method with limited experience by City staff. ROW and Utility impacts that could impace schedule. Complex traffic control during construction with significant traffic impacts on the local and interstate highways. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Contract Administration;#Other | Environmental Commitments;#AJR Approval;#Design Build AAS Concur;#Design Build Certification;#Design Build Procurement;#FMIS Authorization |  | Title VI;#Work Zone/TMP |  | Construction inspections. Focused Reviews on Title VI and Work Zone Traffic Control. FHWA will continue to provide feedback on proposed revisions to the approved AJR and will coordinate with MoDOT and the City on these changes and any required approval. | Reviewed all books of Draft RFP and provided comments on Books 1 and 2, and ITP. • During the confidential one-one-one meetings, I coordinated review of potential AJR deviations with Division staff and leadership. Reviewed proposed TS&O reports and offered feedback and concerns to MoDOT on all three teams’ draft submittals. • Worked with Mike Landvik and Jim Stevenson to develop a draft LPA Design-Build checklist template for use on future LPA Design-Build projects. • Provided recommendations on how to structure the RFP documents when these were in the early stages of development. Assured that federal requirements were conveyed and followed. • Coordinated involvement on an ADA concern from both Civil Rights and Environmental staff members from MoDOT and FHWA to assure that the decision by the City to modify the sidewalk requirements in the RFP did not violate NEPA and/or ADA requirements. • Reviewed and approved the final RFP for release and facilitated the FMIS construction authorization. This took quite a bit of time since the process for approval was different than traditional D-B-B project authorizations. I provided guidance on the RFP certification letter and what needed to be included in the submittal. MoDOT and the City were very appreciative of this guidance and involvement. • Reviewed the proposals and participated in the proposal evaluation process and offered feedback on how FHWA could concur in the project award. Concurred in project award. Reviewed proposed AJR changes and offered valuable feedback. Coordinated a meeting to convey FHWA expectations on the criteria for acceptance of a proposed AJR revision involving a proposed roundabout in lieu of the approved configuration.s expectation |  | 2021-09-29 15:57 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900086 | 9900086 | TAP 9900(086) LPA: NE District - CONSTRUCTION |  | CITY OF EAST PRAIRIE |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#PY20;#PY19 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. | Innovative Contracting/Design Build;#Contract Administration;#Construction Inspection & Quality;#Other;#Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance;#Scoping;#Special Funding;#Bridge TSandL |  | Change Order Approval;#Work Zone/TMP;#Civil Rights/Cert Payroll;#Erosion Control;#DBE Goals;#Buy America;#Title VI |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21: Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21. Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. Reviewed and provided comments to revised project AJR and issued approval. Submitted all required monthly project reports through September, 2021. Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan in coordination with the Division Office Pavement and Materials Engineer. |  | 2021-09-29 15:58 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  | Project Authorization and Project Agreements;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. |  | 2021-09-27 15:19 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397,J5I3572, | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. | Design PSandE Review |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:22 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | B015001 | B015001 | Camden Co. Bridge Replacement on Willow Creek Road |  | Camden |  |  | Pursley, Charles (FHWA);#37 | No | FALSE | FY21 | [8 empty] | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3369 | S402035 | 5S3369 - Central District ADA Improvements - Alternate Project Delivery Method | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address Route: Various nonstandard ADA facilities at various locations in the Central and Northwest Districts. | Various | 2021-11-01 | ADA/Sidewalk | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#Design Build AAS Concur | Design Build Procurement;#Design Build Certification |  | Construction Inspections;#Work Zone/TMP;#ADA |  |  | FY2021-The DB team spent a lot of time refining the project scope. I attended several core team meetings and provided a lot of guidance and advice on the DB process as well as NEPA compliance. The RFQ has been developed and the RFP is being finalized. I reviewed these document and provided input and guidance. FY2022 - |  | 2021-09-27 15:26 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5P3337 | 0543193 | Missouri River Bridge in Jefferson Cit | Bridge rehabilitation over Missouri River. Project involves bridges A4497 and L0550. | Cole, Callaway |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Complexity;#Schedule;#National/Regional Significance;#Local Considerations | [9 empty] | 2021-09-28 20:20 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3269 | S401083 | J5S3269 | Pave Resurfacing from Bus 44 to Rt J, Includes Pave Inprove on Rt H from Rt 17 to End of State Maintenance | Pulaski |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3296 | 0171015 | J9P3296 - Program Development | Pavement Improvements from Route 106 in Summersville to Route 160 Near West Plains, 34.064 miles | TEXAS |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 3219702 | 3219702 | 3219702 | Design to Replace Old Dilapidated Sidewalks Along Main from 15th to 11 St | Jasper |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Other;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#TSandO Approval;#Design Exception Approval;#Differing Eligibilities Review | [6 empty] | VE Study scheduled / OINCC submittal / Major Project | 2021-09-29 17:00 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2090 | 2705360 | J6I2090 | Bridge replacement, bridge rehabilitation and pavement repair over Conway Road and New Ballas Road and bridge rehabilitation for I-270 mainline and ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052, A4654, A4657, A4580 and A4581. | St. Louis |  | Bridge Replacement |  | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations |  | Core Team Member;#TSandO Approval;#Design Exception Approval;#Design Preliminary Plans |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:01 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2222 | 0641061 | J6I2222 I-64 at 22nd and Jefferson | Modify interchange configuration between 18th Street and Garrison Avenue. Project involves bridges A1523, A1501, A1528, A0840, and A0838. $7,900,000 Cost Share and $7,900,000 Land Clearance for Redevelopment Authority funds. | St. Louis City | 2020-05-15 | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Schedule;#Cost;#Urgency;#Environmental & Stakeholders;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 7 change orders with no comments. Reviewed and approved 2 VECP with no comments. The VECPs were previously discussed in the PAVE that was held after award and before NTP. LP-Project has 3 trainee spots of 1000 hours each. Prime says they will not use trainees until summer 2021. Project is scheduled to be completed 6/2022. CUF still needed for D&K Welding. FY 2022 |  | 2021-09-29 17:02 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 Rte N EA | Scoping for environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | New Construction | Peters, Taylor (FHWA);#43 | No | FALSE | FY21 | Environmental & Stakeholders |  | EA/EIS Public Involvement | EA/EIS Public Involvement | [6 empty] | 2021-09-29 07:32 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 & J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Local Considerations |  | Core Team Member | Core Team Member |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:13 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  | Bridge 90% Review;#Design Exception Approval;#Design 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design 90% Review;#Design Exception Approval;#Bridge 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2021-09-28 10:36 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [5 empty] | FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination. FY 2022 |  | 2021-09-29 06:44 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments | [6 empty] | Part of I-270 North Major project / EA reval | 2021-09-29 07:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3233 | not assigned | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371) | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371). Excludes bridge along Missouri River in St. Joseph. | Andrew | 2020-06-19 | Resurfacing | Irving, Kevin (FHWA);#29 | Yes | FALSE | FY21 | Complexity;#Schedule;#Local Considerations | Contract Administration. Pavement and materials quality. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. |  |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. | Due to Covid-19 travel restrictions, construction inspections could not be performed on this project. There were no project actions on this project during FY 21. The project has been completed and therefore will not be carried over as a PoDI in FY 22. |  | 2021-09-21 18:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3201 | 4952604 | J6I3201 LPA David Hoekel Parkway I-70 Interchange Phase 1 and Phase 2 | Payment to Wentzville for adding interchange west of Point Prairie Road. $5,000,000 Cost Share funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Environmental and Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 8 change orders with no issues. No VECP's have been submitted and none are expected. LP- A CUF review is need for Columbia Curb and Gutter. Project has an OJT Goal of 1 trainee for 1000 hours. Contractor says they are looking for a trainee to use summer 2021. Project closing is delayed until 11/2021. FY 2022 |  | 2021-09-29 06:50 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval;#Core Team Member;#Design Preliminary Plans;#ATC;#FMIS Authorization;#CMAQ Project Review;#Design 90% Review | AJR Approval;#Design Build Certification;#FMIS Authorization;#CMAQ Project Review;#Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America;#Pavement/Materials Review;#Quality Control;#Bridge Inspection;#Title VI |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed. FY 2022 |  | 2021-09-29 15:59 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 & J6I3500 | 2553052 &255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Cost;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review | Core Team Member;#Design Preliminary Plans;#Design PSandE Review;#Other |  | Construction Inspections;#Work Zone/TMP;#Bridge Inspection |  |  |  | VE Study | 2021-09-29 06:57 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:30 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3167 | 0073024 | Rte. 7 and South Ave. Signalization Improvements | Add a signalized intersection at Rte. 7 intersection sidewalk connections (Blue Springs) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | This project was originally programmed as an LPA project sponsored by the City of Blue Springs with the TIP #625033. It was later combined with a MoDOT sponsored project under the TIP #690490 and MoDOT Job Number 4S3167. FMIS action completed 5/14/21. The integration of the LPA CMAQ project into the MoDOT project was correctly programmed and the FMIS action aligned with the programming actions. . |  | 2021-09-28 19:38 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P2321 J6P2321B | 0471072 0471080 | FY 2014 TIGER VI J6P2321 & J6P2321B: MO-47 - Bridge over Missouri River | FY 2014 TIGER ​Replace bridge over the Missouri River from Rte. 94 to Fifth Street in Washington. Cost share: $500,000 city of Washington, $250,000 Franklin County and $50,000 Warren County. | Franklin | 2016-05-20 | Bridge Replacement | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#PY20;#PY19;#PY18;#PY17;#PY16;#FY22 | Funding;#Other |  |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY2021 The project is substantially complete with aethetic lighting still be completed. Due to COVID restrictions, the subcontractor has not been able to travel. All TIGER funds have been expended. Project is submitting all quarterly reports and performance measure reports on time as required. FY2022 |  | 2021-09-29 06:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 7302674 | 7302674 | CMAQ - 7302(674) Intersection Improvements | CMAQ - 7302(674) Intersection Improvements - Intersection Improvement, Traffic Signals, Roadway Realignment | St. Charles |  | Reconstruction | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  |  | Design 90% Review | PE work has been completed. ROW authorization in FMIS on 8/14/20 |  |  |  | The project description in the FMIS action and EWG TIP are aligned. A FMIS action on 7/9/21 extended the construction award date by 12 months (July 2022). The EWG FY2022-2025 TIP update to be approved by the EWG in October 2021 reflects the new construction award program year of 2022. |  | 2021-09-28 19:34 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member | Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Title VI |  |  |  |  | 2021-09-29 15:53 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:15 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 | Environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-28 20:23 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build AAS Concur;#Design Build Certification | Design Build Certification |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:28 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0601 | 711063 | 7P0601 - Rte. I-49 Missouri Arkansas Connector | Bella Vista Bypass Connection for New I-49 | McDonald | 2021-09-30 | New Construction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Program Involvement Findings | Construction of new interstate section using BUILD funding | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization |  | Environmental Commitments;#Special Funding;#Change Order Approval;#VECP Approval;#Interstate Designation Request;#Title VI | Change Order Approval;#VECP Approval;#Environmental Commitments;#Special Funding |  | FY2021 Project is under construction. I have reviewed and approved 3 VECPs and 10 change orders since October 1. Additional change orders and VECPs were approved last PY.I prepared the final inspection report to document interstate standards. I have assited with preparing the request for acceptance into the Interstate system. FY2022 |  | 2021-09-29 15:31 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations | Bridge replacement using ATC | ATC | ATC |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:47 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I0445 | 0442293 | Rte. I-44, Webster Co. New Interchange in Marshfield - LPA Administered |  | Webster | 2021-07-27 |  | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | Yes | TRUE | FY21 | Program Involvement Findings |  |  |  |  | Title VI |  |  | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-29 15:35 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 |  | J9P3122 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [7 empty] | 2021-09-23 13:19 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 | Chester Bridge | Perry | 2022-06-22 | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Scoping;#Conceptual Report Review;#Design Build Procurement;#Design Build Certification;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#FMIS Authorization;#Conditional Clearance | [7 empty] | 2021-09-24 09:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 |  | J9P3305 | Scoping for bridge improvements over Current River and Round Spring. | SHANNON |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#Bridge TSandL;#Environmental Commitments | Core Team Member;#Conceptual Report Review;#Bridge TSandL | [6 empty] | 2021-09-23 13:20 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3584 | 0604090 | J9P3584 | Future I-57 and US60; Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds | NEW MADRID |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Scoping;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:36 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | BUTLER |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | BUTLER |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 | AJR Approval;#Design Preliminary Plans;#Conceptual Report Review | Conceptual Report Review;#Design Preliminary Plans;#AJR Approval |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Buy America;#Civil Rights/Cert Payroll |  |  | Provided recommnedation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 |  | J9P3751 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval | [6 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3764 |  | J9P3764 | Future I-57 Phase 1B Add lanes and outer roads to upgrade corridor to freeway standards from County RoadB 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Urgency;#Funding;#Environmental and Stakeholders;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:27 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | LPA City of O'Fallon I-70 at Bryan Road |  | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [6 empty] | no funds yet | 2021-09-29 07:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3232 J9S3232B | S701051/S703077 | J9S3232 & J9S3232B | Bootheel Bridge Bundle Design-Build | VARIOUS |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Environmental and Stakeholders;#Corporate Actions;#Local Considerations | Bundle Bridge project in rural area | Design Build Certification;#Design Build Procurement;#Design Build AAS Concur;#Design Exception Approval | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval |  | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America |  |  | Provided guidance on the Design-Build process. |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 & JP3496B | S502067 S502089 | J6P3496 & JP3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member | [7 empty] | 2021-09-29 07:29 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 |  | J9S3381 | Bridge replacement over Black River. Project involves bridge K0263. | Butler |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Schedule;#Environmental and Stakeholders;#Local Considerations | [9 empty] | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5640613 | 5640613 City of St. Peters | City of St. Peters Jungermann Road Bridge over branch of Spencer Creek, replace culverts (23077 & 23079) - 6563-15 | St. Charles County |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Schedule;#Project Administration;#Local Considerations | LPA project, utility related time extension and problematic contractor |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY 2021 Reviewed 3 change orders. Multiple discussions held on time extensions, LDs, and possible claim along with the format and eligibility of the change orders. 2 of the change orders were approved. The LPA has needed a lot of direction since this project had huge impacts to schedule and budget due to utilities. LP- CUF has been conduted for XL Contracting. No OJT hours on project. FY 2022 |  | 2021-09-25 09:41 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#PY20;#FY20;#FY22 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2021-09-25 10:16 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526 | 0552121 | J6I3526 | Scoping for corridor improvements along the I-55 corridor from 0.5 mile north of Rte. Z to 1 mile south of Rte. 67. Potential Design-Build project. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | 696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:14 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | n/a | 5417604 5417605 | 5417604 & 5417605 LPA City of St. Louis Jefferson/22nd Improvements | LPA City of St. Louis Jefferson/22nd Improvements | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Project Administration;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Design Exception Approval;#Design Preliminary Plans;#Design 90% Review |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Buy America;#Civil Rights/Cert Payroll;#Title VI |  |  | FY 2021 90% final plan package reviewed and multiple comments submitted including Buy America, proprietary items, traffic control, etc. No Design Exceptions have been submitted and none are expected. Most of the comments from the preliminary plan review were addressed. Project was giving conditional PS&E approval and FMIS authorization/obligation with a long list of conditions. MoDOT is monitoring the conditions. FY 2022 |  | 2021-09-29 16:02 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NA | NA | Pedestrian and Bikeways Improvements | Connect existing bikeways on 11th street and 12th street (Kansas City) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | TRUE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | No FMIS ACTION to-date. KC District staff indicate that this project will be authorized and funds obligated in the early Spring (2022). |  | 2021-09-27 13:25 | McMahon, Bradley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3359 | 0444204 | J6I3359 | Scoping for pedestrian studies at Selma Avenue Overpass and I-55 at Daycare Overpass. Project involves pedestrian bridges A1729 and A0619. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#Environmental Commitments | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | Project Authorization and Project Agreements;#Project Planning & Programming;#Project Financing;#Special Funding;#FMIS Authorization |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added: Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted. MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. Reviewed the consultant solicitation document issued by MoDOT. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J6P3510 | not assigned | J6P3510 | Scoping for ADA Transition Plan improvements at various locations in the St. Louis District. Potential DesignBuild project. | Various |  | ADA/Sidewalk | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | Not assigned | N/A | I-29 near Ambassador Drive, Permit Project | Potential Permit Project near KCI Airport at I-29 and Route D interchange near Ambassador Drive. | Platte |  | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE |  | Local Considerations;#Other | Proposed Dogbone Roundabout interchange at I-29 and Rt. D with connection to a development property. | TSandO Approval |  | Meetings and Review and approval of a TS&O report. | [5 empty] | 2021-09-23 14:59 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 | Scoping for interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#AJR Approval;#Design Exception Approval | [6 empty] | System to System Interchange / EIS reval | 2021-09-29 07:33 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
|  |  | J2P3347 | [5 empty] | No | TRUE | [11 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3661 | not assigned | J6P3661 | Scoping for corridor improvements from Rte. 100 to I-44. Project involves various bridges | Franklin |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | Scoping for capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## SE
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | Still a PODI | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | 2700509 | 2700509 | 2700509 - City of Fulton AID Demonstration | Bridge Replacement on 2nd ST Bridge over Stinson Creek and Stinson Creek Greenway, Bridge No. 1555011 located on State Route O in the City of Fulton. Accelerated Innovation Deployment (AID Demonstration program) | Callaway |  | Bridge Replacement | Pursley, Charles (FHWA);#37;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Discretionary Grant and Financing;#Project Administration;#Program Involvement Findings |  | Design Preliminary Plans;#Design 90% Review;#Special Funding;#Differing Eligibilities Review |  |  | Work Zone/TMP;#Bridge Inspection |  |  |  |  | 2021-09-29 08:05 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 4300112 | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  | Design PSandE Review;#Design PSandE Approval;#Environmental Commitments;#Core Team Member;#Design Preliminary Plans;#Other |  | Construction Inspections;#Erosion Control;#Civil Rights/Cert Payroll;#Work Zone/TMP;#Buy America |  | Construction inspections with focused review checklists. | FY 20 and FY 21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ. Submitted all monthly BUILD reports as required. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5617602 5617603 | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  | Design Preliminary Plans;#Design 90% Review;#Design PSandE Approval | Design Preliminary Plans;#Design 90% Review |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted. FY 2022 |  | 2021-09-29 06:56 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5901816 | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  | Design Build Procurement;#Environmental Commitments;#Design Preliminary Plans;#Design Build Certification | Design Build Procurement;#Design Build Certification |  | Environmental Commitments;#Special Funding;#Construction Inspections;#Title VI |  |  | The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. It is nearing completion and should be ready for execution soon. |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5903803 | 5903803 | 5903803 - Jefferson Avenue Foot Bridge Over BNSF Railroad in Springfield | Rehabilitate the Jefferson Avenue foot bridge and provide ADA access | Greene | 2021-11-01 | Bridge Rehabilitation | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Project Administration;#Program Involvement Findings |  | Design PSandE Review | Design PSandE Review |  | Construction Inspections;#Buy America;#Title VI |  |  |  |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Design Build Procurement;#AJR Approval;#Bridge 90% Review;#Interstate Designation Request |  | AJR (if required), Bridge and Roadway 90% plans, Interstate De-designation, Funding review, T&E review, NEPA EA review/approval, Design-Build procurement |  |  |  | FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. |  | 2021-09-20 17:44 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3029 | 0444188 | J6I3029 I-44 at I-270 and Meramec River Bridge |  | St. Louis |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | FALSE | FY21;#FY20;#PY19 | [8 empty] | FY 2021 Reviewed and approved 5 change orders with no issues. LP-CUF Reviews still need to be performed for DW Mertzke,Petro legistics, and Prestige truking. Project ending 2/2022. |  | 2021-09-24 10:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3109 | N/A | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. Project involves twin bridges A1293 in the NB and SB lanes. | Andrew |  | Bridge Replacement | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Schedule;#Project Administration;#Local Considerations;#Program Involvement Findings | Complexity: Likely to include head to head traffic on Interstate. Schedule: Scheduled bridge work has risk of delayed completion. Local considerations: Work Zone complexity will significantly impact traffic. | Contract Administration;#Construction Inspection & Quality |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Title VI |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Due to Covid-19 travel restrictions, no construction inspections were performed on this project. No PoDI activity occurred during PY21. The project is nearly completed so this project will not be retained as a PoDI in FY 22. |  | 2021-09-29 15:32 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3110 | 0292195 | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Atchison | 2020-03-20 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental & Stakeholders;#Funding | Construction inspection to include focused review checklists and a bridge inspection. |  |  | Construction inspection to include focused review checklists and a bridge inspection.. | Construction Inspections;#Work Zone/TMP;#Buy America;#Erosion Control;#Bridge Inspection |  | Construction inspection to include focused review checklists and a bridge inspection. | FY 21: The project has been awarded and construction started in the Spring of 2021. No PoDI activity was performed due to the COVID pandemic travel restrictions. The project has been retained as a construction PoDI for FY 22. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1P3378 | not assigned | Rt. 136 Flood Resiliency Permanent Repair | Flood Resiliency Permanent Repair from Mo. River to I-29 near Rock Port. Atchison County | Atchison | 2022-04-15 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Local Considerations;#Funding | ER funded flood resiliency project. | Design 90% Review |  | Review of 90% Plans and compare to approved DDIR. |  |  |  | FY21: Reviewed resiliency proposal and DDIR and had multiple meetings to discuss the benefit/cost analysis expectations. Approved DDIR and resiliency proposal. |  | 2021-09-23 14:46 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-02-25 | Pavement and Bridge | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. | Final Design;#Plan, Specification, & Estimate Development;#Advertising & Award;#Core Team Member;#Special Funding | Design Preliminary Plans;#Conceptual Report Review;#Environmental Commitments | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting. | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Environmental Commitments;#Buy America |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | Not Assigned | J2I3274 | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | MONTGOMERY |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3309 | 0703276 | J2I3309 | Pavement improvements from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | MONTGOMERY |  | Pavement Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3310 | 0703286 | J2I3310 | Pavement resurfacing from the Callaway County line to 2 miles east of Rte. F near High Hill. | MONTGOMERY |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | Conceptual Report Review |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review;#Civil Rights/Cert Payroll |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 | Scoping for interchange improvements at Stracks Church County Road near Wright City. | WARREN |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3043 | 0471083 | J2P3043 | Interchange improvements at Rte. 61 in Troy. Project involves bridge A2604. | LINCOLN |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2S3221 J2P3222 J2P3 | S201034 / 13620 | J2S3221 / J2P3222 / J2P3224 |  | SCHUYLER |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-29 07:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | MONTGOMERY |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#AJR Approval |  | Title VI |  |  |  |  | 2021-09-29 15:37 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3226 J2I3226B | 0703279 | Rte. I-70, Mineola Hill Truck Climbing Lanes |  | Montgomery | 2021-07-01 | Reconstruction | Pursley, Charles (FHWA);#37 | Yes | FALSE | FY21 | [8 empty] | Project is under construction. I have attended a weekly project status update meeting to track the project progress through construction. Weekly meetings have not been held since December 2020. I have not approved any change orders or VECPs since October 1. Those activities were complete last PY. The final quarterly project QC/QMmeeting was held on June 23, 2021. I atended as well as the Paement and Materiasl Specialist. |  | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3156 | 0544065 | J2P3156 | Add roundabout at Rte. 19 north junction (Basinger Corner) north of Laddonia. $2,346,000 Open Container funds. | Audrain |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Urgency;#Environmental and Stakeholders |  |  |  |  | Construction Inspections |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3259 | 0614179 | J2P3259 | Pavement resurfacing on northbound lanes from Rte. V to 0.4 mile south of Rte. UU in Pike County near Bowling Green. | Lincoln |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity |  |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll;#Pavement/Materials Review |  |  |  |  | 2021-09-23 14:25 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3357 | 0791082 | J2P3357 | Bridge replacement over Lyon Street, Warren Barrett Drive, Burlington Northern Santa Fe Railroad and Bear Creek 0.4 mile north of Rte. T in Hannibal. | MARION |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Program Involvement Findings |  | Core Team Member;#Design Preliminary Plans;#Differing Eligibilities Review |  |  | Title VI |  |  |  |  | 2021-09-29 15:34 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3447 | Not Assigned | J2P3447 | Scoping for roadway improvement between Bus. 54 and Rte. 79 in Louisiana. | Audrain |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member | [7 empty] | 2021-09-23 14:12 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900391 | 9900391 | TAP 9900 (391) LPA: NE District - CONSTRUCTION |  | TROY |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval |  | The previously approved AJR will be reevaluated and updated. Title VI review. | [5 empty] | 2021-09-29 15:56 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I2006 | 0351291 | Add interchange south of Rte. 92 at 19th Street in Kearney. | New Interchange on I-35 at Kearney | Clay | 2022-02-25 | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Local Considerations;#National/Regional Significance;#Program Involvement Findings | New interchange construction with a Diverging Diamond interchange configuration and new bridge. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | Work Zone/TMP;#Title VI |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | The project has been delayed due to ROW acquisition delays, therefore no construction activities have been performed. The project is expected to be let in early 2022. Significant utility relocation is required before construction begins so the main construction will likely occur in FY23. Will consider including as a PoDI during FY23. |  | 2021-09-29 15:29 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | N/A | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY21 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification could require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#Design 90% Review;#AJR Approval;#Design Exception Approval;#Differing Eligibilities Review |  | Core team member. NEPA review and approval. AJR or Traffic Safety and Operational Analysis will likely be required. 90% Plans review and design exception approval. |  |  |  | FHWA has participated in 3 core team meetings and have offered feedback on the level of documentation and analysis needed for multiple interchange configurations. A separate meeting with the HQ Major project specialist was held to confirm that this project was not considered a Major Project as defined by FHWA and will not need a FP nor Major Project Plan. This information was shared with MoDOT. |  | 2021-09-29 08:11 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3189 | 4351323 | I-435 Bridge over the Missouri River in Kansas City, MO | Bridge deck replacement at the Missouri River. Project involves twin bridges A0767. | Clay | 2019-05-17 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Other;#Urgency;#Complexity;#Local Considerations;#Program Involvement Findings | Schedule: Work zone impacts will be significant and will require expedited construction. Local Consideration: Work zone impacts will be regionally significant. |  |  | Construction inspection to include focused checklist for Work Zone Traffic Control. | Work Zone/TMP;#Title VI |  | Construction inspections to include a focused checklist for Work Zone Traffic Control. | FY 21: Due to Covid-19 travel restrictions, no construction inspections were performed on this project. There has been no PoDI involvement this performance year. The project is scheduled to be completed at the end of 2021 and it will be retained as a PoDI project to include a work zone traffic control review. |  | 2021-09-29 16:08 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4P2237 | S300097 | J4P2237- I-49 Outer Roads Conversion to from One-way to Two-way | Conversion of the outer roads of I-49 to two-way traffic on the east outer road from Rt. 150 to Blue Ridge Boulevard and on the west outer road from Blue Ridge Boulevard to 0.5 miles north of Rt. 150 in Grandview. | Jackson | 2023-09-30 |  | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Project Administration;#Local Considerations;#Program Involvement Findings | Large complex local project using the Design-Build delivery method with limited experience by City staff. ROW and Utility impacts that could impace schedule. Complex traffic control during construction with significant traffic impacts on the local and interstate highways. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Contract Administration;#Other | Environmental Commitments;#AJR Approval;#Design Build AAS Concur;#Design Build Certification;#Design Build Procurement;#FMIS Authorization |  | Title VI;#Work Zone/TMP |  | Construction inspections. Focused Reviews on Title VI and Work Zone Traffic Control. FHWA will continue to provide feedback on proposed revisions to the approved AJR and will coordinate with MoDOT and the City on these changes and any required approval. | Reviewed all books of Draft RFP and provided comments on Books 1 and 2, and ITP. • During the confidential one-one-one meetings, I coordinated review of potential AJR deviations with Division staff and leadership. Reviewed proposed TS&O reports and offered feedback and concerns to MoDOT on all three teams’ draft submittals. • Worked with Mike Landvik and Jim Stevenson to develop a draft LPA Design-Build checklist template for use on future LPA Design-Build projects. • Provided recommendations on how to structure the RFP documents when these were in the early stages of development. Assured that federal requirements were conveyed and followed. • Coordinated involvement on an ADA concern from both Civil Rights and Environmental staff members from MoDOT and FHWA to assure that the decision by the City to modify the sidewalk requirements in the RFP did not violate NEPA and/or ADA requirements. • Reviewed and approved the final RFP for release and facilitated the FMIS construction authorization. This took quite a bit of time since the process for approval was different than traditional D-B-B project authorizations. I provided guidance on the RFP certification letter and what needed to be included in the submittal. MoDOT and the City were very appreciative of this guidance and involvement. • Reviewed the proposals and participated in the proposal evaluation process and offered feedback on how FHWA could concur in the project award. Concurred in project award. Reviewed proposed AJR changes and offered valuable feedback. Coordinated a meeting to convey FHWA expectations on the criteria for acceptance of a proposed AJR revision involving a proposed roundabout in lieu of the approved configuration.s expectation |  | 2021-09-29 15:57 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900086 | 9900086 | TAP 9900(086) LPA: NE District - CONSTRUCTION |  | CITY OF EAST PRAIRIE |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#PY20;#PY19 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. | Innovative Contracting/Design Build;#Contract Administration;#Construction Inspection & Quality;#Other;#Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance;#Scoping;#Special Funding;#Bridge TSandL |  | Change Order Approval;#Work Zone/TMP;#Civil Rights/Cert Payroll;#Erosion Control;#DBE Goals;#Buy America;#Title VI |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21: Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21. Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. Reviewed and provided comments to revised project AJR and issued approval. Submitted all required monthly project reports through September, 2021. Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan in coordination with the Division Office Pavement and Materials Engineer. |  | 2021-09-29 15:58 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  | Project Authorization and Project Agreements;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. |  | 2021-09-27 15:19 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397,J5I3572, | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. | Design PSandE Review |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:22 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | B015001 | B015001 | Camden Co. Bridge Replacement on Willow Creek Road |  | Camden |  |  | Pursley, Charles (FHWA);#37 | No | FALSE | FY21 | [8 empty] | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3369 | S402035 | 5S3369 - Central District ADA Improvements - Alternate Project Delivery Method | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address Route: Various nonstandard ADA facilities at various locations in the Central and Northwest Districts. | Various | 2021-11-01 | ADA/Sidewalk | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#Design Build AAS Concur | Design Build Procurement;#Design Build Certification |  | Construction Inspections;#Work Zone/TMP;#ADA |  |  | FY2021-The DB team spent a lot of time refining the project scope. I attended several core team meetings and provided a lot of guidance and advice on the DB process as well as NEPA compliance. The RFQ has been developed and the RFP is being finalized. I reviewed these document and provided input and guidance. FY2022 - |  | 2021-09-27 15:26 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5P3337 | 0543193 | Missouri River Bridge in Jefferson Cit | Bridge rehabilitation over Missouri River. Project involves bridges A4497 and L0550. | Cole, Callaway |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Complexity;#Schedule;#National/Regional Significance;#Local Considerations | [9 empty] | 2021-09-28 20:20 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3269 | S401083 | J5S3269 | Pave Resurfacing from Bus 44 to Rt J, Includes Pave Inprove on Rt H from Rt 17 to End of State Maintenance | Pulaski |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3296 | 0171015 | J9P3296 - Program Development | Pavement Improvements from Route 106 in Summersville to Route 160 Near West Plains, 34.064 miles | TEXAS |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 3219702 | 3219702 | 3219702 | Design to Replace Old Dilapidated Sidewalks Along Main from 15th to 11 St | Jasper |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Other;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#TSandO Approval;#Design Exception Approval;#Differing Eligibilities Review | [6 empty] | VE Study scheduled / OINCC submittal / Major Project | 2021-09-29 17:00 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2090 | 2705360 | J6I2090 | Bridge replacement, bridge rehabilitation and pavement repair over Conway Road and New Ballas Road and bridge rehabilitation for I-270 mainline and ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052, A4654, A4657, A4580 and A4581. | St. Louis |  | Bridge Replacement |  | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations |  | Core Team Member;#TSandO Approval;#Design Exception Approval;#Design Preliminary Plans |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:01 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2222 | 0641061 | J6I2222 I-64 at 22nd and Jefferson | Modify interchange configuration between 18th Street and Garrison Avenue. Project involves bridges A1523, A1501, A1528, A0840, and A0838. $7,900,000 Cost Share and $7,900,000 Land Clearance for Redevelopment Authority funds. | St. Louis City | 2020-05-15 | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Schedule;#Cost;#Urgency;#Environmental & Stakeholders;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 7 change orders with no comments. Reviewed and approved 2 VECP with no comments. The VECPs were previously discussed in the PAVE that was held after award and before NTP. LP-Project has 3 trainee spots of 1000 hours each. Prime says they will not use trainees until summer 2021. Project is scheduled to be completed 6/2022. CUF still needed for D&K Welding. FY 2022 |  | 2021-09-29 17:02 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 Rte N EA | Scoping for environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | New Construction | Peters, Taylor (FHWA);#43 | No | FALSE | FY21 | Environmental & Stakeholders |  | EA/EIS Public Involvement | EA/EIS Public Involvement | [6 empty] | 2021-09-29 07:32 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 & J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Local Considerations |  | Core Team Member | Core Team Member |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:13 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  | Bridge 90% Review;#Design Exception Approval;#Design 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design 90% Review;#Design Exception Approval;#Bridge 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2021-09-28 10:36 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [5 empty] | FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination. FY 2022 |  | 2021-09-29 06:44 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments | [6 empty] | Part of I-270 North Major project / EA reval | 2021-09-29 07:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3233 | not assigned | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371) | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371). Excludes bridge along Missouri River in St. Joseph. | Andrew | 2020-06-19 | Resurfacing | Irving, Kevin (FHWA);#29 | Yes | FALSE | FY21 | Complexity;#Schedule;#Local Considerations | Contract Administration. Pavement and materials quality. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. |  |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. | Due to Covid-19 travel restrictions, construction inspections could not be performed on this project. There were no project actions on this project during FY 21. The project has been completed and therefore will not be carried over as a PoDI in FY 22. |  | 2021-09-21 18:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3201 | 4952604 | J6I3201 LPA David Hoekel Parkway I-70 Interchange Phase 1 and Phase 2 | Payment to Wentzville for adding interchange west of Point Prairie Road. $5,000,000 Cost Share funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Environmental and Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 8 change orders with no issues. No VECP's have been submitted and none are expected. LP- A CUF review is need for Columbia Curb and Gutter. Project has an OJT Goal of 1 trainee for 1000 hours. Contractor says they are looking for a trainee to use summer 2021. Project closing is delayed until 11/2021. FY 2022 |  | 2021-09-29 06:50 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval;#Core Team Member;#Design Preliminary Plans;#ATC;#FMIS Authorization;#CMAQ Project Review;#Design 90% Review | AJR Approval;#Design Build Certification;#FMIS Authorization;#CMAQ Project Review;#Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America;#Pavement/Materials Review;#Quality Control;#Bridge Inspection;#Title VI |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed. FY 2022 |  | 2021-09-29 15:59 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 & J6I3500 | 2553052 &255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Cost;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review | Core Team Member;#Design Preliminary Plans;#Design PSandE Review;#Other |  | Construction Inspections;#Work Zone/TMP;#Bridge Inspection |  |  |  | VE Study | 2021-09-29 06:57 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:30 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3167 | 0073024 | Rte. 7 and South Ave. Signalization Improvements | Add a signalized intersection at Rte. 7 intersection sidewalk connections (Blue Springs) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | This project was originally programmed as an LPA project sponsored by the City of Blue Springs with the TIP #625033. It was later combined with a MoDOT sponsored project under the TIP #690490 and MoDOT Job Number 4S3167. FMIS action completed 5/14/21. The integration of the LPA CMAQ project into the MoDOT project was correctly programmed and the FMIS action aligned with the programming actions. . |  | 2021-09-28 19:38 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P2321 J6P2321B | 0471072 0471080 | FY 2014 TIGER VI J6P2321 & J6P2321B: MO-47 - Bridge over Missouri River | FY 2014 TIGER ​Replace bridge over the Missouri River from Rte. 94 to Fifth Street in Washington. Cost share: $500,000 city of Washington, $250,000 Franklin County and $50,000 Warren County. | Franklin | 2016-05-20 | Bridge Replacement | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#PY20;#PY19;#PY18;#PY17;#PY16;#FY22 | Funding;#Other |  |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY2021 The project is substantially complete with aethetic lighting still be completed. Due to COVID restrictions, the subcontractor has not been able to travel. All TIGER funds have been expended. Project is submitting all quarterly reports and performance measure reports on time as required. FY2022 |  | 2021-09-29 06:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 7302674 | 7302674 | CMAQ - 7302(674) Intersection Improvements | CMAQ - 7302(674) Intersection Improvements - Intersection Improvement, Traffic Signals, Roadway Realignment | St. Charles |  | Reconstruction | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  |  | Design 90% Review | PE work has been completed. ROW authorization in FMIS on 8/14/20 |  |  |  | The project description in the FMIS action and EWG TIP are aligned. A FMIS action on 7/9/21 extended the construction award date by 12 months (July 2022). The EWG FY2022-2025 TIP update to be approved by the EWG in October 2021 reflects the new construction award program year of 2022. |  | 2021-09-28 19:34 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member | Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Title VI |  |  |  |  | 2021-09-29 15:53 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:15 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 | Environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-28 20:23 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build AAS Concur;#Design Build Certification | Design Build Certification |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:28 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0601 | 711063 | 7P0601 - Rte. I-49 Missouri Arkansas Connector | Bella Vista Bypass Connection for New I-49 | McDonald | 2021-09-30 | New Construction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Program Involvement Findings | Construction of new interstate section using BUILD funding | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization |  | Environmental Commitments;#Special Funding;#Change Order Approval;#VECP Approval;#Interstate Designation Request;#Title VI | Change Order Approval;#VECP Approval;#Environmental Commitments;#Special Funding |  | FY2021 Project is under construction. I have reviewed and approved 3 VECPs and 10 change orders since October 1. Additional change orders and VECPs were approved last PY.I prepared the final inspection report to document interstate standards. I have assited with preparing the request for acceptance into the Interstate system. FY2022 |  | 2021-09-29 15:31 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations | Bridge replacement using ATC | ATC | ATC |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:47 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I0445 | 0442293 | Rte. I-44, Webster Co. New Interchange in Marshfield - LPA Administered |  | Webster | 2021-07-27 |  | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | Yes | TRUE | FY21 | Program Involvement Findings |  |  |  |  | Title VI |  |  | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-29 15:35 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 |  | J9P3122 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [7 empty] | 2021-09-23 13:19 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 | Chester Bridge | Perry | 2022-06-22 | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Scoping;#Conceptual Report Review;#Design Build Procurement;#Design Build Certification;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#FMIS Authorization;#Conditional Clearance | [7 empty] | 2021-09-24 09:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 |  | J9P3305 | Scoping for bridge improvements over Current River and Round Spring. | SHANNON |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#Bridge TSandL;#Environmental Commitments | Core Team Member;#Conceptual Report Review;#Bridge TSandL | [6 empty] | 2021-09-23 13:20 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3584 | 0604090 | J9P3584 | Future I-57 and US60; Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds | NEW MADRID |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Scoping;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:36 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | BUTLER |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | BUTLER |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 | AJR Approval;#Design Preliminary Plans;#Conceptual Report Review | Conceptual Report Review;#Design Preliminary Plans;#AJR Approval |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Buy America;#Civil Rights/Cert Payroll |  |  | Provided recommnedation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 |  | J9P3751 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval | [6 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3764 |  | J9P3764 | Future I-57 Phase 1B Add lanes and outer roads to upgrade corridor to freeway standards from County RoadB 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Urgency;#Funding;#Environmental and Stakeholders;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:27 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | LPA City of O'Fallon I-70 at Bryan Road |  | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [6 empty] | no funds yet | 2021-09-29 07:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3232 J9S3232B | S701051/S703077 | J9S3232 & J9S3232B | Bootheel Bridge Bundle Design-Build | VARIOUS |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Environmental and Stakeholders;#Corporate Actions;#Local Considerations | Bundle Bridge project in rural area | Design Build Certification;#Design Build Procurement;#Design Build AAS Concur;#Design Exception Approval | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval |  | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America |  |  | Provided guidance on the Design-Build process. |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 & JP3496B | S502067 S502089 | J6P3496 & JP3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member | [7 empty] | 2021-09-29 07:29 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 |  | J9S3381 | Bridge replacement over Black River. Project involves bridge K0263. | Butler |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Schedule;#Environmental and Stakeholders;#Local Considerations |  |  |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5640613 | 5640613 City of St. Peters | City of St. Peters Jungermann Road Bridge over branch of Spencer Creek, replace culverts (23077 & 23079) - 6563-15 | St. Charles County |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Schedule;#Project Administration;#Local Considerations | LPA project, utility related time extension and problematic contractor |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY 2021 Reviewed 3 change orders. Multiple discussions held on time extensions, LDs, and possible claim along with the format and eligibility of the change orders. 2 of the change orders were approved. The LPA has needed a lot of direction since this project had huge impacts to schedule and budget due to utilities. LP- CUF has been conduted for XL Contracting. No OJT hours on project. FY 2022 |  | 2021-09-25 09:41 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#PY20;#FY20;#FY22 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2021-09-25 10:16 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526 | 0552121 | J6I3526 | Scoping for corridor improvements along the I-55 corridor from 0.5 mile north of Rte. Z to 1 mile south of Rte. 67. Potential Design-Build project. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | 696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:14 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | n/a | 5417604 5417605 | 5417604 & 5417605 LPA City of St. Louis Jefferson/22nd Improvements | LPA City of St. Louis Jefferson/22nd Improvements | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Project Administration;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Design Exception Approval;#Design Preliminary Plans;#Design 90% Review |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Buy America;#Civil Rights/Cert Payroll;#Title VI |  |  | FY 2021 90% final plan package reviewed and multiple comments submitted including Buy America, proprietary items, traffic control, etc. No Design Exceptions have been submitted and none are expected. Most of the comments from the preliminary plan review were addressed. Project was giving conditional PS&E approval and FMIS authorization/obligation with a long list of conditions. MoDOT is monitoring the conditions. FY 2022 |  | 2021-09-29 16:02 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NA | NA | Pedestrian and Bikeways Improvements | Connect existing bikeways on 11th street and 12th street (Kansas City) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | TRUE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | No FMIS ACTION to-date. KC District staff indicate that this project will be authorized and funds obligated in the early Spring (2022). |  | 2021-09-27 13:25 | McMahon, Bradley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3359 | 0444204 | J6I3359 | Scoping for pedestrian studies at Selma Avenue Overpass and I-55 at Daycare Overpass. Project involves pedestrian bridges A1729 and A0619. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#Environmental Commitments | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | Project Authorization and Project Agreements;#Project Planning & Programming;#Project Financing;#Special Funding;#FMIS Authorization |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added: Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted. MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. Reviewed the consultant solicitation document issued by MoDOT. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J6P3510 | not assigned | J6P3510 | Scoping for ADA Transition Plan improvements at various locations in the St. Louis District. Potential DesignBuild project. | Various |  | ADA/Sidewalk | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | Not assigned | N/A | I-29 near Ambassador Drive, Permit Project | Potential Permit Project near KCI Airport at I-29 and Route D interchange near Ambassador Drive. | Platte |  | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE |  | Local Considerations;#Other | Proposed Dogbone Roundabout interchange at I-29 and Rt. D with connection to a development property. | TSandO Approval |  | Meetings and Review and approval of a TS&O report. | [5 empty] | 2021-09-23 14:59 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 | Scoping for interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#AJR Approval;#Design Exception Approval | [6 empty] | System to System Interchange / EIS reval | 2021-09-29 07:33 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
|  |  | J2P3347 | [5 empty] | No | TRUE | [11 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3661 | not assigned | J6P3661 | Scoping for corridor improvements from Rte. 100 to I-44. Project involves various bridges | Franklin |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | Scoping for capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## SW
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | Still a PODI | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | 2700509 | 2700509 | 2700509 - City of Fulton AID Demonstration | Bridge Replacement on 2nd ST Bridge over Stinson Creek and Stinson Creek Greenway, Bridge No. 1555011 located on State Route O in the City of Fulton. Accelerated Innovation Deployment (AID Demonstration program) | Callaway |  | Bridge Replacement | Pursley, Charles (FHWA);#37;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Discretionary Grant and Financing;#Project Administration;#Program Involvement Findings |  | Design Preliminary Plans;#Design 90% Review;#Special Funding;#Differing Eligibilities Review |  |  | Work Zone/TMP;#Bridge Inspection |  |  |  |  | 2021-09-29 08:05 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 4300112 | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  | Design PSandE Review;#Design PSandE Approval;#Environmental Commitments;#Core Team Member;#Design Preliminary Plans;#Other |  | Construction Inspections;#Erosion Control;#Civil Rights/Cert Payroll;#Work Zone/TMP;#Buy America |  | Construction inspections with focused review checklists. | FY 20 and FY 21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ. Submitted all monthly BUILD reports as required. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5617602 5617603 | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  | Design Preliminary Plans;#Design 90% Review;#Design PSandE Approval | Design Preliminary Plans;#Design 90% Review |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted. FY 2022 |  | 2021-09-29 06:56 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build AAS Concur | Design Build Certification |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:28 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0601 | 711063 | 7P0601 - Rte. I-49 Missouri Arkansas Connector | Bella Vista Bypass Connection for New I-49 | McDonald | 2021-09-30 | New Construction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Program Involvement Findings | Construction of new interstate section using BUILD funding |  | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization |  | Interstate Designation Request;#Title VI | Change Order Approval;#VECP Approval;#Environmental Commitments;#Special Funding |  | FY2021 Project is under construction. I have reviewed and approved 3 VECPs and 10 change orders since October 1. Additional change orders and VECPs were approved last PY.I prepared the final inspection report to document interstate standards. I have assited with preparing the request for acceptance into the Interstate system. FY2022 |  | 2021-09-29 15:31 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Design Build Procurement;#AJR Approval;#Bridge 90% Review;#Interstate Designation Request |  | AJR (if required), Bridge and Roadway 90% plans, Interstate De-designation, Funding review, T&E review, NEPA EA review/approval, Design-Build procurement |  |  |  | FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. |  | 2021-09-20 17:44 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3029 | 0444188 | J6I3029 I-44 at I-270 and Meramec River Bridge |  | St. Louis |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | FALSE | FY21;#FY20;#PY19 | [8 empty] | FY 2021 Reviewed and approved 5 change orders with no issues. LP-CUF Reviews still need to be performed for DW Mertzke,Petro legistics, and Prestige truking. Project ending 2/2022. |  | 2021-09-24 10:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3109 | N/A | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. Project involves twin bridges A1293 in the NB and SB lanes. | Andrew |  | Bridge Replacement | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Schedule;#Project Administration;#Local Considerations;#Program Involvement Findings | Complexity: Likely to include head to head traffic on Interstate. Schedule: Scheduled bridge work has risk of delayed completion. Local considerations: Work Zone complexity will significantly impact traffic. | Contract Administration;#Construction Inspection & Quality |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Title VI |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Due to Covid-19 travel restrictions, no construction inspections were performed on this project. No PoDI activity occurred during PY21. The project is nearly completed so this project will not be retained as a PoDI in FY 22. |  | 2021-09-29 15:32 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3110 | 0292195 | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Atchison | 2020-03-20 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental & Stakeholders;#Funding | Construction inspection to include focused review checklists and a bridge inspection. |  |  | Construction inspection to include focused review checklists and a bridge inspection.. | Construction Inspections;#Work Zone/TMP;#Buy America;#Erosion Control;#Bridge Inspection |  | Construction inspection to include focused review checklists and a bridge inspection. | FY 21: The project has been awarded and construction started in the Spring of 2021. No PoDI activity was performed due to the COVID pandemic travel restrictions. The project has been retained as a construction PoDI for FY 22. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1P3378 | not assigned | Rt. 136 Flood Resiliency Permanent Repair | Flood Resiliency Permanent Repair from Mo. River to I-29 near Rock Port. Atchison County | Atchison | 2022-04-15 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Local Considerations;#Funding | ER funded flood resiliency project. | Design 90% Review |  | Review of 90% Plans and compare to approved DDIR. |  |  |  | FY21: Reviewed resiliency proposal and DDIR and had multiple meetings to discuss the benefit/cost analysis expectations. Approved DDIR and resiliency proposal. |  | 2021-09-23 14:46 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-02-25 | Pavement and Bridge | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. | Final Design;#Plan, Specification, & Estimate Development;#Advertising & Award;#Core Team Member;#Special Funding | Design Preliminary Plans;#Conceptual Report Review;#Environmental Commitments | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting. | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Environmental Commitments;#Buy America |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | Not Assigned | J2I3274 | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | MONTGOMERY |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3309 | 0703276 | J2I3309 | Pavement improvements from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | MONTGOMERY |  | Pavement Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3310 | 0703286 | J2I3310 | Pavement resurfacing from the Callaway County line to 2 miles east of Rte. F near High Hill. | MONTGOMERY |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | Conceptual Report Review |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review;#Civil Rights/Cert Payroll |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 | Scoping for interchange improvements at Stracks Church County Road near Wright City. | WARREN |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3043 | 0471083 | J2P3043 | Interchange improvements at Rte. 61 in Troy. Project involves bridge A2604. | LINCOLN |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2S3221 J2P3222 J2P3 | S201034 / 13620 | J2S3221 / J2P3222 / J2P3224 |  | SCHUYLER |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-29 07:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | MONTGOMERY |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#AJR Approval |  | Title VI |  |  |  |  | 2021-09-29 15:37 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3226 J2I3226B | 0703279 | Rte. I-70, Mineola Hill Truck Climbing Lanes |  | Montgomery | 2021-07-01 | Reconstruction | Pursley, Charles (FHWA);#37 | Yes | FALSE | FY21 | [8 empty] | Project is under construction. I have attended a weekly project status update meeting to track the project progress through construction. Weekly meetings have not been held since December 2020. I have not approved any change orders or VECPs since October 1. Those activities were complete last PY. The final quarterly project QC/QMmeeting was held on June 23, 2021. I atended as well as the Paement and Materiasl Specialist. |  | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3156 | 0544065 | J2P3156 | Add roundabout at Rte. 19 north junction (Basinger Corner) north of Laddonia. $2,346,000 Open Container funds. | Audrain |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Urgency;#Environmental and Stakeholders |  |  |  |  | Construction Inspections |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3259 | 0614179 | J2P3259 | Pavement resurfacing on northbound lanes from Rte. V to 0.4 mile south of Rte. UU in Pike County near Bowling Green. | Lincoln |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity |  |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll;#Pavement/Materials Review |  |  |  |  | 2021-09-23 14:25 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3357 | 0791082 | J2P3357 | Bridge replacement over Lyon Street, Warren Barrett Drive, Burlington Northern Santa Fe Railroad and Bear Creek 0.4 mile north of Rte. T in Hannibal. | MARION |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Program Involvement Findings |  | Core Team Member;#Design Preliminary Plans;#Differing Eligibilities Review |  |  | Title VI |  |  |  |  | 2021-09-29 15:34 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3447 | Not Assigned | J2P3447 | Scoping for roadway improvement between Bus. 54 and Rte. 79 in Louisiana. | Audrain |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member | [7 empty] | 2021-09-23 14:12 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900391 | 9900391 | TAP 9900 (391) LPA: NE District - CONSTRUCTION |  | TROY |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval |  | The previously approved AJR will be reevaluated and updated. Title VI review. | [5 empty] | 2021-09-29 15:56 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I2006 | 0351291 | Add interchange south of Rte. 92 at 19th Street in Kearney. | New Interchange on I-35 at Kearney | Clay | 2022-02-25 | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Local Considerations;#National/Regional Significance;#Program Involvement Findings | New interchange construction with a Diverging Diamond interchange configuration and new bridge. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | Work Zone/TMP;#Title VI |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | The project has been delayed due to ROW acquisition delays, therefore no construction activities have been performed. The project is expected to be let in early 2022. Significant utility relocation is required before construction begins so the main construction will likely occur in FY23. Will consider including as a PoDI during FY23. |  | 2021-09-29 15:29 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | N/A | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY21 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification could require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#Design 90% Review;#AJR Approval;#Design Exception Approval;#Differing Eligibilities Review |  | Core team member. NEPA review and approval. AJR or Traffic Safety and Operational Analysis will likely be required. 90% Plans review and design exception approval. |  |  |  | FHWA has participated in 3 core team meetings and have offered feedback on the level of documentation and analysis needed for multiple interchange configurations. A separate meeting with the HQ Major project specialist was held to confirm that this project was not considered a Major Project as defined by FHWA and will not need a FP nor Major Project Plan. This information was shared with MoDOT. |  | 2021-09-29 08:11 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3189 | 4351323 | I-435 Bridge over the Missouri River in Kansas City, MO | Bridge deck replacement at the Missouri River. Project involves twin bridges A0767. | Clay | 2019-05-17 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Other;#Urgency;#Complexity;#Local Considerations;#Program Involvement Findings | Schedule: Work zone impacts will be significant and will require expedited construction. Local Consideration: Work zone impacts will be regionally significant. |  |  | Construction inspection to include focused checklist for Work Zone Traffic Control. | Work Zone/TMP;#Title VI |  | Construction inspections to include a focused checklist for Work Zone Traffic Control. | FY 21: Due to Covid-19 travel restrictions, no construction inspections were performed on this project. There has been no PoDI involvement this performance year. The project is scheduled to be completed at the end of 2021 and it will be retained as a PoDI project to include a work zone traffic control review. |  | 2021-09-29 16:08 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4P2237 | S300097 | J4P2237- I-49 Outer Roads Conversion to from One-way to Two-way | Conversion of the outer roads of I-49 to two-way traffic on the east outer road from Rt. 150 to Blue Ridge Boulevard and on the west outer road from Blue Ridge Boulevard to 0.5 miles north of Rt. 150 in Grandview. | Jackson | 2023-09-30 |  | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Project Administration;#Local Considerations;#Program Involvement Findings | Large complex local project using the Design-Build delivery method with limited experience by City staff. ROW and Utility impacts that could impace schedule. Complex traffic control during construction with significant traffic impacts on the local and interstate highways. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Contract Administration;#Other | Environmental Commitments;#AJR Approval;#Design Build AAS Concur;#Design Build Certification;#Design Build Procurement;#FMIS Authorization |  | Title VI;#Work Zone/TMP |  | Construction inspections. Focused Reviews on Title VI and Work Zone Traffic Control. FHWA will continue to provide feedback on proposed revisions to the approved AJR and will coordinate with MoDOT and the City on these changes and any required approval. | Reviewed all books of Draft RFP and provided comments on Books 1 and 2, and ITP. • During the confidential one-one-one meetings, I coordinated review of potential AJR deviations with Division staff and leadership. Reviewed proposed TS&O reports and offered feedback and concerns to MoDOT on all three teams’ draft submittals. • Worked with Mike Landvik and Jim Stevenson to develop a draft LPA Design-Build checklist template for use on future LPA Design-Build projects. • Provided recommendations on how to structure the RFP documents when these were in the early stages of development. Assured that federal requirements were conveyed and followed. • Coordinated involvement on an ADA concern from both Civil Rights and Environmental staff members from MoDOT and FHWA to assure that the decision by the City to modify the sidewalk requirements in the RFP did not violate NEPA and/or ADA requirements. • Reviewed and approved the final RFP for release and facilitated the FMIS construction authorization. This took quite a bit of time since the process for approval was different than traditional D-B-B project authorizations. I provided guidance on the RFP certification letter and what needed to be included in the submittal. MoDOT and the City were very appreciative of this guidance and involvement. • Reviewed the proposals and participated in the proposal evaluation process and offered feedback on how FHWA could concur in the project award. Concurred in project award. Reviewed proposed AJR changes and offered valuable feedback. Coordinated a meeting to convey FHWA expectations on the criteria for acceptance of a proposed AJR revision involving a proposed roundabout in lieu of the approved configuration.s expectation |  | 2021-09-29 15:57 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900086 | 9900086 | TAP 9900(086) LPA: NE District - CONSTRUCTION |  | CITY OF EAST PRAIRIE |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#PY20;#PY19 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. | Innovative Contracting/Design Build;#Contract Administration;#Construction Inspection & Quality;#Other;#Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance;#Scoping;#Special Funding;#Bridge TSandL |  | Change Order Approval;#Work Zone/TMP;#Civil Rights/Cert Payroll;#Erosion Control;#DBE Goals;#Buy America;#Title VI |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21: Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21. Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. Reviewed and provided comments to revised project AJR and issued approval. Submitted all required monthly project reports through September, 2021. Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan in coordination with the Division Office Pavement and Materials Engineer. |  | 2021-09-29 15:58 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  | Project Authorization and Project Agreements;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. |  | 2021-09-27 15:19 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397,J5I3572, | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. | Design PSandE Review |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:22 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | B015001 | B015001 | Camden Co. Bridge Replacement on Willow Creek Road |  | Camden |  |  | Pursley, Charles (FHWA);#37 | No | FALSE | FY21 | [8 empty] | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3369 | S402035 | 5S3369 - Central District ADA Improvements - Alternate Project Delivery Method | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address Route: Various nonstandard ADA facilities at various locations in the Central and Northwest Districts. | Various | 2021-11-01 | ADA/Sidewalk | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#Design Build AAS Concur | Design Build Procurement;#Design Build Certification |  | Construction Inspections;#Work Zone/TMP;#ADA |  |  | FY2021-The DB team spent a lot of time refining the project scope. I attended several core team meetings and provided a lot of guidance and advice on the DB process as well as NEPA compliance. The RFQ has been developed and the RFP is being finalized. I reviewed these document and provided input and guidance. FY2022 - |  | 2021-09-27 15:26 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5P3337 | 0543193 | Missouri River Bridge in Jefferson Cit | Bridge rehabilitation over Missouri River. Project involves bridges A4497 and L0550. | Cole, Callaway |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Complexity;#Schedule;#National/Regional Significance;#Local Considerations | [9 empty] | 2021-09-28 20:20 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3269 | S401083 | J5S3269 | Pave Resurfacing from Bus 44 to Rt J, Includes Pave Inprove on Rt H from Rt 17 to End of State Maintenance | Pulaski |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3296 | 0171015 | J9P3296 - Program Development | Pavement Improvements from Route 106 in Summersville to Route 160 Near West Plains, 34.064 miles | TEXAS |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 3219702 | 3219702 | 3219702 | Design to Replace Old Dilapidated Sidewalks Along Main from 15th to 11 St | Jasper |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Other;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#TSandO Approval;#Design Exception Approval;#Differing Eligibilities Review | [6 empty] | VE Study scheduled / OINCC submittal / Major Project | 2021-09-29 17:00 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2090 | 2705360 | J6I2090 | Bridge replacement, bridge rehabilitation and pavement repair over Conway Road and New Ballas Road and bridge rehabilitation for I-270 mainline and ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052, A4654, A4657, A4580 and A4581. | St. Louis |  | Bridge Replacement |  | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations |  | Core Team Member;#TSandO Approval;#Design Exception Approval;#Design Preliminary Plans |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:01 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2222 | 0641061 | J6I2222 I-64 at 22nd and Jefferson | Modify interchange configuration between 18th Street and Garrison Avenue. Project involves bridges A1523, A1501, A1528, A0840, and A0838. $7,900,000 Cost Share and $7,900,000 Land Clearance for Redevelopment Authority funds. | St. Louis City | 2020-05-15 | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Schedule;#Cost;#Urgency;#Environmental & Stakeholders;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 7 change orders with no comments. Reviewed and approved 2 VECP with no comments. The VECPs were previously discussed in the PAVE that was held after award and before NTP. LP-Project has 3 trainee spots of 1000 hours each. Prime says they will not use trainees until summer 2021. Project is scheduled to be completed 6/2022. CUF still needed for D&K Welding. FY 2022 |  | 2021-09-29 17:02 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 Rte N EA | Scoping for environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | New Construction | Peters, Taylor (FHWA);#43 | No | FALSE | FY21 | Environmental & Stakeholders |  | EA/EIS Public Involvement | EA/EIS Public Involvement | [6 empty] | 2021-09-29 07:32 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 & J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Local Considerations |  | Core Team Member | Core Team Member |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:13 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  | Bridge 90% Review;#Design Exception Approval;#Design 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design 90% Review;#Design Exception Approval;#Bridge 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2021-09-28 10:36 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [5 empty] | FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination. FY 2022 |  | 2021-09-29 06:44 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments | [6 empty] | Part of I-270 North Major project / EA reval | 2021-09-29 07:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3233 | not assigned | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371) | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371). Excludes bridge along Missouri River in St. Joseph. | Andrew | 2020-06-19 | Resurfacing | Irving, Kevin (FHWA);#29 | Yes | FALSE | FY21 | Complexity;#Schedule;#Local Considerations | Contract Administration. Pavement and materials quality. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. |  |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. | Due to Covid-19 travel restrictions, construction inspections could not be performed on this project. There were no project actions on this project during FY 21. The project has been completed and therefore will not be carried over as a PoDI in FY 22. |  | 2021-09-21 18:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3201 | 4952604 | J6I3201 LPA David Hoekel Parkway I-70 Interchange Phase 1 and Phase 2 | Payment to Wentzville for adding interchange west of Point Prairie Road. $5,000,000 Cost Share funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Environmental and Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 8 change orders with no issues. No VECP's have been submitted and none are expected. LP- A CUF review is need for Columbia Curb and Gutter. Project has an OJT Goal of 1 trainee for 1000 hours. Contractor says they are looking for a trainee to use summer 2021. Project closing is delayed until 11/2021. FY 2022 |  | 2021-09-29 06:50 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval;#Core Team Member;#Design Preliminary Plans;#ATC;#FMIS Authorization;#CMAQ Project Review;#Design 90% Review | AJR Approval;#Design Build Certification;#FMIS Authorization;#CMAQ Project Review;#Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America;#Pavement/Materials Review;#Quality Control;#Bridge Inspection;#Title VI |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed. FY 2022 |  | 2021-09-29 15:59 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 & J6I3500 | 2553052 &255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Cost;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review | Core Team Member;#Design Preliminary Plans;#Design PSandE Review;#Other |  | Construction Inspections;#Work Zone/TMP;#Bridge Inspection |  |  |  | VE Study | 2021-09-29 06:57 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:30 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3167 | 0073024 | Rte. 7 and South Ave. Signalization Improvements | Add a signalized intersection at Rte. 7 intersection sidewalk connections (Blue Springs) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | This project was originally programmed as an LPA project sponsored by the City of Blue Springs with the TIP #625033. It was later combined with a MoDOT sponsored project under the TIP #690490 and MoDOT Job Number 4S3167. FMIS action completed 5/14/21. The integration of the LPA CMAQ project into the MoDOT project was correctly programmed and the FMIS action aligned with the programming actions. . |  | 2021-09-28 19:38 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P2321 J6P2321B | 0471072 0471080 | FY 2014 TIGER VI J6P2321 & J6P2321B: MO-47 - Bridge over Missouri River | FY 2014 TIGER ​Replace bridge over the Missouri River from Rte. 94 to Fifth Street in Washington. Cost share: $500,000 city of Washington, $250,000 Franklin County and $50,000 Warren County. | Franklin | 2016-05-20 | Bridge Replacement | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#PY20;#PY19;#PY18;#PY17;#PY16;#FY22 | Funding;#Other |  |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY2021 The project is substantially complete with aethetic lighting still be completed. Due to COVID restrictions, the subcontractor has not been able to travel. All TIGER funds have been expended. Project is submitting all quarterly reports and performance measure reports on time as required. FY2022 |  | 2021-09-29 06:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 7302674 | 7302674 | CMAQ - 7302(674) Intersection Improvements | CMAQ - 7302(674) Intersection Improvements - Intersection Improvement, Traffic Signals, Roadway Realignment | St. Charles |  | Reconstruction | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  |  | Design 90% Review | PE work has been completed. ROW authorization in FMIS on 8/14/20 |  |  |  | The project description in the FMIS action and EWG TIP are aligned. A FMIS action on 7/9/21 extended the construction award date by 12 months (July 2022). The EWG FY2022-2025 TIP update to be approved by the EWG in October 2021 reflects the new construction award program year of 2022. |  | 2021-09-28 19:34 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member | Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Title VI |  |  |  |  | 2021-09-29 15:53 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:15 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 | Environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-28 20:23 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations | Bridge replacement using ATC |  | ATC |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:47 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I0445 | 0442293 | Rte. I-44, Webster Co. New Interchange in Marshfield - LPA Administered |  | Webster | 2021-07-27 |  | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | Yes | TRUE | FY21 | Program Involvement Findings |  |  |  |  | Title VI |  |  | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-29 15:35 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5903803 | 5903803 - Jefferson Avenue Foot Bridge Over BNSF Railroad in Springfield | Rehabilitate the Jefferson Avenue foot bridge and provide ADA access | Greene | 2021-11-01 | Bridge Rehabilitation | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Project Administration;#Program Involvement Findings |  |  | Design PSandE Review |  | Construction Inspections;#Buy America;#Title VI |  |  |  |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  | Environmental Commitments;#Design Preliminary Plans | Design Build Procurement;#Design Build Certification |  | Environmental Commitments;#Special Funding;#Construction Inspections;#Title VI |  |  | The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. It is nearing completion and should be ready for execution soon. |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 |  | J9P3122 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [7 empty] | 2021-09-23 13:19 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 | Chester Bridge | Perry | 2022-06-22 | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Scoping;#Conceptual Report Review;#Design Build Procurement;#Design Build Certification;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#FMIS Authorization;#Conditional Clearance | [7 empty] | 2021-09-24 09:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 |  | J9P3305 | Scoping for bridge improvements over Current River and Round Spring. | SHANNON |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#Bridge TSandL;#Environmental Commitments | Core Team Member;#Conceptual Report Review;#Bridge TSandL | [6 empty] | 2021-09-23 13:20 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3584 | 0604090 | J9P3584 | Future I-57 and US60; Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds | NEW MADRID |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Scoping;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:36 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | BUTLER |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | BUTLER |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 | AJR Approval;#Design Preliminary Plans;#Conceptual Report Review | Conceptual Report Review;#Design Preliminary Plans;#AJR Approval |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Buy America;#Civil Rights/Cert Payroll |  |  | Provided recommnedation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 |  | J9P3751 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval | [6 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3764 |  | J9P3764 | Future I-57 Phase 1B Add lanes and outer roads to upgrade corridor to freeway standards from County RoadB 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Urgency;#Funding;#Environmental and Stakeholders;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:27 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | LPA City of O'Fallon I-70 at Bryan Road |  | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [6 empty] | no funds yet | 2021-09-29 07:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3232 J9S3232B | S701051/S703077 | J9S3232 & J9S3232B | Bootheel Bridge Bundle Design-Build | VARIOUS |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Environmental and Stakeholders;#Corporate Actions;#Local Considerations | Bundle Bridge project in rural area | Design Build Certification;#Design Build Procurement;#Design Build AAS Concur;#Design Exception Approval | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval |  | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America |  |  | Provided guidance on the Design-Build process. |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 & JP3496B | S502067 S502089 | J6P3496 & JP3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member | [7 empty] | 2021-09-29 07:29 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 |  | J9S3381 | Bridge replacement over Black River. Project involves bridge K0263. | Butler |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Schedule;#Environmental and Stakeholders;#Local Considerations | [9 empty] | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5640613 | 5640613 City of St. Peters | City of St. Peters Jungermann Road Bridge over branch of Spencer Creek, replace culverts (23077 & 23079) - 6563-15 | St. Charles County |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Schedule;#Project Administration;#Local Considerations | LPA project, utility related time extension and problematic contractor |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY 2021 Reviewed 3 change orders. Multiple discussions held on time extensions, LDs, and possible claim along with the format and eligibility of the change orders. 2 of the change orders were approved. The LPA has needed a lot of direction since this project had huge impacts to schedule and budget due to utilities. LP- CUF has been conduted for XL Contracting. No OJT hours on project. FY 2022 |  | 2021-09-25 09:41 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#PY20;#FY20;#FY22 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2021-09-25 10:16 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526 | 0552121 | J6I3526 | Scoping for corridor improvements along the I-55 corridor from 0.5 mile north of Rte. Z to 1 mile south of Rte. 67. Potential Design-Build project. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | not assigned | 696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:14 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | n/a | 5417604 5417605 | 5417604 & 5417605 LPA City of St. Louis Jefferson/22nd Improvements | LPA City of St. Louis Jefferson/22nd Improvements | St. Louis City |  | Resurfacing | Perkins, Dawn (FHWA);#35;#Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Project Administration;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Design Exception Approval;#Design Preliminary Plans;#Design 90% Review |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Buy America;#Civil Rights/Cert Payroll;#Title VI |  |  | FY 2021 90% final plan package reviewed and multiple comments submitted including Buy America, proprietary items, traffic control, etc. No Design Exceptions have been submitted and none are expected. Most of the comments from the preliminary plan review were addressed. Project was giving conditional PS&E approval and FMIS authorization/obligation with a long list of conditions. MoDOT is monitoring the conditions. FY 2022 |  | 2021-09-29 16:02 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NA | NA | Pedestrian and Bikeways Improvements | Connect existing bikeways on 11th street and 12th street (Kansas City) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | TRUE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | No FMIS ACTION to-date. KC District staff indicate that this project will be authorized and funds obligated in the early Spring (2022). |  | 2021-09-27 13:25 | McMahon, Bradley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3359 | 0444204 | J6I3359 | Scoping for pedestrian studies at Selma Avenue Overpass and I-55 at Daycare Overpass. Project involves pedestrian bridges A1729 and A0619. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#Environmental Commitments | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | Project Authorization and Project Agreements;#Project Planning & Programming;#Project Financing;#Special Funding;#FMIS Authorization |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added: Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted. MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. Reviewed the consultant solicitation document issued by MoDOT. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J6P3510 | not assigned | J6P3510 | Scoping for ADA Transition Plan improvements at various locations in the St. Louis District. Potential DesignBuild project. | Various |  | ADA/Sidewalk | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | Not assigned | N/A | I-29 near Ambassador Drive, Permit Project | Potential Permit Project near KCI Airport at I-29 and Route D interchange near Ambassador Drive. | Platte |  | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE |  | Local Considerations;#Other | Proposed Dogbone Roundabout interchange at I-29 and Rt. D with connection to a development property. | TSandO Approval |  | Meetings and Review and approval of a TS&O report. | [5 empty] | 2021-09-23 14:59 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 | Scoping for interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#AJR Approval;#Design Exception Approval | [6 empty] | System to System Interchange / EIS reval | 2021-09-29 07:33 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
|  |  | J2P3347 | [5 empty] | No | TRUE | [11 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3661 | not assigned | J6P3661 | Scoping for corridor improvements from Rte. 100 to I-44. Project involves various bridges | Franklin |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | Scoping for capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans

## SL
State | State Number | FMIS Number | Title | Project Description | County | Letting Date | Type of Improvement | FHWA POC | Project Completed | Still a PODI | FY | Risk | Risk Description | Preconstruction Activities | Preconstruction Activities Completed | Preconstruction Activities Description | Construction Activities | Construction Activities Completed | Construction Activities Description | Value Added | Additional_Info | Modified | Modified By | Item Type | Path
MO | 2700509 | 2700509 | 2700509 - City of Fulton AID Demonstration | Bridge Replacement on 2nd ST Bridge over Stinson Creek and Stinson Creek Greenway, Bridge No. 1555011 located on State Route O in the City of Fulton. Accelerated Innovation Deployment (AID Demonstration program) | Callaway |  | Bridge Replacement | Pursley, Charles (FHWA);#37;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Discretionary Grant and Financing;#Project Administration;#Program Involvement Findings |  | Design Preliminary Plans;#Design 90% Review;#Special Funding;#Differing Eligibilities Review |  |  | Work Zone/TMP;#Bridge Inspection |  |  |  |  | 2021-09-29 08:05 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 4300112 | 4300112 | South Main Corridor Improvement-BUILD Grant project | Reconstruction and realignment of South Main Corridor in the City of Maryville, MO from Highway 71 to South Avenue | Nodaway | 2021-08-12 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Funding;#Project Administration | Large BUILD funded project administered by an LPA using a consultant for construction engineering. |  | Design PSandE Review;#Design PSandE Approval;#Environmental Commitments;#Core Team Member;#Design Preliminary Plans;#Other |  | Construction Inspections;#Erosion Control;#Civil Rights/Cert Payroll;#Work Zone/TMP;#Buy America |  | Construction inspections with focused review checklists. | FY 20 and FY 21: Facilitated the City's POC's access to the RADS reporting system and provided guidance on what to include in report and how to submit. Their first quarterly report was submitted by 10/20/20. Continue to submit monthly reports on the project, a total of 7 monthly reports have been submitted through April 30, 2021. Remind City and assure quarterly reports are submitted. File copy in project file. Keep in close contact with the project team to get status updates on progress towards advertising and awarding the project. Facilitated discussions with MoDOT, the City and FHWA to approve a revised conditional clearance to allow the project to be advertised on 2/8/21 with a letting date of 3/17/21. The project bid results were significantly more than the engineer's estimate. FHWA worked with MoDOT and the City to explore options on how to move forward with the project, given the high bids received. A meeting was held on 3/18/21 to discuss this. Revised project scope white paper and red-lined addendum coordinated with City/MoDOT and submitted to HQ. Reviewed revised final PS&E and offered comments that will require changes to the PS&E. Continue to provide AEM major project updates, update quarterly briefing article. Coordinated the submittal of Amendment 1 of the BUILD Grant agreement and obtained approval from OST. Coordinated the submittal of the Amendment for Bid Award and submitted it to HQ. Submitted all monthly BUILD reports as required. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I0624 | 0704203 | J6I0624 | Road realignment from Wentzville Parkway to I-64/Rte. 61. Project involves bridges A4320 and A4323. | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Other;#Program Involvement Findings |  | Core Team Member;#AJR Approval;#TSandO Approval;#Design Exception Approval;#Differing Eligibilities Review | [6 empty] | VE Study scheduled / OINCC submittal / Major Project | 2021-09-29 17:00 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5901816 | 5901816 | 5901816 - Grant Avenue Connector Parkway in Springfield | The project will reconstruct approximately 3.3 miles of a multi-use bicycle and pedestrian path on Grant Avenue starting in Downtown Springfield, ending at Sunshine Street, including advisory bike lanes, a roundabout, two raised intersections, three protected intersections, a grade-separated crossing at Fassnight Creek, bridge enhancement, utility upgrades, fiber connectivity, and additional crossing and signal timing improvements. | Greene | 2021-06-01 | Reconstruction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Environmental and Stakeholders;#Funding;#Project Administration;#Program Involvement Findings |  | Design Build Procurement;#Environmental Commitments;#Design Preliminary Plans;#Design Build Certification | Design Build Procurement;#Design Build Certification |  | Environmental Commitments;#Special Funding;#Construction Inspections;#Title VI |  |  | The project concepts have been developed to account for public input. The city has initiated the DB process and selected 2 teams. I reviewed and approved the RFQ. I reviewed and approved the RFP. The city is currently conducting the 1 on 1 meetings with the DB teams. I reviewed and commented on the CE2 documentation. The city has provided me with a project status update for the BUILD reporting at a meeting held every 2 weeks. I have spent a lot of time working on the BUILD grant agreement and trying to get it approved by HQ. I have expended a lot of effort in getting the grant agreement drafted. It is nearing completion and should be ready for execution soon. |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 5903803 | 5903803 | 5903803 - Jefferson Avenue Foot Bridge Over BNSF Railroad in Springfield | Rehabilitate the Jefferson Avenue foot bridge and provide ADA access | Greene | 2021-11-01 | Bridge Rehabilitation | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Project Administration;#Program Involvement Findings |  | Design PSandE Review | Design PSandE Review |  | Construction Inspections;#Buy America;#Title VI |  |  |  |  | 2021-09-29 15:55 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3053 | 2292133 | I-229 Environmental Study | Environmental study between Rt. 59 (St. Joseph Ave.) and Rt. 36, including the elevated bridge in downtown St. Joseph. Project involves twin bridge A2225. | Buchanan | 2025-05-30 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Urgency;#Environmental & Stakeholders;#Project Administration;#National/Regional Significance;#Schedule;#Local Considerations | This project is of regional significance due to the access it provides to the St. Joseph, MO area. The project may include an Interstate De-designation of I-229. This will likely be the NW District's first Design-Build project. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Design Build Procurement;#AJR Approval;#Bridge 90% Review;#Interstate Designation Request |  | AJR (if required), Bridge and Roadway 90% plans, Interstate De-designation, Funding review, T&E review, NEPA EA review/approval, Design-Build procurement |  |  |  | FHWA has been closely involved in the development of the NEPA EA document. There have been multiple team meetings where FHWA has provided requested input on the selection of alternatives to be analyzed in the EA and are helping resolve a conflict between the MPO and MoDOT in what alternatives to move forward in the analysis. Guidance has also been provided to MoDOT on both the process for Interstate de-designation and whether an AJR would be necessary. |  | 2021-09-20 17:44 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3029 | 0444188 | J6I3029 I-44 at I-270 and Meramec River Bridge |  | St. Louis |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | FALSE | FY21;#FY20;#PY19 | [8 empty] | FY 2021 Reviewed and approved 5 change orders with no issues. LP-CUF Reviews still need to be performed for DW Mertzke,Petro legistics, and Prestige truking. Project ending 2/2022. |  | 2021-09-24 10:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3109 | N/A | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. | Replace bridges on I-29 over Hopkins Creek, 0.2 miles south of Rt. T near Amazonia. Project involves twin bridges A1293 in the NB and SB lanes. | Andrew |  | Bridge Replacement | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Schedule;#Project Administration;#Local Considerations;#Program Involvement Findings | Complexity: Likely to include head to head traffic on Interstate. Schedule: Scheduled bridge work has risk of delayed completion. Local considerations: Work Zone complexity will significantly impact traffic. | Contract Administration;#Construction Inspection & Quality |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Title VI |  | Construction inspections to include a bridge inspection and construction inspection using focused review checklists. | Due to Covid-19 travel restrictions, no construction inspections were performed on this project. No PoDI activity occurred during PY21. The project is nearly completed so this project will not be retained as a PoDI in FY 22. |  | 2021-09-29 15:32 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3110 | 0292195 | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Bridge rehabilitation over the Nishnabotna River, 1 mile south of the Iowa State line. Involves twin bridges A2369. | Atchison | 2020-03-20 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental & Stakeholders;#Funding | Construction inspection to include focused review checklists and a bridge inspection. |  |  | Construction inspection to include focused review checklists and a bridge inspection.. | Construction Inspections;#Work Zone/TMP;#Buy America;#Erosion Control;#Bridge Inspection |  | Construction inspection to include focused review checklists and a bridge inspection. | FY 21: The project has been awarded and construction started in the Spring of 2021. No PoDI activity was performed due to the COVID pandemic travel restrictions. The project has been retained as a construction PoDI for FY 22. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1P3378 | not assigned | Rt. 136 Flood Resiliency Permanent Repair | Flood Resiliency Permanent Repair from Mo. River to I-29 near Rock Port. Atchison County | Atchison | 2022-04-15 | Reconstruction | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Local Considerations;#Funding | ER funded flood resiliency project. | Design 90% Review |  | Review of 90% Plans and compare to approved DDIR. |  |  |  | FY21: Reviewed resiliency proposal and DDIR and had multiple meetings to discuss the benefit/cost analysis expectations. Approved DDIR and resiliency proposal. |  | 2021-09-23 14:46 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1S3392 | S102024 | J1S3392 East Locust Creek Reservoir BUILD project | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Route: Various Rtes. 5, N, VV and RA near Milan | Sullivan | 2022-02-25 | Pavement and Bridge | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations | This project has a very tight project delivery schedule and the project BUILD grant funds must be obligated by September 30, 2022. The project must be coordinated with the separate East Locust Creek Reservoir project, which has experienced significant delays to their schedule. | Final Design;#Plan, Specification, & Estimate Development;#Advertising & Award;#Core Team Member;#Special Funding | Design Preliminary Plans;#Conceptual Report Review;#Environmental Commitments | Final PS&E approval, BUILD Grant review and approval coordination, Project bi-weekly and monthly reporting. | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Environmental Commitments;#Buy America |  | Construction inspections, focused review checklists. | Continue to submit bi-weekly reports as required. Continued coordination with MoDOT on weekly basis to share information and remain apprised of project progress. Coordination with HQ on significant issues including increasing AC amount and ROW acquisition. Coordinated several meetings including ROW, Finance, and Environmental specialists to help resolve issues to advance project. Recently attended 3 core team meetings and offered significant guidance to MoDOT during meetings. Starting to populate grant agreement and will continue. Assisted MoDOT with development/submittal/approval of a white paper to allow for the possible extension of the BUILD 19 obligation. Coordinate multiple reviews and revisions for a white paper to request OST approval of scope changes. Continued to provide MoDOT with guidance and recommendations on how to approach the development of the white papers and grant agreement. The White papers for a BUILD 19 obligation date extension and for identified scope/schedule changes were submitted to HQ for review on February 19th and March 12th respectively. The draft white paper for scope modification was submitted to Alison Rogers during the week of April 16th and received approval in July, 2021. Coordinated the review and approval of an increase in AC for MoDOT to cover increased design costs. |  | 2021-09-20 18:06 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3274 | Not Assigned | J2I3274 | Scoping to add railroad overpass 1.4 miles east of Rte. F near High Hill. Project involves bridge L0637. | MONTGOMERY |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3309 | 0703276 | J2I3309 | Pavement improvements from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | MONTGOMERY |  | Pavement Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | National/Regional Significance |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3310 | 0703286 | J2I3310 | Pavement resurfacing from the Callaway County line to 2 miles east of Rte. F near High Hill. | MONTGOMERY |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#Design Preliminary Plans | Conceptual Report Review |  | Construction Inspections;#Work Zone/TMP;#Pavement/Materials Review;#Civil Rights/Cert Payroll |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3400 | Not Assigned | J2I3400 | Scoping for interchange improvements at Stracks Church County Road near Wright City. | WARREN |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3043 | 0471083 | J2P3043 | Interchange improvements at Rte. 61 in Troy. Project involves bridge A2604. | LINCOLN |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Conceptual Report Review | [7 empty] | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2S3221 J2P3222 J2P3 | S201034 / 13620 | J2S3221 / J2P3222 / J2P3224 |  | SCHUYLER |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-29 07:27 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3090 | 0194019 | J2P3090 | Interchange improvements over I-70 near New Florence. Project involves bridge A0986. $807,000 Open Container and $443,195 private developer funds. | MONTGOMERY |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  |  | Core Team Member;#Conceptual Report Review;#Design Exception Approval;#AJR Approval |  | Title VI |  |  |  |  | 2021-09-29 15:37 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2I3226 J2I3226B | 0703279 | Rte. I-70, Mineola Hill Truck Climbing Lanes |  | Montgomery | 2021-07-01 | Reconstruction | Pursley, Charles (FHWA);#37 | Yes | FALSE | FY21 | [8 empty] | Project is under construction. I have attended a weekly project status update meeting to track the project progress through construction. Weekly meetings have not been held since December 2020. I have not approved any change orders or VECPs since October 1. Those activities were complete last PY. The final quarterly project QC/QMmeeting was held on June 23, 2021. I atended as well as the Paement and Materiasl Specialist. |  | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3156 | 0544065 | J2P3156 | Add roundabout at Rte. 19 north junction (Basinger Corner) north of Laddonia. $2,346,000 Open Container funds. | Audrain |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Urgency;#Environmental and Stakeholders |  |  |  |  | Construction Inspections |  |  |  |  | 2021-09-23 13:18 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3259 | 0614179 | J2P3259 | Pavement resurfacing on northbound lanes from Rte. V to 0.4 mile south of Rte. UU in Pike County near Bowling Green. | Lincoln |  | Resurfacing | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity |  |  |  |  | Construction Inspections;#Civil Rights/Cert Payroll;#Pavement/Materials Review |  |  |  |  | 2021-09-23 14:25 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3357 | 0791082 | J2P3357 | Bridge replacement over Lyon Street, Warren Barrett Drive, Burlington Northern Santa Fe Railroad and Bear Creek 0.4 mile north of Rte. T in Hannibal. | MARION |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Program Involvement Findings |  | Core Team Member;#Design Preliminary Plans;#Differing Eligibilities Review |  |  | Title VI |  |  |  |  | 2021-09-29 15:34 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J2P3447 | Not Assigned | J2P3447 | Scoping for roadway improvement between Bus. 54 and Rte. 79 in Louisiana. | Audrain |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member | [7 empty] | 2021-09-23 14:12 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900391 | 9900391 | TAP 9900 (391) LPA: NE District - CONSTRUCTION |  | TROY |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I1486D | not assigned | I-70 Corridor Improvements | Corridor Improvements along I-70 from the Paseo to I-435 (Potential Design-Build project). | Jackson |  | Corridor improvements | Irving, Kevin (FHWA);#29 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations;#Cost;#Program Involvement Findings | I-70 corridor impacts will be significant. Interstate access report that was previously approved will be updated. Potential large D-B project along a very congested corridor of I-70. | AJR Approval |  | The previously approved AJR will be reevaluated and updated. Title VI review. | [5 empty] | 2021-09-29 15:56 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I2006 | 0351291 | Add interchange south of Rte. 92 at 19th Street in Kearney. | New Interchange on I-35 at Kearney | Clay | 2022-02-25 | New Construction | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21 | Complexity;#Local Considerations;#National/Regional Significance;#Program Involvement Findings | New interchange construction with a Diverging Diamond interchange configuration and new bridge. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | Work Zone/TMP;#Title VI |  | Construction inspection to include focused review checklists. A bridge inspection will also be performed. | The project has been delayed due to ROW acquisition delays, therefore no construction activities have been performed. The project is expected to be let in early 2022. Significant utility relocation is required before construction begins so the main construction will likely occur in FY23. Will consider including as a PoDI during FY23. |  | 2021-09-29 15:29 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3024 J4I3024B | N/A | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Bridge Replacement and modify interchange configuration at Blue Ridge Boulevard/US 40 in Independence | Jackson | 2023-06-30 | Interchange | Irving, Kevin (FHWA);#29;#Moeller, Sandra (FHWA);#36 | No | TRUE | FY21 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations;#Program Involvement Findings | Interchange modification could require an AJR and design exceptions. Significant traffic control impacts to I-70 are likely. | Environmental Clearances/NEPA;#Design 90% Review;#AJR Approval;#Design Exception Approval;#Differing Eligibilities Review |  | Core team member. NEPA review and approval. AJR or Traffic Safety and Operational Analysis will likely be required. 90% Plans review and design exception approval. |  |  |  | FHWA has participated in 3 core team meetings and have offered feedback on the level of documentation and analysis needed for multiple interchange configurations. A separate meeting with the HQ Major project specialist was held to confirm that this project was not considered a Major Project as defined by FHWA and will not need a FP nor Major Project Plan. This information was shared with MoDOT. |  | 2021-09-29 08:11 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4I3189 | 4351323 | I-435 Bridge over the Missouri River in Kansas City, MO | Bridge deck replacement at the Missouri River. Project involves twin bridges A0767. | Clay | 2019-05-17 | Bridge Rehabilitation | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Other;#Urgency;#Complexity;#Local Considerations;#Program Involvement Findings | Schedule: Work zone impacts will be significant and will require expedited construction. Local Consideration: Work zone impacts will be regionally significant. |  |  | Construction inspection to include focused checklist for Work Zone Traffic Control. | Work Zone/TMP;#Title VI |  | Construction inspections to include a focused checklist for Work Zone Traffic Control. | FY 21: Due to Covid-19 travel restrictions, no construction inspections were performed on this project. There has been no PoDI involvement this performance year. The project is scheduled to be completed at the end of 2021 and it will be retained as a PoDI project to include a work zone traffic control review. |  | 2021-09-29 16:08 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4P2237 | S300097 | J4P2237- I-49 Outer Roads Conversion to from One-way to Two-way | Conversion of the outer roads of I-49 to two-way traffic on the east outer road from Rt. 150 to Blue Ridge Boulevard and on the west outer road from Blue Ridge Boulevard to 0.5 miles north of Rt. 150 in Grandview. | Jackson | 2023-09-30 |  | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Project Administration;#Local Considerations;#Program Involvement Findings | Large complex local project using the Design-Build delivery method with limited experience by City staff. ROW and Utility impacts that could impace schedule. Complex traffic control during construction with significant traffic impacts on the local and interstate highways. | Environmental Clearances/NEPA;#Innovative Contracting/Design Build;#Contract Administration;#Other | Environmental Commitments;#AJR Approval;#Design Build AAS Concur;#Design Build Certification;#Design Build Procurement;#FMIS Authorization |  | Title VI;#Work Zone/TMP |  | Construction inspections. Focused Reviews on Title VI and Work Zone Traffic Control. FHWA will continue to provide feedback on proposed revisions to the approved AJR and will coordinate with MoDOT and the City on these changes and any required approval. | Reviewed all books of Draft RFP and provided comments on Books 1 and 2, and ITP. • During the confidential one-one-one meetings, I coordinated review of potential AJR deviations with Division staff and leadership. Reviewed proposed TS&O reports and offered feedback and concerns to MoDOT on all three teams’ draft submittals. • Worked with Mike Landvik and Jim Stevenson to develop a draft LPA Design-Build checklist template for use on future LPA Design-Build projects. • Provided recommendations on how to structure the RFP documents when these were in the early stages of development. Assured that federal requirements were conveyed and followed. • Coordinated involvement on an ADA concern from both Civil Rights and Environmental staff members from MoDOT and FHWA to assure that the decision by the City to modify the sidewalk requirements in the RFP did not violate NEPA and/or ADA requirements. • Reviewed and approved the final RFP for release and facilitated the FMIS construction authorization. This took quite a bit of time since the process for approval was different than traditional D-B-B project authorizations. I provided guidance on the RFP certification letter and what needed to be included in the submittal. MoDOT and the City were very appreciative of this guidance and involvement. • Reviewed the proposals and participated in the proposal evaluation process and offered feedback on how FHWA could concur in the project award. Concurred in project award. Reviewed proposed AJR changes and offered valuable feedback. Coordinated a meeting to convey FHWA expectations on the criteria for acceptance of a proposed AJR revision involving a proposed roundabout in lieu of the approved configuration.s expectation |  | 2021-09-29 15:57 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 9900086 | 9900086 | TAP 9900(086) LPA: NE District - CONSTRUCTION |  | CITY OF EAST PRAIRIE |  |  | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY21 | [10 empty] | 2021-09-21 18:52 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3085 | 1691104 | Buck O'Neil Bridge improvements over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 mile north of I-70. | Buck O'Neil BUILD Grant Project: Bridge replacement over the Missouri River, 3.1 miles south of Rt. 9 and 0.1 miles north of I-70. Project involves bridges A4649 and A4646. Design-Build project. | Jackson | 2020-09-01 | Bridge Replacement | Irving, Kevin (FHWA);#29;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#PY20;#PY19 | Complexity;#Cost;#Schedule;#Urgency;#Environmental & Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Corporate Action;#Local Considerations;#Program Involvement Findings | BUILD funded project. Design-Build procurement on an aggressive timeline for project delivery and completion. Major project for MoDOT and local area. | Innovative Contracting/Design Build;#Contract Administration;#Construction Inspection & Quality;#Other;#Core Team Member;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance | Core Team Member;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval;#Environmental Commitments;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization;#Conditional Clearance;#Scoping;#Special Funding;#Bridge TSandL |  | Change Order Approval;#Work Zone/TMP;#Civil Rights/Cert Payroll;#Erosion Control;#DBE Goals;#Buy America;#Title VI |  | Design-Build procurement coordination, Design exception review, AJR addendum review, Construction inspections including focused review checklists. An ADA review will be completed as well. | PY 21: Participated in several one-on-one meetings with short listed proposers and offered feedback to MoDOT on AJR modification considerations. Reviewed and approved AAS's, Design Exceptions and 11 RFP addendums. Continue to submit BUILD monthly reports as required. As of 4/30/21 a total of 7 monthly reports have been submitted. Observed scoring of proposals and offered feedback to MoDOT. Attended the presentation of the apparent best value proposal to the MoDOT Executive Management team on 2/1/21. Facilitated the process for MoDOT to access RADS reporting system so they can submit their quarterly reports and also provided guidance on filling in the report items. Continue to assure quarterly reports are submitted. Provided a concurrence in award of the project to MoDOT on 2/9/21. Provided AJR addendum guidance via TEAMS meeting and email. Coordinated with Project Director multiple times to keep apprised of project updates and planned design/construction. Coordinated the review of TS&L Bridge Plans. Continue to update Division Office at AEM's for Major Projects. Updated INPUT multiple times. Provided project update for quarterly briefings. Provided schedule to Kevin Ward and Rick Swanlund for their presentation to ITE. Reviewed and provided comments to revised project AJR and issued approval. Submitted all required monthly project reports through September, 2021. Visited the project office and participated in a meeting offering feedback to the project Quality Oversight Plan in coordination with the Division Office Pavement and Materials Engineer. |  | 2021-09-29 15:58 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3358 | 0703275 | 5I3358 - Rte. I-70 Rocheport Bridge Replacement | Bridge replacement over the Missouri River near Rocheport. Design-Build. Project Route: IS 70 involves bridge L0962 | Cooper and Boone | 2021-07-01 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Funding;#Environmental & Stakeholders;#National/Regional Significance |  | Project Authorization and Project Agreements;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP;#Environmental Commitments |  |  | FY 2021-The DB team has developed all DB documents and issued the RFP. I have reviewed and approved all documents and books in the ITP, RFQ and RFP as well as all addendums. I observed the scoring of proposals and interviews.MoDOT is conducted 1 on 1 meetings with the DB teams. I attended several of these meetings. I reviewed, commented and approved AASs and Design Exceptions as they weresubmitted.A contract was awarded to the best value DB proposing team. I have attend the project design meetings and provide input on appropriate items. |  | 2021-09-27 15:19 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5I3397,J5I3572, | 0443208 | 5I3397, 5I3572 and 5I3482 - I-44 Phelps and Crawford Co. | Pavement Rehabilitation, Pavement Replacement and Bridge Replacement | Phelps | 2021-11-19 | Pavement Rehabilitation | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Schedule;#Local Considerations | Project requested by MoDOT due to accelerated PS&E delivery schedule. | Design PSandE Review |  |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:22 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | B015001 | B015001 | Camden Co. Bridge Replacement on Willow Creek Road |  | Camden |  |  | Pursley, Charles (FHWA);#37 | No | FALSE | FY21 | [8 empty] | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3369 | S402035 | 5S3369 - Central District ADA Improvements - Alternate Project Delivery Method | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address Route: Various nonstandard ADA facilities at various locations in the Central and Northwest Districts. | Various | 2021-11-01 | ADA/Sidewalk | Pursley, Charles (FHWA);#37 | No | TRUE | FY21;#FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build Certification;#Design Build AAS Concur | Design Build Procurement;#Design Build Certification |  | Construction Inspections;#Work Zone/TMP;#ADA |  |  | FY2021-The DB team spent a lot of time refining the project scope. I attended several core team meetings and provided a lot of guidance and advice on the DB process as well as NEPA compliance. The RFQ has been developed and the RFP is being finalized. I reviewed these document and provided input and guidance. FY2022 - |  | 2021-09-27 15:26 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5P3337 | 0543193 | Missouri River Bridge in Jefferson Cit | Bridge rehabilitation over Missouri River. Project involves bridges A4497 and L0550. | Cole, Callaway |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Complexity;#Schedule;#National/Regional Significance;#Local Considerations | [9 empty] | 2021-09-28 20:20 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J5S3269 | S401083 | J5S3269 | Pave Resurfacing from Bus 44 to Rt J, Includes Pave Inprove on Rt H from Rt 17 to End of State Maintenance | Pulaski |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3296 | 0171015 | J9P3296 - Program Development | Pavement Improvements from Route 106 in Summersville to Route 160 Near West Plains, 34.064 miles | TEXAS |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 3219702 | 3219702 | 3219702 | Design to Replace Old Dilapidated Sidewalks Along Main from 15th to 11 St | Jasper |  |  | Moeller, Sandra (FHWA);#36 | No | FALSE | FY21 | Funding | [9 empty] | 2021-09-28 20:19 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2090 | 2705360 | J6I2090 | Bridge replacement, bridge rehabilitation and pavement repair over Conway Road and New Ballas Road and bridge rehabilitation for I-270 mainline and ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052, A4654, A4657, A4580 and A4581. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#National/Regional Significance;#Local Considerations |  | Core Team Member;#TSandO Approval;#Design Exception Approval;#Design Preliminary Plans |  |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:01 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2222 | 0641061 | J6I2222 I-64 at 22nd and Jefferson | Modify interchange configuration between 18th Street and Garrison Avenue. Project involves bridges A1523, A1501, A1528, A0840, and A0838. $7,900,000 Cost Share and $7,900,000 Land Clearance for Redevelopment Authority funds. | St. Louis City | 2020-05-15 | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Schedule;#Cost;#Urgency;#Environmental & Stakeholders;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 7 change orders with no comments. Reviewed and approved 2 VECP with no comments. The VECPs were previously discussed in the PAVE that was held after award and before NTP. LP-Project has 3 trainee spots of 1000 hours each. Prime says they will not use trainees until summer 2021. Project is scheduled to be completed 6/2022. CUF still needed for D&K Welding. FY 2022 |  | 2021-09-29 17:02 | Moeller, Sandra (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I2418 & J6S3520 | 0704190 | J6I2418 & J6S3520 | I-70 at Rte. K Phase 1 and Phase 2 (LPA Cost Share) | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Local Considerations |  | Core Team Member | Core Team Member |  | Construction Inspections;#Work Zone/TMP |  |  |  |  | 2021-09-29 07:13 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 Rte N EA | Scoping for environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | New Construction | Peters, Taylor (FHWA);#43 | No | FALSE | FY21 | Environmental & Stakeholders |  | EA/EIS Public Involvement | EA/EIS Public Involvement | [6 empty] | 2021-09-29 07:32 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020B | 2705352 | J6I3020B I-270 North Corridor (Major Project) | Pavement, bridge and upgrade pedestrian facilities to comply with ADA Transition Plan. on the I-270 North Corridor on disconnected sections in North County. Design-Build | St. Louis |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Complexity;#Cost;#National/Regional Significance;#Environmental & Stakeholders;#Schedule;#Funding;#Urgency;#Local Considerations;#Corporate Action;#Major Project |  | Bridge 90% Review;#Design Exception Approval;#Design 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization | Design 90% Review;#Design Exception Approval;#Bridge 90% Review;#Core Team Member;#AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#FMIS Authorization |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 Reviewed and approved multiple change orders. Comments focused on including independent cost estimate. QMP and revisions reviewed and approved. Attended Quarterly Quality meetings and shared suggestions to improve the quarterly reports. Attending weekly progress meetings to stay informed on ROW, design, and construction issues. Many preliminary plan and final plan packages reviewed with multiple comments on consistency, traffic control, and ADA. 15 Design Exceptions reviewed and comments provided on improving safety analysis and overall content. DE's were revised and resubmitted for approval. LP-CUF's have been completed for 6 professional DBE's and 3 construction DBE's. Project is scheduled to be completed 12/2023. The is time to complete CUF's. The project has an OJT goal of 2 professional service trainees and 6 construction trainees, each trainee is 1000 hours. Documentation has been submitted for at least 6 OJT trainees. |  | 2021-09-28 10:36 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020C | 2705359 | J6I3020C I-270 North at Riverview (Major Project) | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | St. Louis |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Major Project;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [5 empty] | FY 2021 Reviewed and approved the preliminary plan submittal with 3 comments on verbiage, NEPA approval, and format. No Design Exceptions have been submitted. The AJR Re-Evaluation was reviewed and approved after comments were addressed. EA Re-evaluation was reviewed and approved after comments were addressed. Attending regular team meetings to stay informed on the design and the IDOT/IL Div Chain of Rocks Bridge coordination. FY 2022 |  | 2021-09-29 06:44 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3020D | 2705370 | J6I3020D I-270 North Corridor (Major Project) | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations |  | Core Team Member;#Environmental Commitments | [6 empty] | Part of I-270 North Major project / EA reval | 2021-09-29 07:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3201 | 4952604 | J6I3201 LPA David Hoekel Parkway I-70 Interchange Phase 1 and Phase 2 | Payment to Wentzville for adding interchange west of Point Prairie Road. $5,000,000 Cost Share funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Environmental and Stakeholders;#Funding;#Project Administration;#National/Regional Significance;#Local Considerations |  |  |  |  | Change Order Approval;#VECP Approval |  |  | FY 2021 Reviewed and approved 8 change orders with no issues. No VECP's have been submitted and none are expected. LP- A CUF review is need for Columbia Curb and Gutter. Project has an OJT Goal of 1 trainee for 1000 hours. Contractor says they are looking for a trainee to use summer 2021. Project closing is delayed until 11/2021. FY 2022 |  | 2021-09-29 06:50 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J1I3233 | not assigned | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371) | Pavement resurfacing from the I-29 interchange, north of St. Joseph, to 22nd Street (Rte. 371). Excludes bridge along Missouri River in St. Joseph. | Andrew | 2020-06-19 | Resurfacing | Irving, Kevin (FHWA);#29 | Yes | FALSE | FY21 | Complexity;#Schedule;#Local Considerations | Contract Administration. Pavement and materials quality. | Contract Administration;#Construction Inspection & Quality |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. |  |  | Construction inspection to include focused review checklists. A pavement/materials review will also be conducted by the Division pavement/materials specialist. | Due to Covid-19 travel restrictions, construction inspections could not be performed on this project. There were no project actions on this project during FY 21. The project has been completed and therefore will not be carried over as a PoDI in FY 22. |  | 2021-09-21 18:57 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3337 | S502015 | J6I3337 I-70 from Cave Springs to Fairgrounds Design-Build | Corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl & Cave Springs & modify interchange at First Capitol. Design-Build. Bridges A3852,A4040,A6678,A6679,A6680. $2.1M CMAQ,$2.5M Cost Share & $17.5M St. Charles County funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | AJR Approval;#Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval;#Core Team Member;#Design Preliminary Plans;#ATC;#FMIS Authorization;#CMAQ Project Review;#Design 90% Review | AJR Approval;#Design Build Certification;#FMIS Authorization;#CMAQ Project Review;#Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America;#Pavement/Materials Review;#Quality Control;#Bridge Inspection;#Title VI |  |  | FY 2021 AJR draft has been reviewed and comments provided. The AJR presentation was held virtually. Attending weekly meetings (sometimes 2 times a week) to discuss the AJR and direction of the project. The draft RFP Book 1 and 2 and ITP were reviewed and comments provided. Due to public meeting and public comments the schedule has been pushed so RPF release won't be until later FY2021. No Design Exceptions have been submitted yet. A lot of direction has been provided to MoDOT regarding the public opinion, AJR, and possible changes to the project. Conceptual AJR approval completed. FY 2022 |  | 2021-09-29 15:59 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3413 & J6I3500 | 2553052 &255305 | J6I3413 & J6I3500 | Bridge rehabilitation at Mississippi River (Jefferson Barracks Bridge). $15,500,000 IDOT funds. Bridge rehabilitation at Koch Road. | St. Louis |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Cost;#Urgency;#Environmental and Stakeholders;#National/Regional Significance |  | Core Team Member;#Design Preliminary Plans;#Other;#Design PSandE Review | Core Team Member;#Design Preliminary Plans;#Design PSandE Review;#Other |  | Construction Inspections;#Work Zone/TMP;#Bridge Inspection |  |  |  | VE Study | 2021-09-29 06:57 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526B | 0552121 | J6I3526B | Add lanes and bridge rehabilitations from 1.5 miles north of Rte. Z to 1.0 mile south of Rte. 67. Potential Design-Build. Project involves various bridges. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:30 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P2321 J6P2321B | 0471072 0471080 | FY 2014 TIGER VI J6P2321 & J6P2321B: MO-47 - Bridge over Missouri River | FY 2014 TIGER ​Replace bridge over the Missouri River from Rte. 94 to Fifth Street in Washington. Cost share: $500,000 city of Washington, $250,000 Franklin County and $50,000 Warren County. | Franklin | 2016-05-20 | Bridge Replacement | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#PY20;#PY19;#PY18;#PY17;#PY16;#FY22 | Funding;#Other |  |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY2021 The project is substantially complete with aethetic lighting still be completed. Due to COVID restrictions, the subcontractor has not been able to travel. All TIGER funds have been expended. Project is submitting all quarterly reports and performance measure reports on time as required. FY2022 |  | 2021-09-29 06:39 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J4S3167 | 0073024 | Rte. 7 and South Ave. Signalization Improvements | Add a signalized intersection at Rte. 7 intersection sidewalk connections (Blue Springs) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | This project was originally programmed as an LPA project sponsored by the City of Blue Springs with the TIP #625033. It was later combined with a MoDOT sponsored project under the TIP #690490 and MoDOT Job Number 4S3167. FMIS action completed 5/14/21. The integration of the LPA CMAQ project into the MoDOT project was correctly programmed and the FMIS action aligned with the programming actions. . |  | 2021-09-28 19:38 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3418 | S502045 | J6P3418 | Eliminate signal, add through lanes and construct new interchange at Rte. 94/364 and Muegge Road. $4,975,000 Cost Share and $12,727,540 St. Charles funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Schedule;#Environmental and Stakeholders;#National/Regional Significance;#Corporate Actions;#Program Involvement Findings |  | Core Team Member | Core Team Member |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Title VI |  |  |  |  | 2021-09-29 15:53 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | 7302674 | 7302674 | CMAQ - 7302(674) Intersection Improvements | CMAQ - 7302(674) Intersection Improvements - Intersection Improvement, Traffic Signals, Roadway Realignment | St. Charles |  | Reconstruction | McMahon, Bradley (FHWA);#30 | No | FALSE | FY21 | Funding;#Local Considerations |  |  | Design 90% Review | PE work has been completed. ROW authorization in FMIS on 8/14/20 |  |  |  | The project description in the FMIS action and EWG TIP are aligned. A FMIS action on 7/9/21 extended the construction award date by 12 months (July 2022). The EWG FY2022-2025 TIP update to be approved by the EWG in October 2021 reflects the new construction award program year of 2022. |  | 2021-09-28 19:34 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3603 | not assigned | J6P3603 | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:15 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6S3342 | not assigned | J6S3342 | Environmental study from I-64 to Point Prairie Road at Jackson Road in St. Charles County. $1,500,000 St. Charles County. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-28 20:23 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5617602 5617603 | 5617602 & 5617603 LPA City of St. Louis Jefferson/22nd Improvements | FY 2020 BUILD Improve approximately 2 miles of Jefferson Avenue to a Complete Street between Market Street and Natural Bridge Avenue in St. Louis. This project will also improve 20th Street to include new low-stress bicycle facilities between Market Street and St. Louis Avenue. The project also includes signal improvements, pedestrian improvements, and storm water improvements. | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY22 | Cost;#Schedule;#Environmental & Stakeholders;#Funding;#Project Administration;#Corporate Action;#Local Considerations;#Discretionary Grant and Financing;#Urgency |  | Design Preliminary Plans;#Design 90% Review;#Design PSandE Approval | Design Preliminary Plans;#Design 90% Review |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP |  |  | FY 2021 BUILD grant agreement is drafted and coordination with HQ is on-going. BUILD grant agreement is partially executed and awaiting PS&E approval. Attending regular team meetings. Bi-weekly reports are being submitted as required. Preliminary plans were reviewed and comments addressed. 90% PS&E was reviewed and comments submitted. FY 2022 |  | 2021-09-29 06:56 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7I3420 | 0441106 | 7I3420 - I-44 Bridges Rebuild DB Part 2 | DB contract to replace and rehabilitate various bridges along the I-44 corridor | Jasper | 2021-08-26 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations |  | Design Build Procurement;#Design Build AAS Concur;#Design Build Certification | Design Build Certification |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:28 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J7P0601 | 711063 | 7P0601 - Rte. I-49 Missouri Arkansas Connector | Bella Vista Bypass Connection for New I-49 | McDonald | 2021-09-30 | New Construction | Pursley, Charles (FHWA);#37;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Schedule;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Program Involvement Findings | Construction of new interstate section using BUILD funding | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization | Design PSandE Review;#Design Exception Approval;#Environmental Commitments;#ATC;#Special Funding;#FMIS Authorization |  | Environmental Commitments;#Special Funding;#Change Order Approval;#VECP Approval;#Interstate Designation Request;#Title VI | Change Order Approval;#VECP Approval;#Environmental Commitments;#Special Funding |  | FY2021 Project is under construction. I have reviewed and approved 3 VECPs and 10 change orders since October 1. Additional change orders and VECPs were approved last PY.I prepared the final inspection report to document interstate standards. I have assited with preparing the request for acceptance into the Interstate system. FY2022 |  | 2021-09-29 15:31 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J7S3194 | S602025 | 7S3194 - Rte. 86, Taney o. | Bridge replacement over Table Rock Lake. Project involves bridge A0590. | Taney | 2021-11-19 | Bridge Replacement | Pursley, Charles (FHWA);#37 | No | TRUE | FY22 | Project Administration;#Local Considerations | Bridge replacement using ATC | ATC | ATC |  | Construction Inspections;#Bridge Inspection;#Work Zone/TMP |  |  |  |  | 2021-09-27 15:47 | Pursley, Charles (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J8I0445 | 0442293 | Rte. I-44, Webster Co. New Interchange in Marshfield - LPA Administered |  | Webster | 2021-07-27 |  | Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | Yes | TRUE | FY21 | Program Involvement Findings |  |  |  |  | Title VI |  |  | No construction inspection have been conducted due to travel restrictions. |  | 2021-09-29 15:35 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3122 |  | J9P3122 | Bridge replacement over I-55. Project involves bridge A0628. | Cape Girardeau |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Urgency;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Bridge TSandL | [7 empty] | 2021-09-23 13:19 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3239 | 0512037 | J9P3239 | Chester Bridge | Perry | 2022-06-22 | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations | Bridge Replacement - Major Bridge over the Mississippi River | Core Team Member;#Scoping;#Conceptual Report Review;#Design Build Procurement;#Design Build Certification;#Design Build AAS Concur;#Design Exception Approval;#Bridge TSandL;#FMIS Authorization;#Conditional Clearance | [7 empty] | 2021-09-24 09:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3305 |  | J9P3305 | Scoping for bridge improvements over Current River and Round Spring. | SHANNON |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Environmental and Stakeholders;#Local Considerations |  | Core Team Member;#Scoping;#Conceptual Report Review;#Bridge TSandL;#Environmental Commitments | Core Team Member;#Conceptual Report Review;#Bridge TSandL | [6 empty] | 2021-09-23 13:20 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3584 | 0604090 | J9P3584 | Future I-57 and US60; Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds | NEW MADRID |  | Interchange | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Scoping;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:36 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3661 | 0671025 | J9P3661 | Future I-57 Phase 3 Scoping to convert to freeway from 0.5 mile north of Rte. 160 to the Arkansas State line. | BUTLER |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Environmental and Stakeholders;#Funding;#National/Regional Significance |  | Core Team Member;#Scoping;#Conceptual Report Review;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3663 | 0671026 | J9P3663 | Phase 1 - Future I-57and US67; Add lanes and outer roads to upgrade corridor to freeway standards | BUTLER |  | Pavement and Bridge | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Funding;#National/Regional Significance | Improvements to convert US67 to I-57 | AJR Approval;#Design Preliminary Plans;#Conceptual Report Review | Conceptual Report Review;#Design Preliminary Plans;#AJR Approval |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Buy America;#Civil Rights/Cert Payroll |  |  | Provided recommnedation to relocated outerroad to the south to improve safety. Provided guidance on the AJR process. |  | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3751 |  | J9P3751 | Future I-57 Phase 2 Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Environmental and Stakeholders;#Local Considerations;#Urgency;#Cost |  | Core Team Member | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval | [6 empty] | 2021-09-23 13:21 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9P3764 |  | J9P3764 | Future I-57 Phase 1B Add lanes and outer roads to upgrade corridor to freeway standards from County RoadB 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Butler |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY22 | Complexity;#Urgency;#Funding;#Environmental and Stakeholders;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Conceptual Report Review;#Design Preliminary Plans;#AJR Approval;#Design Exception Approval |  |  | Title VI |  |  |  |  | 2021-09-29 15:27 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | LPA City of O'Fallon I-70 at Bryan Road |  | St. Charles |  | Reconstruction | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [6 empty] | no funds yet | 2021-09-29 07:28 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3232 J9S3232B | S701051/S703077 | J9S3232 & J9S3232B | Bootheel Bridge Bundle Design-Build | VARIOUS |  | Bridge Rehabilitation | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#FY22 | Complexity;#Cost;#Environmental and Stakeholders;#Corporate Actions;#Local Considerations | Bundle Bridge project in rural area | Design Build Certification;#Design Build Procurement;#Design Build AAS Concur;#Design Exception Approval | Design Build AAS Concur;#Design Build Procurement;#Design Build Certification;#Design Exception Approval |  | Construction Inspections;#Change Order Approval;#Bridge Inspection;#Work Zone/TMP;#Erosion Control;#Civil Rights/Cert Payroll;#Buy America |  |  | Provided guidance on the Design-Build process. |  | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3496 & JP3496B | S502067 S502089 | J6P3496 & JP3496B | Safety improvements on various locations in the St. Louis District. Potential Design-Build project. $Safety improvements on various routes in St. Louis County. Potential Design-Build project. $2,000,000 St. Louis County.9,391,000 Open Container funds. | St. Louis |  | Safety Improvement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member | [7 empty] | 2021-09-29 07:29 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J9S3381 |  | J9S3381 | Bridge replacement over Black River. Project involves bridge K0263. | Butler |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Schedule;#Environmental and Stakeholders;#Local Considerations | [9 empty] | 2021-09-23 13:22 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5640613 | 5640613 City of St. Peters | City of St. Peters Jungermann Road Bridge over branch of Spencer Creek, replace culverts (23077 & 23079) - 6563-15 | St. Charles |  | Pavement and Bridge | Perkins, Dawn (FHWA);#35 | No | TRUE | FY21;#FY20;#PY19;#FY22 | Schedule;#Project Administration;#Local Considerations | LPA project, utility related time extension and problematic contractor |  |  |  | Change Order Approval;#Final Acceptance |  |  | FY 2021 Reviewed 3 change orders. Multiple discussions held on time extensions, LDs, and possible claim along with the format and eligibility of the change orders. 2 of the change orders were approved. The LPA has needed a lot of direction since this project had huge impacts to schedule and budget due to utilities. LP- CUF has been conduted for XL Contracting. No OJT hours on project. FY 2022 |  | 2021-09-25 09:41 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 7304609 | 7304609 LPA City of Wentzville Wentzville Parkway | LPA City of Wentzville Wentzville Parkway | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY21;#PY20;#FY20;#FY22 | Complexity;#Urgency;#National/Regional Significance;#Local Considerations |  |  |  |  | Work Zone/TMP;#Construction Inspections;#Buy America |  |  | FY 2021 90% final plan package reviewed with multiple comments including JSPs, typicals, traffic control, TMP, signing, etc. Previous comments were addressed. No Design Exceptions have been submitted and none are expected. TS&O was approved after several rounds of comments. |  | 2021-09-25 10:16 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3526 | 0552121 | J6I3526 | Scoping for corridor improvements along the I-55 corridor from 0.5 mile north of Rte. Z to 1 mile south of Rte. 67. Potential Design-Build project. | Jefferson |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Conceptual Report Review;#AJR Approval;#Design Exception Approval | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 0696422 | 0696422 | LPA City of St. Peters Rte 370 and Salt River Road - Phase 1 | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | TRUE | FY22 | Complexity;#Cost;#Environmental and Stakeholders;#National/Regional Significance;#Local Considerations |  | Core Team Member;#AJR Approval;#Design Exception Approval;#Design Preliminary Plans | [7 empty] | 2021-09-29 07:14 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | LPA | 5417604 5417605 | 5417604 & 5417605 LPA City of St. Louis Jefferson/22nd Improvements | LPA City of St. Louis Jefferson/22nd Improvements | St. Louis City |  | Resurfacing | Gonzalez, Felix (FHWA);#27;#Peters, Taylor (FHWA);#43;#Paulwell, Lauren (FHWA);#34 | No | TRUE | FY21;#FY20;#FY22 | Complexity;#Cost;#Schedule;#Urgency;#Project Administration;#Corporate Actions;#Local Considerations;#Program Involvement Findings |  | Core Team Member;#Design Exception Approval;#Design Preliminary Plans;#Design 90% Review |  |  | Construction Inspections;#Change Order Approval;#VECP Approval;#Work Zone/TMP;#Buy America;#Civil Rights/Cert Payroll;#Title VI |  |  | FY 2021 90% final plan package reviewed and multiple comments submitted including Buy America, proprietary items, traffic control, etc. No Design Exceptions have been submitted and none are expected. Most of the comments from the preliminary plan review were addressed. Project was giving conditional PS&E approval and FMIS authorization/obligation with a long list of conditions. MoDOT is monitoring the conditions. FY 2022 |  | 2021-09-29 16:02 | Peters, Taylor (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | NA | NA | Pedestrian and Bikeways Improvements | Connect existing bikeways on 11th street and 12th street (Kansas City) | Jackson |  | ADA/Sidewalk | McMahon, Bradley (FHWA);#30 | No | TRUE | FY21 | Funding;#Local Considerations |  | Project Financing | [5 empty] | No FMIS ACTION to-date. KC District staff indicate that this project will be authorized and funds obligated in the early Spring (2022). |  | 2021-09-27 13:25 | McMahon, Bradley (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3359 | 0444204 | J6I3359 | Scoping for pedestrian studies at Selma Avenue Overpass and I-55 at Daycare Overpass. Project involves pedestrian bridges A1729 and A0619. | St. Louis |  | Bridge Replacement | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#Environmental Commitments | [7 empty] | 2021-09-29 07:30 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | not assigned | not assigned | BUILD FY 2020 I-29/I-35 Corridor Study | ​The project conducts a corridor study of the Interstate 29, Interstate 35, and US 169 corridors that merge directly north of Kansas City’s central business district to document existing conditions, freight impact, and potential solutions to better serve people and goods movement in the northern portion of the Kansas City metropolitan area | Jackson | 2021-10-31 |  | Irving, Kevin (FHWA);#29 | No | TRUE | FY21;#FY22 | Schedule;#Funding;#Corporate Action;#Local Considerations | BUILD funded study will require development of a grant agreement and reporting requirements. | Project Authorization and Project Agreements;#Project Planning & Programming;#Project Financing;#Special Funding;#FMIS Authorization |  | Development of BUILD grant agreement, monitor consultant selection |  |  |  | FY 21 value added: Conducted a congratulatory call to recipient (City of KC), held a project BUILD kickoff meeting and provided information to the recipient and MoDOT. Sent guidance to the City and MoDOT on how to request a recipient change as the City of KC said they would like to have MoDOT administer the project and will plan to transfer the BUILD grant to them. Contacted MoDOT multiple times to check on the status of the recipient change request and also inquired about the status of the BUILD grant agreement template for planning projects. The BUILD Grant Agreement template for planning projects was received from HQ on 3/15/21 and it was forwarded to both MoDOT and the City of KC. As of 4/30/21, there have been 9 BUILD bi-weekly reports submitted. MoDOT and the City submitted the recipient change request and it was forwarded to HQ. OST approved the recipient change on April 16th, 2021. FHWA met with MoDOT and discussed the draft grant agreement on 4/29/21 and answered questions. FHWA Missouri coordinated review of the draft agreement with MoDOT and HQ with multiple coordination meetings. The draft BUILD grant agreement was finalized and sent to OST for review in July and is expected to be approved in October, 2021. Reviewed the consultant solicitation document issued by MoDOT. |  | 2021-09-21 18:53 | Perkins, Dawn (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
| J6P3510 | not assigned | J6P3510 | Scoping for ADA Transition Plan improvements at various locations in the St. Louis District. Potential DesignBuild project. | Various |  | ADA/Sidewalk | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:31 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | Not assigned | N/A | I-29 near Ambassador Drive, Permit Project | Potential Permit Project near KCI Airport at I-29 and Route D interchange near Ambassador Drive. | Platte |  | Interchange | Irving, Kevin (FHWA);#29 | No | TRUE |  | Local Considerations;#Other | Proposed Dogbone Roundabout interchange at I-29 and Rt. D with connection to a development property. | TSandO Approval |  | Meetings and Review and approval of a TS&O report. | [5 empty] | 2021-09-23 14:59 | Irving, Kevin (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3527 | 0641096 | J6I3527 | Scoping for interchange improvements at I-64 and I-70 interchange. Potential Design-Build. | St. Charles |  | Interchange | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping;#AJR Approval;#Design Exception Approval | [6 empty] | System to System Interchange / EIS reval | 2021-09-29 07:33 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
|  |  | J2P3347 | [5 empty] | No | TRUE | [11 empty] | 2021-09-23 13:17 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6P3661 | not assigned | J6P3661 | Scoping for corridor improvements from Rte. 100 to I-44. Project involves various bridges | Franklin |  | Corridor improvements | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans
MO | J6I3033 | not assigned | J6I3033 | Scoping for capacity improvements from I-70 to Rte. K. Includes bridges L0428,A1456 and A6754. | St. Charles |  | Widen and Resurface | Gonzalez, Felix (FHWA);#27 | No | FALSE | FY22 |  |  | Core Team Member;#Scoping | [7 empty] | 2021-09-29 07:40 | Gonzalez, Felix (FHWA) | Item | teams/fhwa-div-MO/Lists/Project Specific PoDI Plans