## Structure Exc.
206 STRUCTURE EXCAVATION CHECKLIST |  |  |  | Date:
Contractor: |  | Contract:
Route: |  | Project:
Item and Location:
QC FIELD INSPECTIONS
No. | Items |  | Yes | No | N/A
1 | Waste Disposal Agreement signed and copy provided to QA
2 | - HOLD POINT
3 | Excavated to plan depth, dimension and shape. Removed unsuitable material and free of loose material, also 206.3.2, and 206.4.2.
4 | - HOLD POINT
5 | Checked foundation integrity, stability, and for voids using test holes. (Reference CM 703.2.7)
6 | Document, get approval, and request change order in accordance to Sec. 206.6.2 if extra work is required to stabilize foundation.
7 | Foundation excavation protection "competent person" required. Evaluation of protective system prior to persons entering excavation.
8 | Footing is keyed 6" into rock and 18" into soft rock or shale. All cavities and crevices are filled in accordance with Sec. 703.3.39.
9 | - HOLD POINT
10 | If box culvert foundation is supposed to be on material other than rock and rock is encountered, remove 6" below bottom slab and replace with material similar to remainder of box.
11 | - HOLD POINT
12 | Foundation soil is dry at concrete placement. Excess water pumped out. See Sec 206.4.6 Footing Drainage.
Comments:
COFFERDAMS
No. | Items |  | Yes | No | N/A
20 | Proposed method accepted by engineer prior to work. Shall be within Right of Way.
21 | Clearance maintained. Tilted or moved cofferdams shall be corrected.
22 | Foundation excavation protection "competent person" required. Evaluation of protective system prior to persons entering excavation.
TEMPORARY SHORING
No. | Items |  | Yes | No | N/A
30 | Proposed method accepted by engineer prior to work. Shall follow submitted plan and consist of sheet pile, MSE walls or similar methods.
31 | Foundation excavation protection "competent person" required. Evaluation of protective system prior to persons entering excavation.
SEAL COURSE
40 | Proposed method accepted by engineer prior to work. If optional in contract, the Resident Engineer shall determine if necessary.
41 | Seal course construction shall follow approved plans. Verify adequate size and concrete thickness to offset hydrostatic pressure.
42 | - HOLD POINT
43 | Construction in prolonged cold weather can retard concrete set. Failure or leakage can occur at interface. Supplemental heating is suggested.
44 | Post curing and pumping requirements completed. Soft laitance, sediment, and loose material removed. High spots chipped off and low spots filled.
45 | - HOLD POINT
46 | Removal of sheeting or outer seal course form. Care shall be taken not to damage seal of footing.
Comments:
BACKFILL
60 | Method of backfill approved by QA rep and all requirements met.
61 | - HOLD POINT
62 | Backfill free from large or frozen lumps or other extraneous material
63 | Backfill placed in 6" lifts compacted to the same density as the adjacent roadbed.
64 | Do not backfill any structure until the concrete has reached the required strength.
65 | Bench slopes greater than 6:1.
66 | Backfill on opposing side of the structure shall remain equal in elevation. Do not unbalance fill on end bents until deck is poured and cured.
67 | Place drains at weep holes consisting of 5 CY of coarse aggregate, except when porous backfill is required.
68 | Maintain drainage away from backwall a minimum of 3' at a 6:1 slope until grade is completed.
POROUS BACKFILL
No. | Items |  | Yes | No | N/A
80 | Method of porous backfill approved by QA rep and all requirements met.
81 | - HOLD POINT
82 | Placed per plan and consolidated in 12" lifts. Placed so porous backfill will not be contaminated with other backfill.
83 | Determine if contamination prevention measures are included in contract. Geotextile fabric may be specified and shall be installed according to plans.
FLOWABLE BACKFILL
90 | Items |  | Yes | No | N/A
91 | Method of flowable backfill approved by QA rep and all requirements met.
92 | - HOLD POINT
93 | May be used in place of compacted backfill, but not porous backfill. Placed in accordance with Sec 621.
Comments:
QC Inspector Print Name: |  | QC Inspector Signature:
Company: