## 613
613 PAVEMENT REPAIR CHECKLIST |  |  |  | Date:
Contractor: |  | Contract:
Route: |  | Project:
Item and Location:
Standard Plans: 613.00X
MATERIALS
No. | Items |  | Yes | No | N/A
1 | Do all materials meet specification and is proper documentation supplied to MoDOT? (Epoxy mortar, Backer Rod, Bond Breaker, Curing Membrane)
GENERAL REQUIREMENTS
No. | Items |  | Yes | No | N/A
10 | Is the work scheduled such that all pavement removed is replaced that same day?
11 | Is the concrete placed in accordance with section 501 and 502?(See checklist for Section 501 and 502)
12 | Do the repaired areas provide a smooth ride?
FULL DEPTH PAVEMENT REPAIR
No. | Items |  | Yes | No | N/A
20 | Was all material taken out of the repaired area recycled or disposed of in accordance with this section? This may require written agreements with land owners.
21 | Was subgrade and aggregate base replaced and/or compacted?
22 | Were all tie bars and dowel bars installed properly?
23 | - HOLD POINT
24 | Was a MoDOT approved "pavement repair" mix used, and did test results yield specification compliant concrete?
CLASS A PARTIAL DEPTH PAVEMENT REPAIRS
No. | Items |  | Yes | No | N/A
30 | Was the joint milled out, cleaned and bonding agent applied?
31 | Was a bond breaker applied to exposed dowels?
32 | Were existing joints reestablished?
Comments:
CLASS B PARTIAL DEPTH PAVEMENT REPAIR
No. | Items |  | Yes | No | N/A
40 | Was unsuitable material removed?
41 | Was the patch tacked and filled in accordance with specifications?
DOWEL BAR RETROFIT
No. | Items |  | Yes | No | N/A
50 | Were dowel bar slots cut and cleaned to specified requirements?
51 | Were the dowel bars, expansion caps, and joint material properly positioned prior to placing the rapid set concrete?
52 | Was the expansion joint maintained and filled with hot pour joint sealer?
53 | Was the area closed to traffic for a minimum of 2 hours and the compressive strength reached 1,600 psi?
CROSS STITCHING
No. | Items |  | Yes | No | N/A
60 | Were the drilled holes of the proper size, of the correct angle, in the proper location and completely clean?
61 | Was the sufficient amount of epoxy dispensed into each hole?
62 | Was the tie bar inserted to the proper depth, and was the epoxy evenly distributed around the bar and extruding from the surface opening?
63 | Was the excess epoxy cleaned form the pavement surface leaving a flush finish?
64 | Was the repaired pavement kept free from traffic until the epoxy had cured in accordance with the manufacturers recommendations?
Comments:
QC Inspector Print Name: |  | QC Inspector Signature:
Company: