AASHTOWare Project Contract Payment Estimate Exception Override

Quick Reference Guide

Contract Payment Estimate Exception Overrides (overrides) allow a user to determine how Payment Estimate Exceptions are handled for a specific contract.

This Quick Reference Guide (QRG) will describe the policies and procedures for AASHTOware Project Construction & Materials (AWP).  Payment Estimate Exception Override settings are set by system administrators.  However, the “Insufficient Materials” Exception setting can be overridden at the Contract level by the RE per this QRG.  If the RE makes this change at the Contract level it will enable inspectors to override materials exceptions on estimates or the Contract.  Users will still need the CM Construction Project Manager role to Acknowledge or Override exceptions.

Manual line item adjustments should not be used to pay when a materials exception would withhold contractor pay.  To do so creates the risk of overpaying the contractor when the exception clears if that manual line item adjustment is not offset.  If the RE wants to pay, the materials exception must be overridden, which may require adding the Contract Payment Estimate Exception Override for “Insufficient Materials” exceptions.

By policy, MoDOT will not pay over contract quantity without an approved change order.  Accordingly, AWP will create an “Item Overrun” exception and this exception must be acknowledged to withhold pay exceeding contract quantity.   This does not work if the line has a materials exception, as AWP automatically overrides the “item overrun” exception, and this cannot be undone by the inspector.  If the materials exception is overridden, AWP will pay the full amount, including the overrun amount.  The inspector cannot acknowledge the “item overrun” exception to withhold only the overrun amount.

In this case (line with both an “item overrun” exception and a materials exception), MoDOT would prefer that the materials exception be acknowledged.  This will withhold contractor pay until the change order is processed (or the materials exception is satisfied so that the item overrun exception can be acknowledged) but gets away from using manual line item adjustments.  If the RE wants to pay the contractors on the current estimate, the materials exception must be overridden and a manual line item adjustment entered to withhold the overrun pay amount.  See Flowchart 1 for an illustration.

Summary:

- Item overrun – no materials exception

  - Acknowledge the “Item Overrun” exception

  - Withhold pay over contract quantity until change order is processed

- Item overrun –materials exception cannot be satisfied on the current estimate:

  - System automatically overrides the “item overrun” exception

    - User cannot change this to “acknowledged”

  - Materials exception can be acknowledged to withhold all pay for the line for the estimate

  - If the contractor is to be paid, the materials exception must be overridden

    - Manual line item adjustment will be needed to withhold the overrun pay quantity from the contractor

    - The line item adjustment will need to be offset after the change order clears.

Add Contract Payment Estimate Exception Override

Log on to AWP in the CM Resident Engineer role and navigate to the Contract Administration Summary for your contract.

Navigate to the Payment Estimate Exception Override component.

Click Select Contract Payment Estimate Exception Override

Select the Insufficient Material Payment Estimate Exception and Click Add to Contract Payment Estimate Exception Override

Click Save with the Progress setting as May be left Unresolved

Contract Materials Exceptions can now be overriden or acknowledged

Avoiding Overpayments from Overriding Materials Exceptions

If a manually entered line item adjustment used to offset withholding from a materials exception:

- Materials exception overridden (or satisfied) on next estimate:

  - AWP pays amount withheld due to materials exception

  - User will need to enter a negative line item adjustment to offset the total amount previously paid using manually entered line item adjustments

- Utilize the Line item Adjustments with Remarks Cognos Report to determine status of Materials Exception Payments

- Report location:  Public Folders ‎> AASHTOWARE ‎> Headquarters ‎> Contract - Estimates‬

- Run the report for your contract OR specific line item, as needed.

- Verify the balance of the Material and Material Credit adjustments for each line.

- Verify the offsetting payments.  This should be the Other Item Adjustment of PPPS (Partial Payment Pending Sample), however, we have found this to also be the Other Item Adjustment of MDPA (Material Discrepancy Payment adjustment)

- During the verification, should you find the values do not balance out to zero – you will need to create an Other Adjustment of the appropriate type (either MDPA or PPPS) to off-set the amount to zero.

- AWP Tracking of Item Quantity Paid with Materials Exceptions

  - Contractor paid by manually entered line item adjustment

  - Contractor paid by overriding materials exception

- Materials Exceptions on a line with no item quantity posted for the current estimate but item quantity posted on previous estimates with materials exceptions

    - Previous payments made to this line with a manually entered line item adjustment

  - Materials exception unsatisfied on current estimate

    - This example overpays the contractor $59917.05

  - Materials exception partially satisfied on current estimate

    - This example overpays the contractor $24316.24

  - Materials exception satisfied on current estimate

    - This example overpays the contractor $511.52

- Materials Exceptions on a line with item quantity posted for the current estimate and item quantity posted on previous estimates with materials exceptions

    - Previous payments made to this line with a manually entered line item adjustment

  - Materials exception unsatisfied on current estimate

    - This example overpays the contractor $23638.95

  - Materials exception partially satisfied on current estimate

    - This example overpays the contractor $37205.42

  - Materials exception satisfied on current estimate

    - This example overpays the contractor $37205.42

- Materials Exceptions on a line with item quantity posted for the current estimate but no item quantity posted on previous estimates

    - No previous payment made to this line with a manually entered line item adjustment

  - Materials Exception not satisfied on current estimate

    - This example does not overpay the contractor

- Materials Exceptions on on a line with item quantity posted for the current estimate and item quantity posted on previous estimates with materials exceptions

    - Previous payments made to this line by overriding materials exception

  - Materials exception not satisfied on current estimate

    - This example does not overpay the contractor

  - Materials exception partially satisfied on current estimate

    - This example does not overpay the contractor

  - Materials exception satisfied on current estimate

    - This example does not overpay the contractor

Flowchart 1

End of Quick Reference Guide