AASHTOWare Project Estimate

Quick Reference Guide

The Contract Pay Estimate is generated to provide payment to the prime contractor for all work performed during the estimate period.

This Quick Reference Guide (QRG) will describe the policies and procedures for Estimate Generation and Approval in AASHTOware Project Construction & Materials (AWP).

Prior to generating the estimate, the user should verify all DWR's have been compiled and approved in the diaries through the estimate period.  This may be done in the Daily Work Reports - History section.   All pay quantities contained in DWR's for the estimate period that have been authorized on a Diary will be included for payment.  Any DWR's that have not been authorized will not be included for payment until such a time they are authorized on a Diary.

IMPORTANT NOTE:  Refer to the end of this QRG regarding “Rejected Estimates” and what is required of the Project Office for contractor notification.

The user must be logged on as a Construction Project Manager to generate Progress estimates.

Estimate Generation

Log on to AASHTOWare Project (AWP) in the CM Project Manager role and navigate to the Contract Progress for your contract.

Select your contract from the Search window

Now select Payment Estimates.

Select the Add Payment Estimates button

Select the Type of Estimate to generate (see below regarding types of estimates).

There are 3 types of estimates to choose:  Progress, Final, and Supplemental.

- Progress Estimates are generated with period end dates of either the 1st or the 15th (See EPG 109.7.1), with the exception of the ends of the State Fiscal Year (June 30th) and the Federal Fiscal Year (September 30th).  Estimates may be generated at any time prior to the estimate ending date in order to resolve exceptions or check quantities. Note:  Progress estimates may be suspended when work has not been performed in the pay estimate period and no payment is due to the contractor.  The project office should notify the Financial Services office that no work was performed on the contract and no estimate will be produced for the current pay period and/or future pay periods until work resumes.

- Final Estimates are generated at the end of the project, once it has been verified that all DWR’s are correct and have been authorized.  Final Estimates are generated at the CM Resident Engineer role.  Reference the AWP_CO_Estimate_Final QRG for further details.

- Supplemental Estimates are only used if an error is found after the final approval of the Final Estimate type.  This type will only be selected if directed to do so by a System Administrator.

The Period Begin Date is automatically populated by AWP.  The first Progress Estimate Period Begin date for every contract will be the Award Date of that contract.  Thereafter, the period begin date is the day following the last Progress Estimates’ Period End Date, normally the 2nd and the 16th of each month, unless the progress estimate follows the end of the State or Federal Fiscal Year.

Verify the Period End Date for the estimate.  Note:  AWP Default is for the 1st and the 15th.  You will need to adjust the Period End Date for Progress estimates produced at the end of the State (June 30th) or Federal (September 30th) Fiscal Year.

Select the Add Payment Estimate button

AWP will begin generating the estimate, you will see the Saving process begin, then display a message the Add Payment Estimate Process started.  Acknowledge the message by selecting the X in the right hand corner.

Verify successful completion of the estimate by selecting the Process History Overview section.  Select the link from the top of the Add Contract Payment Estimate window.

You will see the status of the estimate generation process:

It may take a few minutes for the generated estimate to display.

Open the AddPaymentEstimate.log to verify successful estimate generation.  This is important to review – especially if you do not see the generated estimate in the Contract Progress window.

Review the message, then close the window.  Any warnings (such as Obsolete Code table values) are normal and does not prevent the estimate from generating.  Any errors do, and will need to be corrected.

Also review the Error.log.  Any errors will need to be corrected.

Select the Previous button, and select the Contract Progress Summary for the contract.

Select the Payment Estimates tab.

Select the estimate Number link

This navigates you to the Contract Payment Estimate Summary window.  This is where you will manage the Exceptions, Milestones, Project Distribution, Contract Adjustments, Item Adjustments and Approval and Tracking of the Estimates..

General Tab

The General tab displays the following read-only information regarding the payment estimate:

Pay Amount This Contract Payment Estimate - Total amount paid for the current payment estimate, including item-level adjustments.

Total Pay Amount (All Payment Estimates) - Total amount paid for all of the payment estimates for the contract.

Transfer to Accounting Date - The date entered by MoDOT to indicate when the payment estimate is marked as ready to transfer to Financial Services.

Accounting Received Date - The date entered by MoDOT to indicate when Financial Services received the payment estimate.

Transaction Number - The check number for the payment estimate.

Transaction Date - The date on the check for the payment estimate.

Prime Contractor – The contractor who was awarded the contract.

Current Contract Amount - The awarded contract amount plus or minus any approved change orders.

Contract Percent Complete - The percentage of the contract time that has been completed, based on its current time scheduled and the charges processed for the contract time, or the time that has passed since the start of the contract time. The calculation to determine this percentage depends on the time type.

Created By - The name of the person who generated the estimate.

Created Date - The date and time this estimate was added to AWP.

The lower portion of the component displays the information available on the Contract Payment Estimate Summary report. The report header displays current values in these fields:

Contract – The Contract ID for this contract.

Payment Est Number – The payment estimate number.

Period End Date - The Period End date for this estimate.

Status – The current status of the estimate.  This could be Draft, Pending, Rejected or Approved.

Type – The type of estimate.  This could be one of the four types.

Below the report header, the report lists three columns of data: Previous Pay Est, This Pay Estimate, and Total (All Pay Est). In each column, information is displayed in these fields:

Posted Item Pay – Amount of payment on the estimate for the items.  This doesn’t include any item-level adjustments

Gross Item Adjustments - Total gross item adjustments of all types on the current estimate.

Gross Item Pay - Item amount paid for the payment estimate, including item-level adjustments.

Participating Item Pay - Total participating item amount paid on the payment estimate.

Non-Participating Item Pay - Total non-participating item amount paid on payment estimate.

Retainage - The total retainage amount paid on the payment estimate.  MoDOT doesn’t automatically withhold retainage on estimates.

Cash Retainage - Total cash retainage amount paid on the payment estimate.

Non-Cash Retainage - Total non-cash retainage amount paid via securities and escrow on the payment estimate.

Incentive - The total incentive amount paid on the payment estimate.

Disincentive - Total disincentive amount paid on the payment estimate.

Liquidated Damage - Total liquidated damage amount paid on the payment estimate.

Other Contract Adjustments:

Previous Pay Est - Total contract adjustments of this user-defined type for all previous estimates.

This Pay Estimate - Total contract adjustments of this user-defined type for the current estimate.

Total (All Pay Est) - Total contract adjustments of this user-defined type for all estimates (previous and current).

Total Pay Amount - Total amount paid for the payment estimate, including item-level adjustments.

Item Adjustment Type (Column Heading) Identifies the type of item adjustment listed below.

Overrun

Previous Pay Est - The total of overrun adjustment amounts summed for this project on the current estimate.

This Pay Estimate - The total of overrun adjustment amounts summed for this project on the current estimate.

Total (All Pay Est) - The total of overrun adjustment amounts summed for this project on all estimates (previous and current).

Price

Previous Pay Est - The total of price adjustment amounts summed for the contract on all previous estimates.

This Pay Estimate - The total of price adjustment amounts summed for the contract on the current estimate.

Total (All Pay Est) - The total of price adjustment amounts for the contract on all estimates (previous and current).

Construction Stockpile

Previous Pay Est - The total of construction stockpile adjustment amounts summed for the contract on all previous estimates.

This Pay Estimate - The total of construction stockpile adjustment amounts summed for the contract on the current estimate.

Total (All Pay Est) - The total of construction stockpile adjustment amounts for the contract on all estimates (previous and current).

Other Item Adjustments:

Previous Pay Est - The total other user-defined item adjustment amounts summed for this contract for all previous estimates.

This Pay Estimate - The total other user-defined item adjustment amounts summed for this contract on the current estimate.

Total (All Pay Est) - The total other user-defined item adjustment amounts summed for this contract for all estimates (previous and current).

Gross Item Adjustments:

Previous Pay Est - The total gross item adjustments of all types summed for the contract on all previous estimates.

This Pay Estimate - Total gross item adjustments of all types on the current estimate.

Total (All Pay Est) - Total gross item adjustments of all types for the contract on all estimates (previous and current).

Notes Tab

Navigate to the Notes tab on the Contract Payment Estimate Summary.  This contains a list of notes added by the user for the payment estimate. MoDOT does not require notes to be added to the payment estimate.  This feature is to allow the user to add a remark about an estimate.  To add a new note for the payment estimate, click the New button

AWP adds a blank row. To save the new row, you must enter a remark in the Payment Estimate Note field. AWP automatically enters your name and the current date in the Created By and Created Date fields once the remark is saved.

Note:  You can modify or delete a note only if you are logged in with the account used to create the note.To delete a note from the payment estimate, select Delete from the Actions menu on the note row. The system shades the row gray to indicate it is marked for deletion. To reverse the delete action, click the Undo button.

To save your changes, click the Save button.

Exceptions Tab

The Exceptions tab on the Contract Payment Estimate Summary lists exceptions and discrepancies generated for the payment estimate. You can view the list of exceptions and address them as needed to allow approval of the payment estimate. You address an exception by changing its status to Acknowledged or Override.  Do not leave any Exception as Unresolved.

Note:  You can resolve exceptions by completing sample records and/or other resolutions.  If this is the case, be sure to Recalculate Exceptions to remove any from the estimate BEFORE you Acknowledge the exception.  Recalculate will remove any of the resolutions you made for each exception.  In addition, we recommend to Recalcualte Exceptions as the first order of business when opening this tab.

AWP reconciles any exception deduction EACH estimate period.  For example – if an exception for “Insufficient Materials” withheld on a line item in the amount of - $10,000 last estimate period,  the very first thing that happens on the current estimate is a Material Credit for a +$10,000 will be shown.  Then, the system determines if there are any further exceptions on this estimate.  If the materials requirements are still not satisfied, it will then take the appropriate dollar amount back.  This can change based on some or all of the testing requirements being satisfied, or if additional quantity was posted during this estimate period.

AWP allows multiple exceptions on a line to be Acknowledged or Overridden.  For instance, if a pay item has been paid over plan quantity and also has a Material deficiency, there will be 2 exceptions generated, one for the Insufficient Materials and one for the Item Overrun.  The preferred method for resolution is Acknowledge Item Overruns and then Override the Insufficient Materials exception.  However, it is allowable based on District policy to Override (pay) the Item Overrun exceptions and Acknowledge (withhold payment) the Insufficient materials exception. Either way prevents over-penalizing the contractor.  In no cases should the Insufficient Materials Exception and the Item Overrun Exception be set to Acknowledged for the same line item on the same estimate

From the Action Menu in the Tasks area, select “Recalculate Exceptions”.

All exceptions initially produced by an estimate will come through with the status of Unresolved.

Unresolved status means the exception has occurred and need to be addressed.

Acknowledged status means you agree with the exception and you want the money withheld by the Item Adjustment created from the exception.

Overridden is a status which means you do not want the money witheld.  For more information regarding Item Adjustments, please reference the AWP_Item_Adjustments QRG.

You can only change the status of an exception only when the payment estimate is in Draft status. When the payment estimate is changed to a status other than Draft, exceptions for the payment estimate can no longer be modified.

Each row on the Exceptions tab includes an Actions button and current values in these fields:

Except ID - Unique identifier for a payment estimate exception.

Payment Estimate Exception - Identifies the type of payment estimate exception that will be generated for the specified condition when a payment estimate is generated.

Status - Status of the Exception.  It could be Unresolved, Acknowledged.  Do not change a system status of Overridden.

Drop-down the exception row to display information in these fields:

Description – Text describing the Exception type.

Status – Status of the Exception.  It could be Unresolved, Acknowledged, or Overridden.

The text in the Description field is generated by the system and cannot be modified. In the Status field, select Acknowledged.

TIP:  When you have multiple Exceptions to Acknowledge, you can use the Range Fill from the Status drop down section to Acknowledge all of the Exceptions at once.  Select Acknowledge for the first Exception – then drop down the Status to fill the rows you want (all Displayed or All Rows). Be sure to Save when complete!

When you are finished making changes, click the Save button.

Note: Once an exception is saved with a status of Acknowledged, you cannot change the exception status.

Exception Types which must be addressed on Progress Estimates:

These must be resolved:

Missing Start Time

These must be acknowledged:

Exceeded Available Time - Note:  if Liquidated Damages are to be assessed, this date will occur after the Original or Current Contract Completion date.  Please contact ReDEV to have the "Exceed Overall Contract Time" exception rule modified for the contract.  Once changed, recalculate this exception and it will be removed.

Exceeded Calendar Time - Note:  if Liquidated Damages are to be assessed, this date will occur after the Original or Current Contract Completion date.  Please contact ReDEV to have the "Exceed Overall Contract Time" exception rule modified for the contract.  Once changed, recalculate this exception and it will be removed.

Exceeded Completion Date - Note:  if Liquidated Damages are to be assessed, this date will occur after the Original or Current Contract Completion date.  Please contact ReDEV to have the "Exceed Overall Contract Time" exception rule modified for the contract.  Once changed, recalculate this exception and it will be removed.

Insufficient Materials

Item Incomplete

Item Overrun (when it stands alone and there is not an Insuffucient Materials Discrepancy for the same line number)

Pending or Draft Daily Work Reports

These may be Overriden with RE approval

Insufficient Materials

Item Overrun (based on District policy and there is an Insuffucient Materials Discrepancy for the same line number which has been Acknowledged)

These are Not Calculated or Displayed, but would need to be resolved on the Final Estimate

CD  ,Contract Completion Date Missed

MD  ,Milestone Completion Date Missed

Construction Stockpile Balance

NOTE:  There may be circumstances where an Insufficient Materials exception should NOT be included on the estimate per RE approval.  In this case, the Insufficient Materials exception MUST be overridden.  Manual Line Item Adjustments shall NOT be used to compensate the contractor for work completed.  There is risk of overpaying the contractor when the exception clears if the manual line item adjustment is not offset at that time.  Additionally, tracking the manual line item adjustments is an administrative burden.

For more information, please reference the AWP_Item_Adjustments.

Time Charges Tab

The Time Charges tab on the Contract Payment Estimate Summary contains a list of contract times associated with the contract.  When a Time Charge event occurs, there will be a row of information that contains and actions button and current, read only values in these fields:

Time ID - Time Description - Unique identifier for a contract time, including the contract time description.

Time Type - The type of time information recorded in this contract time record (Available Time, Calendar Time, Completion Date, Informational, or Recurring).

Time Unit - The type of unit being used to measure the proposal time, either Days or Hours.

% Compl - The percentage of the contract time that has been completed, based on its current time scheduled and the charges processed for the contract time, or the time that has passed since the start of the contract time. The calculation to determine this percentage depends on the time type.

Current Time Charged - Number of time units charged to the contract time for the current estimate.

More information is available in the AWP_Contract_Times QRG and the AWP_Milestones QRG.

ProjectsTab

The Contract Payment Estimate Project tab lists information about all of the payment estimates recorded for the selected contract project. You can access the summary by navigating to the Contract Payment Estimate Summary, clicking the Projects tab, and then clicking the appropriate Project ID.

For the selected contract project, the component displays read-only values in the fields.

The lower portion of the component lists three columns of data: Previous Pay Est, This Pay Estimate, and Total (All Pay Est). In each column, the component displays data for the project in the fields.

All of the fields in this window are at the project level, and the field descriptions are the same as what is listed on pages 6 through 8 of this QRG.

You can access any additional projects by using the Drop Down list in the left hand corner of the window, or the Page Advance in the right hand corner of the window.

Items

The Items tab on the Contract Payment Estimate Summary displays read-only information about items included in the selected payment estimate. You can locate a specific item by entering criteria in the Quick Find search box. You can also select a value in the Items field to filter the list and show only payments made during the current period. The system displays rows of payment estimate items that match your criteria.

Each item row contains an Actions button and current values in these fields:

Project – Descr – Lists the project number and brief description of the project.

Category – Descr – The category of the line number along with a brief description of the category.

Proj Item Ln Num – Line Number for the project.  Same as Contract Item Ln Num..

Contract Item Ln Num – Line number for the project  Same as Prj Item Ln Num.

Ref Item ID – Item code of the Line Number.

Description – Description of the item.

Supplemental Description - Used with MISC items, further describes the item.

Pay Amt This Pay Est – Dollar amount paid for the item on this current payment estimate.

You can expand an item row to display read-only values in these fields:

Posted Quantity This Payment Estimate – The quantity of the item that was installed or posted for the current payment estimate.

Pay Quantity This Payment Estimate - Quantity of the item paid on the current payment estimate, including item-level adjustments.

Difference in Posted/Pay Quantity This Pay Estimate - The difference between the installed amount and paid amount for the item on the current payment estimate.

Calculated Overrun Quantity This Payment Estimate - The quantity that exceeds the maximum overrun quantity for the item on the current payment estimate.

Total Posted Quantity Previous Payment Estimates - Total installed quantity for all previous payment estimates for this contract item.

Total Pay Quantity Previous Payment Estimates - Total paid quantity for all previous payment estimates for this contract item.

Posted Amount This Payment Estimate - The dollar amount posted for the item in the current payment estimate. Calculated as the installed quantity multiplied by the unit price for the item.

Pay Amount This Payment Estimate - Dollar amount paid for the current payment estimate, including item-level adjustments.

Difference in Posted/Pay Amount This Pay Estimate - The difference between the installed amount and paid amount for the item on the current payment estimate.

Total Adjustment Amount This Payment Estimate - Total of all adjustment amounts for the item on the current payment estimate.

Total Posted Amount Previous Payment Estimates - Calculated as the Total Posted Quantity from previous payment estimates multiplied by the unit price for the item.

Total Pay Amount Previous Payment Estimates - Calculated as the Total Paid Quantity from previous payment estimates multiplied by the unit price for the item.

Within an item row, you can expand the Contract Project Item section to view information in these fields:

Item Description – Description of the Line Item.

Unit of Measure – Units of measure for the item.

Bid Quantity – The original number of the units of the item.

Current Quantity – The current number of units of the item, adjusted by any approved Change Orders.

Pending Change Order Quantity - The change order quantity for the contract project item awaiting approval.

Quantity Posted To Date Appr DWRs - The total of all quantity posted entries for an item on one or more approved DWRs, regardless of whether they are included on an estimate.

Spec Book – 2-digit year for the spec book associated to the Ref Item ID (Item Code).

Supplemental Description - Used with MISC items, further describes the item.

Unit Price - The unit price for the item at the contract project level.

Bid Quantity Extended Amount - The total original quantity of units bid at the time of award for this project item, calculated as the product of the Bid Quantity multiplied by the Contract Item Unit Price.

Current Quantity Extended Amount - The bid amount or initial change order amount plus or minus all approved amounts via change orders (increased or decreased quantities).

Pending Change Order Amount - The change order amount for the contract project item awaiting approval.

Quantity Paid To Date - The total of all Quantity Posted entries for an item on one or more DWRs, regardless of whether the quantities are authorized and or included on a payment estimate.

Within an item row, you can also expand the Payment Estimate Exceptions section to view rows of exceptions recorded for the item. Each exception row displays information in these fields:

Exception ID - Unique identifier for a payment estimate exception.

Payment Estimate Exception- Identifies the type of payment estimate exception that was generated.

Status – The current state of the contract payment estimate exception (that is, Unresolved, Acknowledged, or Overridden).

Contract Adjustments & Item Adjustments

Specific details explaining these tabs are clearly defined in the AWP_Contract_Adjustments, AWP_Construction Stockpiles and the AWP_Item_Adjustments QRGS.  Please reference them for specific adjustments on your estimate and how to maintain and/or add them.

Final Estimates have three approval levels – CM Resident Engineer, CM Final Plans and CM FS Estimate Approval.

Submit Estimate for Approval

From the Contract Payment Estimate Summary window, select the Actions menu.  In the Tasks section select Submit for Approval.

Once the estimate has processed sucessfully – the CM Project Manager role will still need to approve the estimate.  See below.

Estimate Approval Decisions

The first level (CM Project Manager) and will need to submit for approval from the Actions menu and then approve the estimate from the Actions menu.

Before you approve the estimate, verify the payment matches in these 2 areas – Gross Item Pay for this Estimate and Pay Amount This Contract Pay Estimate.  If these amounts do not match – do not approve the estimate.  Set it back to Draft.  It will need to be deleted and regenerated because something is not right.

Subsequent levels of approval can use the Contract Payment Estimate Overview from the Main Home Page to Approve or Reject the estimate.  Log on to AWP with the correct Role (RE or Financial Services) and navigate to the Contract Payment Estimate Overview component on the Home Page.

From the filter – choose “All Pending Est.”

A list of the contracts that are Pending will appear. This will be for any level pending status so you will see ones you just approved.  Note:  If you use the Draft Filter you will see the estimates that have been generated but not approved by the Project Manager

From this window, click on the Estimate Number to open.

When the estimate opens, verify the payment matches in these 2 areas – Gross Item Pay for this Estimate and Pay Amount This Contract Pay Estimate.  If these amounts do not match – do not approve the estimate.  You will need to Reject is so the PM can change it to Draft and then delete it.  The estimate will need to be regenerated because something is not right.

Select the Approval Tracking tab and verify the PM Level has approved the estimate:

When you are certain to approve, Select the Actions Menu and Approve

Note:  Negative Progress estimates will continue to be generated and approved at the PM and RE levels.  The Controller’s office will reject negative progress estimates.  The next estimate will then include the items and/or adjustments from the rejected estimate.  This will continue until positive payment is achieved.

Rejected estimates will need to be submitted to the Prime contractor by the Project Office as they are not included in the Web Estimate generation.  Produce the Cognos report AFTER the Controller’s Office has Rejected the estimate.  This will inform the contractor of why the estimate was rejected by displaying what pay items were paid that period, what items were retracted, as well as list any other contract adjustments.  The email should also be cc:’d to any Subcontractor who had a pay quantity adjustment (positive or negative) or contract adjustment on the rejected estimate.   This is necessary in order to provide payment information to ensure the Prime and Subcontractors stay in compliance with the Missouri Prompt Payment law.

Once you have produced the Rejected Cognos report and saved it to eProjects for your Contract – you will need to change the status of the estimate to Draft in order to Delete the estimate.  This will allow you to generate the estimate on the next pay cycle.

The Controller’s office can approve a negative Final estimate and will generate a bill to the contractor.

Approval Tracking

Once the first approval is made on the estimate, this window will populate as it goes through the estimate approval process.

Progress Estimates have three approval levels – CM Project Manager, CM Resident Engineer and CM FS Estimate Approval.

Notes about Estimate Generation

Once you have generated the estimate, you can view the status of the estimate generation by selecting the Process History Overview link at the top of the window.

When complete, two log files will be generated:  Error.log and AddPaymentEstimate.log.  You can click on the AddPaymentEstimate.log to veify the estimate processed.

Estimates cannot be re-generated without having to delete the previously generated estimate.  Should a user not delete a previously generated estimate, the AddPaymentEstimate.log will show the following message:

Users can delete the estimate from the Contract Payment Estimate Overview window’s Action menu for the estimate:

Final Estimates

Final Estimate instructions are found in the AWP_CO_Estimate_Final Quick Reference Guide.

End of Quick Reference Guide