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DRAFTER’S NOTE:  IT IS DIFFICULT TO PRESCRIBE COMMON LANGUAGE FOR THIS APPLICATION, HOWEVER THE LANGUAGE BELOW IS BEING PROVIDED AS AN EXAMPLE FOR ROAD CLOSURE APPLICATIONS.

1.0  General  This provision will govern the Road Closure of _____________.

2.0  Description  This provision will describe the timelines needed for proper notification of the traveling public ahead of a road closure.

3.0  Schedule Requirements  As soon as a tentative closure date can be determined it shall be submitted to the engineer for approval, but not less than 3 weeks prior to the closure date. The closure date shall be confirmed at least 16 days prior to the day of the road closure. 14 days prior to the closure, changeable message boards shall be placed notifying drivers of the date of the closure.

3.1  The contractor shall also provide a tentative opening date at least 2 weeks prior to closing and shall communicate to the engineer promptly any items which will result in a change in the schedule of the road closure.

INCENTIVE / DISINCENTIVE IS ENCOURAGED IN SITUATIONS INVOLVING HIGH VOLUME ROADWAYS.

4.0  Basis of Payment.  No direct payment will be made for this provision.





